## Slide 1: Digitization Workflow

## Slide 2
Digitization
Workflow
Prepare
Material
Determine
& Document
Benchmarks
Assign
Device
Profile
Calibrate/
Characterize
Devices
Scan
Determine
Filenames
Convert
to Working
Space
Apply
Photoshop
Adj
Archive Derivatives
Quality
Control 1
Archive
Masters &
CM target
Quality
Control 2

## Slide 3: Phase I: Set the Stage
Define Goals, including
  Desired outcomes for source material
  Functional requirements for digital assets
Determine selection criteria
Assess copyright
Assess physical characteristics of material
Define audience; establish use cases
Determine preservation plan
Secure funding

## Slide 4: Phase 2: Scope the Project
Determine material requirements, including conservation needs
Set Imaging Parameters
Define Master vs. Access Images
Determine Quality Control Metrics
Determine Storage Requirements
Set Metadata Requirements
Determine Delivery Method
Establish Preservation Plan
Project Assessment

## Slide 5: Phase 3: Implement Workflow
Coordinate Overlapping Processes for conservation, digitization, and metadata
Assign roles & responsibilities
Hardware & space considerations
Establish digitization workflow
  Scanner settings
  Color Management
  Archiving
  Post-processing
  Quality Control
Write training guides
  Scanning & Post-processing
  Quality Control

## Slide 6: Recap: Aligning Document Attributes with Digital Requirements
Identify key document attributes
  Tone, color, and detail
Characterize them, if possible through objective measurements
Determine quality requirements and tolerance levels
Translate between analog and digital and between scanning requirements and scanning performance

## Slide 7
Establishing the workflow
Benchmarks / Scanner Settings
Filenames
Color management
  Characterize scanners
  Calibrate monitors
Photoshop
  Assign device profile/ Convert to working space
  Image adjustment (levels, curves)
  Image repair (clone tool, selection, layers)
  Batch processing

## Slide 8: Determine Imaging Benchmarks
  Resolution / PPI-DPI
  Bit-depth
  Color Space (master vs. derivative)
  File Formats (master vs. derivative)
  Compression Techniques (if any)
  Filenaming
And Scanner Settings…
  Document type
  Exposure (auto exposure or no?)
  Quality
  Color management (on or off?)

## Slide 9: Workflow Coordination
Not necessarily a linear process
Allow for overlapping workflows for conservation, digitization, and metadata creation
Determine rough flow of events (conservation-digitization-metadata), but allow for flexibility
Establish contingency plans

## Slide 10: Roles & Responsibilities
Provide clear guidance to staff
  Defined job parameters
  Expectations for deliverables (time and quality)
Avoid single points of failure
  Have back-ups for staff

## Slide 11: Hardware Considerations
  Capture device
    One size doesn’t fit all- flatbed, overhead, bound book, slide/film scanner
    Quality
    ICE or ROC?
    Color management devices
  Computer
    Memory & Speed
    Back-up for local drives
    Archiving
  Network
    Gigabit line

## Slide 12: Space Considerations
Temperature/humidity requirements
Space for multiple devices allows for multi-tasking
No windows near overhead devices (mixed lighting)
Ability to turn off overhead lights

## Slide 13
Digitization
Workflow
Prepare
Material
Determine
& Document
Benchmarks
Assign
Device
Profile
Calibrate/
Characterize
Devices
Scan
Determine
Filenames
Convert
to Working
Space
Apply
Photoshop
Adj
Archive Derivatives
Quality
Control 1
Archive
Masters &
CM target
Quality
Control 2

## Slide 14: Create training guides
Scanning guides should include:
  Capture device settings (auto-exposure, color management on/off, etc?)
  Dpi
  Color space
  Processing specs for master & derivative images
  Calibration methods
  Filenames
Quality control
  Methodology/ frequency
  Image settings

## Slide 15: Digitization Strategies
Batch / Automate as often as possible
Quality Control early and often
Benchmark for project goals
Write effective training guides and keep them located next to scanning devices

## Slide 16: Phase 3 Documentation
Overall workflow plan with contingencies
Roles & responsibilities
Hardware & space requirements
Digitization workflow & parameters
Scanning & QC Guides