## TIMELINE & MILESTONES-TEMPLATE
Appendix B - Timeline and Milestones
Project Name: Instruction web site
Vision of Success:
|  | March April | [5 empty] | May - June |  |  |  |  | June - July
|  | 11 | 30 | 30 | 15 | 25 |  | 3 | 15 | 17 |  |  |  | 1 |  | 15 |  | 1
Major Activities
Objective 1 | Activity 1 | 1 | 2 | 3
| Activity 2 |  |  |  | 4 | 5 |  |  |  |  | 6
| Activity 3 | [6 empty] | 7 | 8 | 9
Objective 2 | Activity 4 | [8 empty] | 10 | [5 empty] | 11
| Activity 5 | [12 empty] | 12 |  | 13
Objective 3 | Activity 6 | [16 empty] | 14
| Activity 7 | [5 empty] | 15 |  |  |  |  | 16 |  |  | 17
[17 empty] | Milestones | 17
Objective 1: | CUL instruction web site
Activity 1: | Design and Content
Milestones: | 1 Agree on components
2. Carla to present mockup (design)
3. Camille, Kaila, Jaron draft content
Activity 2: | Design with Content for Internal Review
Milestones: | 4. Draft with content for internal review
5. Draft with changes
6. Second internal review - okay to go to stakeholders?
Activity 3: | External review
Milestones: | 7.Share with taskforce and PSEC instruction
8. Changes due from the groups and Janet
9 Collate changes
Activity 4: | Buidling the site
Milestones: | 10. First 12 Tier 1 Workshops completed
11. Tier 2 Follow up workshops completed (12 workshops)
Activity 5: | User testings
Milestones: | 12. Coordinate user testing
13. Collate changes from user testing
Activity 6: | Launch and Ongoing Maintanence
Milestones: | 13. Plan in place for multi-platform collection of usage data.
14. Launch
Activity 7: | Conduct evaluations
Milestones: | 15. Year 1 analysis of progress and TEEAL use.
16. Year 2 analysis of progress and TEEAL use.
17. External evaluation is conducted and completed.