## Slide 2: RDA Implementation & Review
November 2011
  Local guidelines for working with incoming RDA records for copy catalogers established
  Catalogers will review training materials on the wiki & RDA Toolkit
  New macros and input templates will start being created
December 2011
  Original catalogers will create at least 3 new RDA bibliographic records
  Copy catalogers will enhance & edit existing and incoming RDA/AACR2 hybrid records
  All catalogers will talk with their reviewers to set a workable review process.
  2CUL RDA Listserv will be operational for RDA policy questions, Q-tips, etc.

## Slide 3: RDA Implementation & Review
January 2012
  Original catalogers will create RDA records at least one day per week and give records & resources to their reviewer
  Two meetings per month on RDA implementation will be devoted to talking about common mistakes, lessons learned, example records, local implementation decisions.
February & March 2012
  Implementation & review period continues; more records created
  Constant assessment of what is needed to make RDA operational full time
  More local policies established
  Quality control continues of incoming RDA/AACR2 hybrid records

## Slide 4: RDA Records Review
Jean will review Pam, Roswitha, Tracey, Law Catalogers
Sarah will review Yen, Yelena, Apikanya
Cecilia will review Ali, Anne, Margaret, Teresa
Tracey will review Sung Ok, Beth, Jean
Ardeen will review Sarah, Cecilia
Cynthia will review Greg, Mei-hsi, Margaret C., Swe Swe

## Slide 5: Bibliographic Framework Transition Initiative
The Library of Congress released the initial plan for its Bibliographic Framework Transition Initiative.
The plan is available at: http://www.loc.gov/marc/transition/news/framework-103111.html
Additional Links
  Bibliographic Framework Transition Initiative Website http://www.loc.gov/marc/transition/
  Bibliographic Framework Transition Initiative Listserv http://listserv.loc.gov/listarch/bibframe.html
  Working Group on the Future of Bibliographic Control Website http://www.loc.gov/bibliographic-future/

## Slide 6: Requirements for a New Bibliographic Framework Environment
Broad accommodation of content rules and data models
Provision for types of data that logically accompany or support bibliographic description
Accommodation of text data, linked data with URIs instead of text, both
Consideration of the relationships between and recommendations for communications format tagging record input conventions, and system storage/manipulation
Consideration of the needs of all sizes and types of libraries
Continuation of maintenance of MARC until no longer necessary
Compatibility with MARC-based records
Provision of transformation from MARC 21 to a new bibliographic environment
 Approach and Timetable