## SummaryofOptions
| Estimates in hours |  | Phase 1 |  |  |  | Phase 2 |  |  |  | Phase 3 |  |  |  | All phases
Categories | Low | High | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult
Identity Management and IT Security | 580 | 1120 | 33000 | 37500 | 62000 | 75000 | 0 | 0 | 0 | 0 | 33000 | 37500 | 62000 | 75000 | 33000 | 37500 | 62000 | 75000
Direct, Core Workday transactional impact | 9320 | 16295 | 133250 | 1014875 | 223750 | 1815625 | 326750 | 193125 | 605750 | 384375 | 460000 | 1208000 | 829500 | 2200000 | 786750 | 1401125 | 1435250 | 2584375
Data delivery, warehouses and BI | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General technical and project management | 5425 | 10780 | 191755 | 0 | 376510 | 0 | 172755 | 0 | 345510 | 0 | 364510 | 0 | 722020 | 0 | 537265 | 0 | 1067530 | 0
Totals | 15325 | 48195 | 360000 | 1050000 | 660000 | 1890000 | 500000 | 190000 | 950000 | 380000 | 857510 | 1245500 | 1613520 | 2275000
Notes: | [8 empty] | Total Low, both phases | ----> | 2103010
CU Rates |  | 100 | [6 empty] | Total High, both phases | ----> | 3888520
Consultant Rates |  | 150
Percentage break down for 06/2011 - 07/2012 and 07/2012 - 01/2013 can be found on the details tab.
| Due date | Low Estimate-Staff | Low Estimate - Consulting | High Estimate Staff | High Estimate Consulting
HR Only | July 2012 | 360000 | 1050000 | 660000 | 1890000
Kronos Capital Project | July 2013 | 150000 | 540000 | 150000 | 540000
Payroll and Data delivery | July 2013 | 500000 | 190000 | 950000 | 380000
lower limit (totals of low estimates) | 2790000
upper limit (totals of high estimates) | 4570000
a. Switch COLTS users to Kronos, licenses & VMS - $540K
b. Kronos technical assistance - $500K to $1M
c. Project manager - $150K
FY 12
FY13

## NOTES
Changes made:
Time collection: | The Kronos license and VM fees and upgrade project are entirely excluded as a separate project.
The costs still exist, and this is a prerequisite, but the costs will be counted separately in another project.
Data delivery: | All efforts concerning the HR-Payroll data warehouse and other warehouses and systems downstream of them is now deemed optional although the business impact to units and their decision making based on that data is unknown.
More analysis is recommended to determine use of the data and to prioritize requirements.
The high estimate is purely based on the effort (hours) spent to date and projected for the completion of the KDW.
HR has clearly stated they want a data warehouse, and have also said they don't have requirements.
Integration of People data: | Rather than having EMN, Library and the IdManagement tools connect with Workday we would keep PeopleSoft as intact as possible to minimize changes to them.
PeopleSoft stays as the 'People Data Hub'.
Architecturally and for long term support it is better, but the financial implications of this change are rather small.
Creating services for applications to get that data rather than using the high number of direct connects should be done, but is out side the scope of Workday.
Reserves for impacts to 'other' systems: | We believe there are other systems that will be impacted than those listed.
They will either be allowed to fail or require separate funding to remediate.
Consulting for Payroll: | Eliminated. If Payroll wants additional consulting for help with tools such as Windstar that CIT does not currently support it will require separate funding.
Technical Project Management: | It was moved up into the 'General technical and Project Management' category.
Changes contemplated but not made to the estimates and options:
Replace Id. Mgmt software: | This replaces campus wide single authentication infrastructure.
Analysis of the effort and the impact will require a project. A quick assessment is that this is a very large risky project of unknown size that requires more work to understand the size.

## Charts
High Estimates for each option |  | 2012-07-01 | 2013-01-01 | Defered
Identity Management and IT Security | High Cost/Staff | 62000 | 0 | 62000
| High Cost/Consult | 75000 | 0 | 75000
Direct, Core Workday transactional impact | High Cost/Staff | 223750 | 605750 | 829500
| High Cost/Consult | 1815625 | 384375 | 2200000
Data delivery, warehouses and BI | High Cost/Staff | 0 | 0 | 0
| High Cost/Consult | 0 | 0 | 0
General technical and project management | High Cost/Staff | 376510 | 345510 | 722020
| High Cost/Consult | 0 | 0 | 0
TOTAL HIGH COSTS (STAFF/CONSULT) |  | 2552885 | 1335635 | 3888520
Low Estimates for each option |  | 2012-07-01 | 2013-01-01 | Defered
Identity Management and IT Security | Low Cost/Staff | 33000 | 41375 | 33000
| Low Cost/Consult | 37500 | 24938 | 37500
Direct, Core Workday transactional impact | Low Cost/Staff | 245000 | 358733 | 460000
| Low Cost/Consult | 505500 | 342439 | 1208000
Data delivery, warehouses and BI (DEFFERED) | Low Cost/Staff | 0 | 0 | 0
| Low Cost/Consult | 0 | 0 | 0
General technical and project management | Low Cost/Staff | 177750 | 179006 | 364510
| Low Cost/Consult | 16875 | 14991 | 0
TOTAL LOW COSTS (STAFF/CONSULT) |  | 1015625 | 961481 | 0
|  | Identity Management and IT Security | Direct, Core Workday transactional impact | Data delivery, warehouses and BI | General technical and project management
Low Estimates July 2012 Go-Live | Staff | 0 | 605750 | 0 | 345510
| Consulting | 0 | 384375 | 0 | 0
High Estimates July 2012 Go-Live | Staff | 62000 | 223750 | 0 | 376510
| Consulting | 75000 | 1815625 | 0 | 0
Low Estimates Jan 2013 Go-Live | Staff | 0 | 326750 | 0 | 172755
| Consulting | 0 | 193125 | 0 | 0
High Estimates Jan 2013 Go-Live | Staff | 0 | 605750 | 0 | 345510
| Consulting | 0 | 384375 | 0 | 0
Low Estimates Deferred post-July 2012 | Staff | 33000 | 460000 | 0 | 364510
| Consulting | 37500 | 1208000 | 0 | 0
High Estimates Deferred post-July 2012 | Staff | 62000 | 829500 | 0 | 722020
| Consulting | 75000 | 2200000 | 0 | 0

## Details
Categories | ITEM | WHY IS IT ON THE LIST | COMPLEXITY (H,M,L) | RESOURCE LOW EST. IN HOURS | RESOURCE HIGH EST. IN HOURS | RESOURCE % FROM NOW-JULY 2012 |  |  | RESOURCE % FROM JULY 2012-JULY 2013 |  |  | RESOURCE % FROM JULY 2013-TBD |  |  |  | Phase 1 |  |  |  | Phase 2 |  |  |  | Phase 3 |  |  |  | Total dollars for both phases |  | ASSUMPTIONS | Risks or change notes | SubTotal Lower | SubTotal Upper
[6 empty] | Staff | Consulting | Phase 1 subtotal % | Staff | Consulting | Phase 2 subtotal % | Staff | Consulting | Phase 3 subtotal % | Total % | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult | Low Cost/Staff | Low Cost/Consult | High Cost/Staff | High Cost/Consult | Total Low | Total High
Identity Management and IT Security | [31 empty] | 580 | 1120
| Provisioning (netid Admin, active directory, directory changes, ref groups...) | Generates and loads all netids (employees, students etc) into PS. Queries people population. | H | 500 | 1000 | 50% | 50% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 25000 | 37500 | 50000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 62500 | 125000 | It is not known how much the requirements have changed. If they have changed it is a new spec. NetID Provisioning is tightly coupled with PeopleSoft. Job data will have to be collected from Workday. Goal is to keep netid tools from changing as much as possible by using PeopleSoft as a people data hub. Some changes and much testing is required. The PS datahub work is covered in the PeopleSoft changes. | The tools for the NetID creation will fail and processes to provision netids will not work.
| authentication and authorization for users | Ensure Shib is working. Apparently it requires some customization, according to Georgetown. | L | 40 | 60 | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 4000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000 | 6000
| authentication and authorization for applications | Research, prototype, and document ideal method for securing service calls. | L | 40 | 60 | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 4000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000 | 6000
SUBTOTALS |  |  |  | 580 | 1120 | [10 empty] | 33000 | 37500 | 62000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70500 | 137000 |  |  | 5150 | 8250
Direct, Core Workday transactional impact | [31 empty] | 9320 | 16295
| Data extract and conversion support | Payroll does not have resources or skillset to support this need and Workday needs the data for prototyping. | M | 150 | 250 | 25% | 25% | 50% | 25% | 25% | 50% | 0% | 0% | 0% | 100% | 3750 | 5625 | 6250 | 9375 | 3750 | 5625 | 6250 | 9375 | 0 | 0 | 0 | 0 | 18750 | 31250 | scope is limited to a subset of Payroll transactional tables exported to flat files for loading into WD iload spreadsheets by HRIS/Workday. | Changed to 0. We don't know enough about it.
| PeopleSoft with Payroll | extract and transform job and benefit data from Workday to fit PeopleSoft exactly. | H | 2000 | 3000 | 0% | 90% | 90% | 10% | 0% | 10% | 0% | 0% | 0% | 100% | 0 | 270000 | 0 | 405000 | 20000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 290000 | 435000 | Assumptions: 1) PS data of record for ALL people bio/demo: "whoIam" 2) PS data of record for "whoIamHere" at Cornell 3) WD is data of record for all HR, Payroll and Benefits business transactions. In support of these assumptions: A) Synch of campus community data to PS for employees B) Synch from WD of employee information about "WhoIAmHere" at Cornell to PS C) PS must send WD updates about "WhoIAmHere" at Cornell (ie: email address) D) Create new tables for "WhoIAmHere". Remediate existing customizataions to pull from these new tables. E) PS is still a consumer (point-to-point) for some transactional data (ie: student gross earning for FA awards)
| PeopleSoft -other than Payroll | Integration data mapping, design and development with Workday (emplids, campus community data, search/match), remediation to current customizations and shared data tables supporting Student and Contributor Relations and outward facing interfaces including Library , KIM and EMN. | H | 3000 | 5000 | 40% | 50% | 90% | 10% | 0% | 10% | 0% | 0% | 0% | 100% | 120000 | 225000 | 200000 | 375000 | 30000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 375000 | 625000 | Assumptions: 1) PS data of record for ALL people bio/demo: "whoIam" 2) PS data of record for "whoIamHere" at Cornell 3) WD is data of record for all HR, Payroll and Benefits business transactions. In support of these assumptions: A) Synch of campus community data to PS for employees B) Synch from WD of employee information about "WhoIAmHere" at Cornell to PS C) PS must send WD updates about "WhoIAmHere" at Cornell (ie: email address) D) Create new tables for "WhoIAmHere". Remediate existing customizataions to pull from these new tables. E) PS is still a consumer (point-to-point) for some transactional data (ie: student gross earning for FA awards)
| Financial Aid's use of Student Employment | TBD | L | 40 | 60 | 50% | 50% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 2000 | 3000 | 3000 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 7500
| PS transactional queries | Users in PS have the ability to write transactional queries and use that data for business processing, analytics and reporting. Any queries that use employee related data will no longer work. | L | 0 | 40 | 50% | 50% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 0 | 2000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Business areas will need to seek HR's Workday contact for employee related data and continue to use PeopleSoft for Student. | Direct access from auxiliary systems without an integration broker will propagate point-to-point solutions and increase support issues.
| Sending student employee data to Workday | support Student Employment functionality within Workday | M | 150 | 250 | 50% | 50% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 7500 | 11250 | 12500 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | 31250 | Unknown specs and requirements. No PS to WD transformation of values. WD assumes all transformation of data into their system.
| Kronos | Produces time for employees to collect wages on. Integrations to/from Workday. | H | 2500 | 5000 | 0% | 0% | 0% | 50% | 50% | 100% | 0% | 0% | 0% | 100% |  | 500000 |  | 1000000 | 125000 | 187500 | 250000 | 375000 | 0 | 0 | 0 | 0 | 812500 | 1625000 | See Payroll's write up. These numbers are from them and are not based on our rates or formulas. | Changed to Medium
| COLTS | To avoid having to remediate Colts. Decommission and expand Kronos. | L | 40 | 60 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 4000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 4000 | 6000 | Conversion of existing data, decommission application, interfaces, PS customizations. | Changed to small
| KFS | Liability, position, salary earnings detail, gross pay encumbrance data is needed in KFS from Payroll system. Workday will need chart of account data. | H | 1000 | 2000 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 100000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 100000 | 200000 | See Workday Context Diagram. Hours are based on KFS remediation effort which included 4 fte for 1 1/2 years and it is believed that this effort is simpler. | All financial accounting will be missing University labor charges.
| UnitedWay | UnitedWay ships gets basic HR Bio data and ships pledge data for payroll withholdings. | M | 150 | 150 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | The interface is straight forward for pushing pledge commitments.
| ID Card | All University Id cards are produced out of PeopleSoft. Data is fed real-time and batch to Campus Life, Transportation and Facilities based on data in the University Id Card system. | M | 150 | 225 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 15000 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 15000 | 22500 | See Workday Context Diagram | If we do not remediate this system, University Id Card system will no longer have up-to-date employee information. Student information will not be impacted.
| ELM | Campus Community data for all students and employees go to ELM. Employee job data (workforce and position) is sent to ELM from PS. | M | 100 | 200 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 10000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 10000 | 20000 | Keep feeds the same or upgrade to a single service as a separate improvement effort.
| Harris Connect | Employee and Alumni data come from the CR and HR warehouses and HC updates PS with alumni Bio/Demographic data | L | 40 | 60 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 4000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 4000 | 6000 | This will have to be redone to the new warehouses or go directly from PeopleSoft's new people data hub.
SUBTOTALS |  |  |  | 9320 | 16295 | [10 empty] | 133250 | 1014875 | 223750 | 1815625 | 326750 | 193125 | 605750 | 384375 | 0 | 0 | 0 | 0 | 1668000 | 3029500 |  |  | 26183.7822 | 111782.6189
Data delivery, warehouses and BI | [31 empty] | 0 | 20000
| Needs analysis for data delivery | This would include a discovery effort of business requirements, data analysis and technical solutions for a data delivery solution. | H | 0 | 2000 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | Data warehouse solution can be deferred. KDW effort to date is 14000 hours, as of 4/26/2011. 12000 hours is still expected for a total of 26000. This estimate has been reduced to 20000 as the operational reporting needs are believed to be as high as it is for KFS. | Changed the low estimate to 0 - we just don't do it.
| data warehouse and reporting solution | This would include planning, modeling, extracts and transformations, reports and sub-project management. It doesn't include functional time | H | 0 | 20000 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000 | Data warehouse solution can be deferred. KDW effort to date is 14000 hours, as of 4/26/2011. 12000 hours is still expected for a total of 26000. This estimate has been reduced to 20000 as the operational reporting needs are believed to be as high as it is for KFS. | Changed the low estimate to 0 - we just don't do it.
SUBTOTALS |  |  |  | 0 | 20000 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 2000000 |  |  | 0 | 0
General technical and project management |  |  | B | [28 empty] | 5425 | 10780
| Technical Project management |  | H | 5235 | 10470 | 33% | 0% | 33% | 33% | 0% | 33% | 33% | 0% | 33% | 66% | 172755 | 0 | 345510 | 0 | 172755 | 0 | 345510 | 0 | 172755 | 0 | 345510 | 0 | 518265 | 1036530
| help desk and NOC setup | NOC and Help Desk are common contact areas for Cornell Community | L | 40 | 60 | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 4000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 6000 | Workday Deployment project will create necessary support documents and educate others.
| Architectural design to support Workday interaction with any systems with Cornell. | Strategic planning backed by prototyping, practices, tools and documentation to enable stability and long-term support | M | 150 | 250 | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 15000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 25000 | Use existing tools and infrastructure until such time a new direction is approved (Oracle SOA).
SUBTOTALS |  |  | B | 5425 | 10780 | [10 empty] | 191755 | 0 | 376510 | 0 | 172755 | 0 | 345510 | 0 | 172755 | 0 | 345510 | 0 | 537265 | 1067530 |  |  | 15325 | 48195
| TOTAL IN HOURS | CU and Consultant Rates |  | 15325 | 48195 | [26 empty] | 61983.7822 | 216422.6189
| TOTALS for Each Phase; Low/High, Staff/Consultant Rates | 100 | [13 empty] | 360000 | 1050000 | 660000 | 1890000 | 500000 | 190000 | 950000 | 380000 | 170000 | 0 | 2350000 | 0 | 2275765 | 6234030
|  | 150 | [13 empty] | 1410000 |  | 2550000 |  | 690000 |  | 1330000 |  | 170000 |  | 2350000 |  | 2270000 | 6230000 | <-Rounded
ROUNDED TOTALS LOW/HIGH per Go-Live Option
| TOTAL IN FTE |  |  | 8.7822 | 27.6189

## Kronos
Notes from Payroll | Low | High
a. Kronos upgrade assistance, 200 to 400 hours | 200 | 400
b. Data conversion within Kronos, 100 to 200 hours | 100 | 200
c. Kronos configurations, 700 to 1,400 hours | 700 | 1400
d. Kronos – Workday integrations, 800 to 1,600 hours | 800 | 1600
e. Reporting for error detection and control 400 to 800 hours | 400 | 800
f. Accrual rule configuration due to policy changes, 300 to 600 hours | 300 | 600
TOTALS | 2500 | 5000