## SummaryofOptions
OPTIONS
|  |  | Most cost and risk, 7/2012 |  | Med cost, 1/2013 |  | Lowest cost, has to wait.
| Estimates in hours |  | At 100% Consultant Rates (for 7/2012) |  | At 5/6 Consultants and 1/6 CU rates (for 1/2013) |  | At Cornell Rates (Start after 6/2012)
Categories | Low | High | July 2012, Low | July, 2012, High | January 2013, Low | Jan 2013, High | Start after KFS - Low | Start after KFS - High
Identity Management and IT Security | 580 | 1120 | 87000 | 168000 | 82166.6667 | 158666.6667 | 58000 | 112000
Direct, Core Workday transactional impact | 7570 | 11970 | 1135500 | 1795500 | 1072416.6667 | 1695750 | 757000 | 1197000
Data delivery, warehouses and BI | 2600 | 30000 | 390000 | 4500000 | 368333.3333 | 4250000 | 260000 | 3000000
Niche or unit apps | 680 | 855 | 102000 | 128250 | 96333.3333 | 121125 | 68000 | 85500
General Technical and project management | 1890 | 3710 | 283500 | 556500 | 267750 | 525583.3333 | 189000 | 371000
Totals | 13320 | 47655 | 1998000 | 7148250 | 1887000 | 6751125 | 1332000 | 4765500
Notes:
CU Rates |  | 100 | an hour
Consultant Rates |  | 150 | an hour
5/6 and 1/6 formula = | Through 6/2012 is 100% consultants and July 2012 to Jan 2013 is 50% consultants and 50% CU staff
Applicability of the formula: | The 5/6-1/6th formula was applied across the board although it may only need to be applied for certain activities and not others.
More analysis is needed to determine, for example, if it really applies to Identity Management's work.
Descriptions of changes and source of estimates:
Refer to the Details tab for individual efforts listed.
Refer to the Notes tab for a list of what changed since the original estimates were made.
Refer to the Charts tab for a set of charts.

## NOTES
Changes made:
Time collection: | The Kronos license and VM fees and upgrade project are entirely excluded as a separate project.
The costs still exist, and this is a prerequisite, but the costs will be counted separately in another project.
Data delivery: | All efforts concerning the HR-Payroll data warehouse and other warehouses and systems downstream of them is now deemed optional although the business impact to units and their decision making based on that data is unknown.
More analysis is recommended to determine use of the data and to prioritize requirements.
The high estimate is purely based on the effort (hours) spent to date and projected for the completion of the KDW.
HR has clearly stated they want a data warehouse, and have also said they don't have requirements.
Integration of People data: | Rather than having EMN, Library and the IdManagement tools connect with Workday we would keep PeopleSoft as intact as possible to minimize changes to them.
PeopleSoft stays as the 'People Data Hub'.
Architecturally and for long term support it is better, but the financial implications of this change are rather small.
Creating services for applications to get that data rather than using the high number of direct connects should be done, but is out side the scope of Workday.
Reserves for impacts to 'other' systems: | We believe there are other systems that will be impacted than those listed.
They will either be allowed to fail or require separate funding to remediate.
Consulting for Payroll: | Eliminated. If Payroll wants additional consulting for help with tools such as Windstar that CIT does not currently support it will require separate funding.
Technical Project Management: | It was moved up into the 'General technical and Project Management' category.
Changes contemplated but not made to the estimates and options:
Replace Id. Mgmt software: | This replaces campus wide single authentication infrastructure.
Analysis of the effort and the impact will require a project. A quick assessment is that this is a very large risky project of unknown size that requires more work to understand the size.

## Charts
Low Estimates for each option |  | At 100% Consultant Rates (for 7/2012) | At 5/6 Consultants and 1/6 CU rates (for 1/2013) | At Cornell Rates (Start after 6/2012)
Identity Management and IT Security | Low | 87000 | 82166.6667 | 58000
Identity Management and IT Security | High | 168000 | 158666.6667 | 112000
Direct, Core Workday transactional impact | Low | 1135500 | 1072416.6667 | 757000
Direct, Core Workday transactional impact | High | 1795500 | 1695750 | 1197000
Data delivery, warehouses and BI | Low | 390000 | 368333.3333 | 260000
Data delivery, warehouses and BI | High | 4500000 | 4250000 | 3000000
Niche or unit apps | Low | 102000 | 96333.3333 | 68000
Niche or unit apps | High | 128250 | 121125 | 85500
General Technical and project management | Low | 283500 | 267750 | 189000
General Technical and project management | High | 556500 | 525583.3333 | 371000
Totals | Low | 1998000 | 1887000 | 1332000
Totals | High | 7148250 | 6751125 | 4765500

## Details
Categories | ITEM | WHY IS IT ON THE LIST | Integration Type(s) | COMPLEXITY (H,M,L) | RESOURCE LOW EST. IN HOURS | RESOURCE HIGH EST. IN HOURS | ASSUMPTIONS | Risks or change notes | SubTotal Lower | SubTotal Upper
Identity Management and IT Security | [8 empty] | 580 | 1120
| Provisioning (netid Admin, active directory, directory changes, ref groups...) | Generates and loads all netids (employees, students etc) into PS. Queries people population. | Direct Connect | H | 500 | 1000 | It is not known how much the requirements have changed. If they have changed it is a new spec. NetID Provisioning is tightly coupled with PeopleSoft. Job data will have to be collected from Workday. Goal is to keep netid tools from changing as much as possible by using PeopleSoft as a people data hub. Some changes and much testing is required. The PS datahub work is covered in the PeopleSoft changes. | The tools for the NetID creation will fail and processes to provision netids will not work.
| authentication and authorization for users | Ensure Shib is working. Apparently it requires some customization, according to Georgetown. |  | L | 40 | 60
| authentication and authorization for applications | Research, prototype, and document ideal method for securing service calls. |  | L | 40 | 60
Direct, Core Workday transactional impact | [8 empty] | 7570 | 11970
| Data extract and conversion support | Payroll does not have resources or skillset to support this need and Workday needs the data for prototyping. | batch | M | 150 | 250 | scope is limited to a subset of Payroll transactional tables exported to flat files for loading into WD iload spreadsheets by HRIS/Workday. | Changed to 0. We don't know enough about it.
| PeopleSoft | Integrations with Workday (emplids, campus community, data, search/match), decommissioning of Payroll, Human Resources and Benefits jobs, remediation to current customizations supporting Student and Contributor Relations and outward facing interfaces. Design and implement a solution to address "stale" data. | Batch/Web Methods | H | 6000 | 9000 | Assumptions: 1) PS data of record for ALL people bio/demo: "whoIam" 2) PS data of record for "whoIamHere" at Cornell 3) WD is data of record for all HR, Payroll and Benefits business transactions. In support of these assumptions: A) Synch of campus community data to PS for employees B) Synch from WD of employee information about "WhoIAmHere" at Cornell to PS C) PS must send WD updates about "WhoIAmHere" at Cornell (ie: email address) D) Create new tables for "WhoIAmHere". Remediate existing customizataions to pull from these new tables. E) PS is still a consumer (point-to-point) for some transactional data (ie: student gross earning for FA awards)
| Financial Aid's use of Student Employment | TBD |  | L/H | 40 | 60
| PS Production control decomm | Payroll, Human Resources and Benefits use production control to run their workflows out of Peoplesoft. |  | L | 40 | 60 | Workday will not need production control to run processes out of Peoplesoft.
| PS transactional queries | Users in PS have the ability to write transactional queries and use that data for business processing, analytics and reporting. Any queries that use employee related data will no longer work. |  | L | 0 | 40 | Business areas will need to seek HR's Workday contact for employee related data and continue to use PeopleSoft for Student. | Direct access from auxiliary systems without an integration broker will propagate point-to-point solutions and increase support issues.
| Sending student employee data to Workday | support Student Employment functionality within Workday |  | M | 150 | 250 | Unknown specs and requirements. No PS to WD transformation of values. WD assumes all transformation of data into their system.
| Kronos | Produces time for employees to collect wages on. | Batch | M | 150 | 250 | Multiple jobs, CU customizations and the decommissioning of COLTS and expansion of Kronos all make this a significant project requiring analysis, specs, and new integration development and deployment. | Changed to Medium
| COLTS | To avoid having to remediate Colts. Decommission and expand Kronos. |  | S | 40 | 60 | Conversion of existing data, decommission application, interfaces, PS customizations. | Changed to small
| KFS | Liability, position, salary earnings detail, gross pay encumbrance data is needed in KFS from Payroll system. Workday will need chart of account data. | Batch/Web Methods | H | 1000 | 2000 | See Workday Context Diagram. Hours are based on KFS remediation effort which included 4 fte for 1 1/2 years and it is believed that this effort is simpler. | All financial accounting will be missing University labor charges.
| Cynergy |  | Direct Connect
Data delivery, warehouses and BI | [8 empty] | 2600 | 30000
| data warehouse and reporting total | This would include planning, modeling, extracts and transformations, reports and sub-project management. It doesn't include functional time |  | H | 2600 | 30000 | 10 to 15 FTE for 1 year for an effort similar to the KDW. KDW effort to date is 14000 hours, as of 4/26/2011. 12000 hours is still expected for a total of 26000. It's been rounded to the nearest 10K for the low and high estimates | Changed the low estimate to 0 - we just don't do it.
Niche or unit apps | [8 empty] | 680 | 855
| Library (Voyager) | Student and Employee data go to the Library | Batch | n/a | 20 | 40 | Keep feeds the same or upgrade to a single service as a separate improvement effort.
| ELM | Campus Community data for all students and employees go to ELM. Employee job data (workforce and position) is sent to ELM from PS. | Batch | n/a | 40 | 100 | Keep feeds the same or upgrade to a single service as a separate improvement effort.
| Emergency Contact and EMN | Translate table, Custom phone table and emergency contact table. Extraction and storing of data for EMN | Direct Connect/Replication(?) | n/a | 20 | 40 | Keep feeds the same or upgrade to a single service as a separate improvement effort.
| UnitedWay | UnitedWay ships gets basic HR Bio data and ships pledge data for payroll withholdings. | Batch | M | 150 | 150 | The interface is straight forward for pushing pledge commitments.
| KIM | KIM needs key identity data | Batch | M | 150 | 150 |  | dded KIM since we left oit out before
| Harris Connect | Employee and Alumni data come from the CR and HR warehouses and HC updates PS with alumni Bio/Demographic data | Batch | M | 150 | 150 | This will have to be redone to the new warehouses or go directly from PeopleSoft's new people data hub.
| ID Card | All University Id cards are produced out of PeopleSoft. Data is fed real-time and batch to Campus Life, Transportation and Facilities based on data in the University Id Card system. | Batch/Direct Connect/Web Methods | M | 150 | 225 | See Workday Context Diagram | If we do not remediate this system, University Id Card system will no longer have up-to-date employee information. Student information will not be impacted.
General Technical and project management | [8 empty] | 1890 | 3710
| Technical Project management |  |  | H | 1700 | 3400
| help desk and NOC setup | NOC and Help Desk are common contact areas for Cornell Community |  | L | 40 | 60 | Workday Deployment project will create necessary support documents and educate others.
| Architectural design to support Workday interaction with any systems with Cornell. | Strategic planning backed by prototyping, practices, tools and documentation to enable stability and long-term support |  | M | 150 | 250 | Use existing tools and infrastructure until such time a new direction is approved (Oracle SOA).
| TOTAL IN HOURS |  |  |  | 13320 | 47655 |  |  | 13320 | 47655
| At CU Rates 100% | 100 |  |  | 1330000 | 4770000
| At contractor rates 100% | 150 |  |  | 2000000 | 7150000
| TOTAL IN FTE |  |  |  | 7.6332 | 27.3095
| TOTAL $s at CU Rates ROUNDED |  |  |  | 1300000 | 4800000
| TOTAL $s at 100% contractor rates Rates ROUNDED |  |  |  | 2000000 | 7200000

## OLD Notes on Options
DON"T USE THIS TAB AT THIS TIME. This is incomplete and now represented in the Summary of Options tab.
Category | Factor : Scope | Factor: 7/12 or 1/13 | Factor: Consultant or CU reallocated | Low | high | Comments
Data delivery | original estimates for warehouse based on KDW effort |  |  | 2000000 | 3000000
| FULL WAREHOUSE remediation | 2012-07-01 | Use rate for 100% consultants | 3000000 | 4500000
| FULL WAREHOUSE remediation | 2013-01-01 | 5/6, 1/6 formula (see note below) | 2833333.3333 | 3000000
| NO WAREHOUSE: 100% data delivery is out of Workday and all reports are done by units. No warehouses get remediated in the time allocated. If they remediated it is after 2013 and Cornell lives without them for a period of time. | NA |  | 0 | 0 | The business risk to units using the data has not been investigated.
Point to Point or maximize PeopleSoft | PeopleSoft as a People Data hub |  |  | 7570 | 11970 | Make PS a people data hib and e;iminate a number of directo to Workday queries/extracts.
| PeopleSoft as a People Data hub | 2012-07-01 | Use rate for 100% consultants | 11355 | 17955
| PeopleSoft as a People Data hub | 2013-01-01 | 5/6, 1/6 formula (see note below) | 11355 | 11457.5
| Workday to individual systems |  |  |  |  | ELM, Library…go to Workday AND PeopleSoft
| Workday to individual systems | 2012-07-01 | Use rate for 100% consultants |  |  | The same as above.
| Workday to individual systems | 2013-01-01 | 5/6, 1/6 formula (see note below) |  |  | The same as above.
Identity Management
| Reimplement customizations in central admin tools | 2012-07-01 | Use rate for 100% consultants |  |  | Id Mgmt needs a chance to weigh in on the consultant and time factors. That hasn't been done yet. For now we're just applying the same formula.
| Reimplement customizations in central admin tools | 2013-01-01 | 5/6, 1/6 formula (see note below) |  |  | The same as above.
| Replace all authentication and authorization infrastructure | 2012-07-01 | Use rate for 100% consultants |  | UNKNOWN | This probably requires remediation of every system at Cornell to replace CUWebAuth. Therefor this is not calculable without much research. And, there is considerable risk. Identity Management may have estimates for this.
| Replace all authentication and authorization infrastructure | 2013-01-01 | 5/6, 1/6 formula (see note below) |  | UNKNOWN | The same as above.
Time Collection | [5 empty] | Move this out of the equation since it is a separate Capital project that just has to move up.
| Kronos expansion | 2012-07-01 | Consultant /CU factor is immaterial. | Not Applicable | Not Applicable
|  | 2013-01-01 |  | Not Applicable | Not Applicable
New July 2012 estimates
New Jan 2013 Estimates
New do-it-when-it-can-be-done-with-100% CU resources estimates