## Sheet1
Categories | ITEM | WHY IS IT ON THE LIST | Integration Type(s) | COMPLEXITY (H,M,L) | RESOURCE LOW EST. IN HOURS | RESOURCE HIGH EST. IN HOURS | ASSUMPTIONS | Risks | SubTotal Lower | SubTotal Upper
Identity Management and IT Security | [8 empty] | 2120 | 3180
| Provisioning (netid Admin, active directory, directory changes, ref groups...) | Generates and loads all netids (employees, students etc) into PS. Queries people population. | Direct Connect | H | 2000 | 3000 | It is not known how much the requirements have changed. If they have changed it is a new spec. NetID Provisioning is tightly coupled with PeopleSoft. Job data will have to be collected from Workday. Scale Factors: realtime-ness, use PS or direct to Workday. There needs to be something to get the Employee and push the NetID to Workday. A number of specific rules exist in Directory feeds to convert data from PS to Directory representation. More analysis is required to understand the needs. The job cost analysis is needed to go into it. There is an opportunity to simplify the UDF feed from PS. | The tools for the NetID creation will fail and processes to provision netids will not work.
| WhoIAm | Direct Connect from the WhoIAm application to PS for email administration of all Cornell assigned email addresses. | Direct Connect | L | 40 | 60
| authentication and authorization for users | Ensure Shib is working. Apparently it requires some customization, according to Georgetown. |  | L | 40 | 60
| authentication and authorization for applications | Research, prototype, and document ideal method for securing service calls. |  | L | 40 | 60
Direct, Core Workday transactional impact | [8 empty] | 10670 | 18535
| W2s | There is a legal requirement to have the ability to re-produce W2's for x number of years. Workday will not be converting enough historical data to support this legal requirement. |  | L | 40 | 60 | Re-producing W2's for x number of years will occur out of Peoplesoft until the record retention needs are met within Workday.
| Puerto Rico paychecks | Workday does not support Peurto Rico payroll |  | M | 150 | 225 | A routine integration is needed to 3rd party provider. A one-time load/conversion is need to prime 3rd party system either from Peoplesoft or Workday depending when 3rd party provider system is used.
| PeopleSoft | Integrations with Workday (emplids, campus community, data, search/match), decommissioning of Payroll, Human Resources, Benefits and SES, remediation to current customizations supporting Student and Contributor Relations and outward facing interfaces. Design and implement a solution to address "stale" data. | Batch/Web Methods | H | 6000 | 9000
| Financial Aid's use of Student Employment | ??????????? |  | L/H | 40 | 2000
| Campus community synchronization | Single data repository of people data (including students, employees, alumni) |  | M/H | 300 | 500 | One way integration from WD to PS of employee bio/demographic data. Determination of what campus community data to synch and the schedule (real-time, batch)
| PS Production control decomm | Payroll, Human Resources and Benefits use production control to run their workflows out of Peoplesoft. |  | L | 40 | 60 | Workday will not need production control to run processes out of Peoplesoft.
| PS transactional queries | Users in PS have the ability to write transactional queries and use that data for business processing, analytics and reporting. Any queries that use employee related data will no longer work. |  | L | 0 | 40 | Business areas will need to seek HR's Workday contact for employee related data and continue to use PeopleSoft for Student. | Direct access from auxiliary systems without an integration broker will propagate point-to-point solutions and increase support issues.
| Sending student employee data to Workday | support Student Employment functionality within Workday |  | M | 150 | 225 | Unknown specs and requirements. No PS to WD transformation of values. WD assumes all transformation of data into their system.
| Kronos | Produces time for employees to collect wages on. | Batch | H | 2800 | 4200 | Multiple jobs, CU customizations and the decommissioning of COLTS and expansion of Kronos all make this a significant project requiring analysis, specs, and new integration development and deployment. | This does not include licences.
| COLTS | To avoid having to remediate Colts. Decommission and expand Kronos. |  | M | 150 | 225 | Conversion of existing data, decommission application, interfaces, PS customizations.
| KFS | Liability, position, salary earnings detail, gross pay encumbrance data is needed in KFS from Payroll system. Workday will need chart of account data. | Batch/Web Methods | H | 1000 | 2000 | See Workday Context Diagram. Hours are based on KFS remediation effort which included 4 fte for 1 1/2 years and it is believed that this effort is simpler. | All financial accounting will be missing University labor charges.
| Cynergy |  | Direct Connect
Data delivery, warehouses and BI | [8 empty] | 20000 | 30000
| data warehouse and reporting total | This would include planning, modeling, extracts and transformations, reports and sub-project management. It doesn't include functional time |  | H | 20000 | 30000 | 10 to 15 FTE for 1 year for an effort similar to the KDW. KDW effort to date is 14000 hours, as of 4/26/2011. 12000 hours is still expected for a total of 26000. It's been rounded to the nearest 10K for the low and high estimates
Niche or unit apps | [8 empty] | 610 | 900
| Library (Voyager) | Student and Employee data go to the Library | Batch | L | 40 | 60 | See Workday Context Diagram | If we do not remediate this interface Library will no longer get up-to-date employee information. Student information will not be impacted.
| Transportation | PeopleSoft currently interacts with Transportation via 3 data feeds (student, employee and employee deductions). Decommission all employee data feeds. Workday will interact directly with Transportation. Student is unaffected. | Batch | L | 40 | 60 | See Workday Context Diagram
| ELM | Campus Community data for all students and employees go to ELM. Employee job data (workforce and position) is sent to ELM from PS. | Batch | M | 150 | 225 | See Workday Context Diagram | Human Resources, EHS, Cash Mgmt (PCI), KFS and Gannett will not have all employee data needed to offer courses and access courses in ELM for training and compliance. compliance training.
| Emergency Contact and EMN | Translate table, Custom phone table and emergency contact table. Extraction and storing of data for EMN | Direct Connect/Replication(?) | L | 40 | 60 | See Workday Context Diagram | Emergency mass notification uses obsolete data and people don't get called in the event of an emergency.
| CU Police | CU Police utilize PS when responding to emergency situations as PS has the entire CU community | Transactional | L | 0 | 60 | CU Police will have access to Workday and PeopleSoft
| UnitedWay | UnitedWay ships gets basic HR Bio data and ships pledge data for payroll withholdings. | Batch | M | 150 | 150 | The interface is straight forward for pushing pledge commitments.
| Harris Connect | Employee and Alumni data come from the CR and HR warehouses and HC updates PS with alumni Bio/Demographic data | Batch | L | 40 | 60 | An Employee warehouse exists for the feed.
| ID Card | All University Id cards are produced out of PeopleSoft. Data is fed real-time and batch to Campus Life, Transportation and Facilities based on data in the University Id Card system. | Batch/Direct Connect/Web Methods | M | 150 | 225 | See Workday Context Diagram | If we do not remediate this system, University Id Card system will no longer have up-to-date employee information. Student information will not be impacted.
General Technical | [8 empty] | 190 | 285
| Implement an MDM solution | an option |  |  | 0 | 0 | We do not know if we are pursuing but it would be outside of scope of Workday if it is.
| Implement Oracle SOA | an option |  |  | 0 | 0 | We do not know if we are pursuing but it would be outside of scope of Workday if it is.
| help desk and NOC setup | NOC and Help Desk are common contact areas for Cornell Community |  | L | 40 | 60 | Workday Deployment project will create necessary support documents and educate others.
| Architectural design to support Workday interaction with any systems with Cornell. | Strategic planning backed by prototyping, practices, tools and documentation to enable stability and long-term support |  | M | 150 | 225 | Use existing tools and infrastructure until such time a new direction is approved (Oracle SOA).
Consult/Advise Payroll | [8 empty] | 300 | 375
| Workday to 3rd party oversight or development for Payroll | Payroll requested CIT developer support for building and maintaining ALL Payroll integrations and reports |  | M | 150 | 150 | Outstanding question on inventory list
| Data extract and conversion support | Payroll does not have resources or skillset to support this need and Workday needs the data for prototyping. | batch | M | 150 | 225 | scope is limited to a subset of Payroll transactional tables exported to flat files for loading into WD iload spreadsheets by HRIS/Workday.
| TOTAL IN HOURS |  |  |  | 33890 | 53275 |  |  | 33890 | 53275
| At $100 an hour | 100 |  |  | 3390000 | 5330000
| TOTAL IN FTE |  |  |  | 19.4212 | 30.5301
| TOTAL $s ROUNDED UP |  |  |  | 3400000 | 5400000
Not Included:
|  | VMS for new DWs and integration tools |  |  | unknown | unknown
|  | Licenses for Kronos for all campus hourly employees |  |  | unknown | unknown
Categories of efforts | Lower Estimate | Upper estimate
Identity Management and IT Security | 212000 | 318000 |  |  |  |  | Category | Lower Estimate | Upper Estimate
Direct, Core Workday transactional impact | 1067000 | 1853500 |  |  |  |  | Core CIT Technical labor subtotal | 3389000 | 5327500
Data delivery, warehouses and BI | 2000000 | 3000000 |  |  |  |  | Kronos licenses , VMs, and 1st year support: | 410000 | $410,00
Niche or unit apps | 61000 | 90000 |  |  |  |  | Contingency for $150/ hour contractors for ½ of the work | 500000 | 750000
General Technical | 19000 | 28500 |  |  |  |  | Changes to all down stream systems (a complete guess!) | 100000 | 500000
Consult/Advise Payroll | 30000 | 37500 |  |  |  |  | Technical Project overhead of CIT tech Labor (15%) | 508350 | 799125
Totals | 3389000 | 5327500 |  |  |  |  | TOTAL rounded to nearest ten thousand | 4910000 | 7380000