## Slide 1: Workday
Revised technical summary
May 17, 2011

## Slide 2: Topics
Assumptions
Changes
Context diagram
Estimates
  Low/High ratios
  Low/High by category by option

## Slide 3: Assumptions
Rates used:
  CU Rates $100 an hour
  Consultant Rates $150 an hour
Formula for January 2013:
  5/6 and 1/6 formula = Through 6/2012 is 100% consultants and July 2012 to Jan 2013 is 50% consultants and 50% CU staff Applicability of the formula:
  The 5/6-1/6 formula was applied across the board although it may only need to be applied for certain activities and not others. More analysis is needed to determine, for example, if it really applies to Identity Management's work.

## Slide 4: Changes made
Time collection: The Kronos license and VM fees and upgrade project are entirely excluded. The costs still exist, and this is a prerequisite, but the costs will be counted separately in another project.
Result: No longer included.

## Slide 5: Changes made
Data delivery:
  All efforts concerning the HR-Payroll data warehouse and other warehouses and systems downstream of them is now deemed optional and the low estimate is zero.
  The business impact to units and their decision making based on that data is unknown.
  HR has clearly stated a data warehouse is wanted and requirements are needed.
  More analysis is recommended to determine use of the data and to prioritize requirements.
  The high estimate is purely based on the effort (hours) spent to date and projected for the completion of the KDW.
Result: Changed to optional.

## Slide 6: Changes made
Integration of People data:
  Rather than having EMN, Library and the IdManagement tools connect with Workday we would keep PeopleSoft as intact as possible to minimize changes to them.
  PeopleSoft stays as the 'People Data Hub'.
  Architecturally and for long term support it is better, but the financial implications of this change are relatively small.
  Creating services for applications to get that data rather than using the high number of direct connects should be done, and is outside the scope of Workday.
Result: Changed

## Slide 7: Changes made
Reserves for impacts to 'other' systems:
  We believe there are other systems that will be impacted than those listed.
  They will either be allowed to fail or require separate funding to remediate.
Result: No longer included.

## Slide 8: Changes made
Consulting for Payroll:
  If Payroll wants additional consulting for help with tools such as Windstar that CIT does not currently support it will require separate funding.
Result: No longer included.

## Slide 9: Changes Made
Technical Project Management:
  It was moved up into the 'General technical and Project Management' category.
  It is an hour count now rather than a % of the project.
Result: Reduced and moved.

## Slide 10: Changes discussed and not made
Replace Id. Mgmt software:
  PS Data Hub concept reduces impact.
Result: Effort reduced.

## Slide 11: PeopleSoft as the person ‘data hub’

## Slide 12: Ratios of efforts
Chart: 
| Identity Management and IT Security | Direct, Core Workday transactional impact | Data delivery, warehouses and BI | Niche or unit apps | General Technical and project management
Low Estimates | 58000 | 757000 | 0 | 68000 | 189000

## Slide 13: Ratios of efforts
Chart: 
| Identity Management and IT Security | Direct, Core Workday transactional impact | Data delivery, warehouses and BI | Niche or unit apps | General Technical and project management
High Estimates | 112000 | 1197000 | 3000000 | 85500 | 371000

## Slide 14: Costs of three options – Low Estimates
Chart: 3 options for low estimates for each category. No data delivery work is included.
| At Cornell Rates (Start after 6/2012) | At 5/6 Consultants and 1/6 CU rates (for 1/2013) | At 100% Consultant Rates (for 7/2012)
Identity Management and IT Security Low | 58000 | 82166.6667 | 87000
Direct, Core Workday transactional impact Low | 757000 | 1072416.6667 | 1135500
Data delivery, warehouses and BI Low | 0 | 0 | 0
Niche or unit apps Low | 68000 | 96333.3333 | 121125
General Technical and project management Low | 283500
Totals Low | 1072000 | 1518666.6667 | 1627125

## Slide 15: Costs of three options – High Estimates
Chart: 3 options with high estimates for each category
| At Cornell Rates (Start after 6/2012) | At 5/6 Consultants and 1/6 CU rates (for 1/2013) | At 100% Consultant Rates (for 7/2012)
Identity Management and IT Security High | 112000 | 158666.6667 | 168000
Direct, Core Workday transactional impact High | 1197000 | 1695750 | 1795500
Data delivery, warehouses and BI High | 3000000 | 4250000 | 4500000
Niche or unit apps High | 85500 | 121125 | 128250
General Technical and project management High | 371000 | 525583.3333 | 556500
Totals High | 4765500 | 6751125 | 7148250