## Sheet1
Task Name | 10/03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28
Use lasers to map the properties of the lenses | bar: 2011-10-10 to 2011-10-17
Figure out how to handle the difference between lamp/sunlight | bar: 2011-10-17 to 2011-10-24
Design different methods to use the lenses and test them | bar: 2011-10-17 to 2011-11-21
Design a system that uses both the fresnel lenses and mirror(s) that can attach to the solar oven | bar: 2011-11-14 to 2011-11-28
Potentially experiment with other methods of solar cooking using the lenses | bar: 2011-11-07 to 2011-11-14
Design a method to reach fry temperature (contingent on results) | [9 empty] | (long term goal possibly?) | bar: 2011-10-24 to 2011-11-28
Reach out to potential sponsors
Meet with professors | bar: 2011-10-17 to 2011-11-07
Prepare final results and plan for future work | bar: 2011-11-28