ColdFusion v9 - Migration Project       Status Period: 8/8-8/19/2011

| Customer: CIT | Project Sponsor: Nancy VanOrman – changed from Dave Koehler |
| --- | --- |
| Project Manager: Nathan Reimer | Project Director: Donna Taber |
|  | Key Customers: ColdFusion 7 Customers |
| Start Date: June 5, 2010 | End Date: August 31, 2011 TBD |
| Objective The goal of this project is to migrate customers from MSCF v7 to ColdFusion v9 hosting environment. |  |

| Project Status: |  | No major issue(s) |  | Cautionary issue(s) |  | Critical issue(s) |
| --- | --- | --- | --- | --- | --- | --- |

| Yes | No | Status Summary (explain if "yes" is checked) |
| --- | --- | --- |
|  |  | Have the objectives in the Phase or Project Plan changed? |
|  |  | Have the assumptions in the Phase or Project Plan changed? |
|  |  | Have the deliverables in the Phase or Project Plan changed? |
|  |  | Are there significant changes to Scope requested? |
|  |  | Are there any major issues? |
|  |  | Is the project impacted by external factors? |
|  |  | Will the deliverables fail to meet specifications? |
|  |  | Are there business sponsorship issues? |
|  |  | Are there any problems affecting the project team's ability to perform the work? |
|  |  | Does the actual time expended to date vary significantly (>10%) from the project plan? |
|  |  | Are there resourcing problems? |
|  |  | Is a deliverable/milestone about to be missed? |
|  |  | Will the approved budget be overrun? |
|  |  | Will the benefits or projected savings not be realized? |
| Explanation of checked items: For every item answered “yes”, give a brief explanation. |  |  |
| - End date of Aug. 31 was arbitrary picked but due to various delays that is no longer attainable. No new date has been set yet. - Removing SVN was implemented May 11, 2011 - Some customers have expressed unwillingness to migrate until v9.0.1 is installed. We need a plan and timeline on upgrading existing VMs. - CUWebAuth issues listed below are preventing some applications from migrating - Fedora issues are preventing some applications from migrating |  |  |

### Project Milestones and Key Deliverables

| Milestone Report | Start Dates |  | Completion Dates |  |
| --- | --- | --- | --- | --- |
|  | Planned | Actual | Planned | Actual |
| Environment ready for customers | 05/01/10 | 05/01/10 | 05/15/10 | 06/05/10 |
| Site migrations started https://confluence.cornell.edu/x/16dpBw | 06/01/10 | 06/01/10 |  |  |
| www.cornell.edu went live in CF9 |  |  |  | 01/11/11 |
| Environment ready for customers with SVN issues resolved |  |  |  | 05/11/11 |
| Communication sent to customers regarding SVN fix and target retirement date for MSCF 7 of 8/31/11 | 05/26/11 | 05/26/11 | 05/26/11 | 05/26/11 |
| CIT Custom Apps migration effort listed here: https://confluence.cornell.edu/x/l5LBC |  |  | 08/31/11 |  |
| Upgrade CF9 to v9.0.1 (New VMs have v9.0.1, and upgraded VMs are ready to be used for COLTS). |  |  | 07/31/11 | 08/05/11 |
| Upgrade to latest production release of CUWebAuth. Still testing functionality to resolve issues |  |  | 08/14/11 | 08/21/11 |
| Move Dev/Test instances to Hardware Load Balancer |  |  | 08/07/11 | 08/07/11 |
| Move Prod instances to Hardware Load Balancer (note: Most were moved on 8/14/11. No date yet set to move the remaining VMs) |  |  | 08/14/11 |  |
| Install Grid (OEM) agents |  |  | 07/15/11 | 08/03/11 |
| Upgrade RAM to 4GB |  |  | 08/14/11 |  |
| Finish migrations | 08/31/11 |  | 08/31/11 |  |
| Turn off MSCF 7 | 10/15/11 |  | 10/15/11 |  |

### Issues Analysis – If necessary, attach CPMM_IssuesLog (Highlight critical issues here if appropriate.)

| Issue Description | Impact | Resolution |
| --- | --- | --- |
| May 2010 - Performance issues with SVN integration using KProxy | Most customers were not willing to migrate. | Resolved: SVN integration with KProxy - performance resolved – 10/11/10 |
| June 2010 - Additional issues with SVN integration - Unable to see hidden files - Transferring large sites was slow | Customers only can see SVN files Some sites transfers took up to 24 – 48 hours | Resolved: Removed SVN – resolved on 05/11/11 |
| June 2011 MSCF 7 still running most sites and having periodic performance issues and occasional service outages. | Unstable production environment | Resolved: ColdFusion 9 issues resolved May 2011, started aggressively working with customers to migrate |
| Default installation uses v9.0 CommonSpot v6.2 requires v9.0.1 | New instances are on hold until v9.0.1 is available Some customers can’t migrate Can’t upgrade to CommonSpot v6.2 which adds support for Firefox 5 and IE9, preventing authors from using the tool PaperThin has stopped support v6.0 since the release of v6.2 | Resolved: new VMs are built using v9.0.1. Customers must migrate code and CF9 settings from old v9 VM. CommonSpot VMs need to be upgraded/migrated to be in compliance with support |
| Grid (OEM) agents installed on all VMs planned mid-July but hasn’t started. | Full VM monitoring not available via Grid | Resolved: Agents installed on 8/3/11 |
| Fedora issue with CF9 | Fedora doesn’t work. Currently not bringing cookie Sites affected: fCOI (Conflict of Interest) CHE instance RMPS instance | Open: Need someone to assist with testing. Need ownership and expertise. |
| Webservices issue with CUWebAuth | Webservices do not work Sites affected: SPD (Staff Position/Performance Dialogue) | Open: should be resolved with new version of CUWebAuth. Testing underway by Custom Dev. team |
| Horizontal scaling issue with CUWebAuth | Load balancing does not work Sites affected: LaunchPad | Open: should be resolved with new version of CUWebAuth. Testing underway by Custom Dev. team |
| VMs seem to go to sleep when not used. This is related to the database connection and drivers | Performance delay for initial user | Open: Workaround is for customers to use the Macromedia Database Driver, but additional testing need to happen since symptoms still remain using that driver. |
| Upgrade VMs to 4gb | Better performance | Open: S&O needs to schedule this |

### Change Request Analysis – If necessary, attach CPMM_ChangeLog (Highlight new changes since last status report here.)  Include a brief analysis of trends in change requests, such as whether they are increasing or decreasing, whether they can continue at the same rate and stay within the 30% limit, etc.

| Change Requested | Impact | Resolution |
| --- | --- | --- |

### Risk Analysis – Refer to attached updated CPMM_RiskMgmtPlan

Include a brief analysis of how successful the risk management practices have been and the percentage of risks that have been escalated into issues, etc.

### Financial Commentary

### Project Manager Comments

Project Estimated % Complete is: 50% Total Customers: 31 - Total completed: 0 - Not continuing with service: 10 - Total customer left to migrate: 21 Migration customer list and tentative schedule are located at: https://confluence.cornell.edu/x/16dpBw

As of August 19, 2011 - New VMs built with v9.0.1 - Custom Dev. Team has begun migrating apps to v9.0.1 - New CUWebAuth code installed and is being Testing - Continue to work with customers to migrate and go live on CF9