CommonSpot v6 - Migration Project       Status Period: 06/2011

| Customer: CIT | Project Sponsor: Nancy VanOrman – changed from Dave Koehler |
| --- | --- |
| Project Manager: Nathan Reimer | Project Director: Donna Taber |
|  | Key Customers: CommonSpot v5 Customers |
| Start Date: October 10, 2010 | End Date: August 31, 2011 |
| Objective The goal of this project is to migrate customers from CommonSpot v5 to v6 hosting environment. |  |

| Project Status: |  | No major issue(s) |  | Cautionary issue(s) |  | Critical issue(s) |
| --- | --- | --- | --- | --- | --- | --- |

| Yes | No | Status Summary (explain if "yes" is checked) |
| --- | --- | --- |
|  |  | Have the objectives in the Phase or Project Plan changed? |
|  |  | Have the assumptions in the Phase or Project Plan changed? |
|  |  | Have the deliverables in the Phase or Project Plan changed? |
|  |  | Are there significant changes to Scope requested? |
|  |  | Are there any major issues? |
|  |  | Is the project impacted by external factors? |
|  |  | Will the deliverables fail to meet specifications? |
|  |  | Are there business sponsorship issues? |
|  |  | Are there any problems affecting the project team's ability to perform the work? |
|  |  | Does the actual time expended to date vary significantly (>10%) from the project plan? |
|  |  | Are there resourcing problems? |
|  |  | Is a deliverable/milestone about to be missed? |
|  |  | Will the approved budget be overrun? |
|  |  | Will the benefits or projected savings not be realized? |
| Explanation of checked items: For every item answered “yes”, give a brief explanation. |  |  |

### Project Milestones and Key Deliverables

| Milestone Report | Start Dates |  | Completion Dates |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Planned | Actual | Planned | Current | Actual |
| Environment ready for customers | 11/24/10 | 11/24/10 | 12/01/10 |  | 12/01/10 |
| Site migrations begin with Computing at Cornell as beta site | 12/09/10 | 12/09/10 | 12/14/10 |  | 12/17/10 |
| Computing at Cornell (www.cit.cornell.edu) went live on v6 | 12/09/10 | 12/17/10 | 02/13/10 |  | 03/03/11 |
| Engage with PaperThin to migrate customer sites https://confluence.cornell.edu/x/uwJyC | 10/15/10 | 10/15/10 |  |  |  |
| SVN issues resolved |  |  |  |  | 05/11/11 |
| Arts & Sciences Site Migrated |  |  | 06/09/11 |  | 06/10/11 |
| DFA Site Migrated |  |  | 05/19/11 |  | 06/18/11 |
| Gov Relations Site Migrated |  |  | 07/07/11 |  | 07/07/11 |
| Engineering Site Migrated |  |  | 07/14/11 |  | 07/15/11 |
| CALS Site Migrated |  |  | 07/21/11 |  |  |
| Gannett Site Migrated |  |  | 07/28/11 |  |  |
| AAP Site Migrated |  |  |  |  |  |
| DOS Site Migrated |  |  |  |  |  |
| Land Grant Site Migrated |  |  |  |  |  |
| Press Office Site Migrated |  |  |  |  |  |
| NEES Site Migrated |  |  |  |  |  |
| OADI (OMEA) Site Migrated |  |  |  |  |  |
| CIT Hosting Site Migrated to Computing at Cornell Site |  |  | 07/28/11 |  |  |
| Engineering Departments Migrated to Engineering site (BME, CBE, MSE, ORIE, TAM) |  |  |  |  |  |
| Finish migrations | 08/31/11 |  | 08/31/11 |  |  |
| Turn off CommonSpot v5 | 10/15/11 |  | 10/15/11 |  |  |

### Issues Analysis – If necessary, attach CPMM_IssuesLog (Highlight critical issues here if appropriate.)

| Issue Description | Impact | Resolution |
| --- | --- | --- |
| June 2010 - Additional issues with SVN integration - Unable to see hidden files - Transferring large sites was slow | Customers only can see SVN files Some sites transfers took up to 24 – 48 hours | Removed SVN – resolved on 05/11/11 |

### Change Request Analysis – If necessary, attach CPMM_ChangeLog (Highlight new changes since last status report here.)  Include a brief analysis of trends in change requests, such as whether they are increasing or decreasing, whether they can continue at the same rate and stay within the 30% limit, etc.

| Change Requested | Impact | Resolution |
| --- | --- | --- |

### Risk Analysis – Refer to attached updated CPMM_RiskMgmtPlan

Include a brief analysis of how successful the risk management practices have been and the percentage of risks that have been escalated into issues, etc.

### Financial Commentary

### Project Manager Comments

Comment from the project director: This is the first official status report. The CommonSpot v6 migration was not considered an official project, but in hindsight, should have had monthly status reports. This report is attempting to provide as much pertinent information to give an overview of the CommonSpot v6 migration project. There will be weekly status reports going forward. Project Estimated % Complete is: 60% Total Customers: 15 - Total completed: 5 - Not continuing with service: 3 - Total customer left to migrate: 7 Migration customer list and tentative schedule are located at: https://confluence.cornell.edu/x/uwJyC

As of July 15, 2011 - Continue to work with customers to migrate and go live on CommonSpot v6