CommonSpot v6 - Migration Project       Status Period: 8/22-8/26/2011

| Customer: CIT | Project Sponsor: Nancy VanOrman – changed from Dave Koehler |
| --- | --- |
| Project Manager: Nathan Reimer | Project Director: Donna Taber |
|  | Key Customers: CommonSpot v5 Customers |
| Start Date: October 10, 2010 | End Date: August 31, 2011 TBD |
| Objective The goal of this project is to migrate customers from CommonSpot v5 to v6 hosting environment. |  |

| Project Status: |  | No major issue(s) |  | Cautionary issue(s) |  | Critical issue(s) |
| --- | --- | --- | --- | --- | --- | --- |

| Yes | No | Status Summary (explain if "yes" is checked) |
| --- | --- | --- |
|  |  | Have the objectives in the Phase or Project Plan changed? |
|  |  | Have the assumptions in the Phase or Project Plan changed? |
|  |  | Have the deliverables in the Phase or Project Plan changed? |
|  |  | Are there significant changes to Scope requested? |
|  |  | Are there any major issues? |
|  |  | Is the project impacted by external factors? |
|  |  | Will the deliverables fail to meet specifications? |
|  |  | Are there business sponsorship issues? |
|  |  | Are there any problems affecting the project team's ability to perform the work? |
|  |  | Does the actual time expended to date vary significantly (>10%) from the project plan? |
|  |  | Are there resourcing problems? |
|  |  | Is a deliverable/milestone about to be missed? |
|  |  | Will the approved budget be overrun? |
|  |  | Will the benefits or projected savings not be realized? |
| Explanation of checked items: For every item answered “yes”, give a brief explanation. |  |  |
| - End date of Aug. 31 was arbitrary picked but due to various delays that is no longer attainable. No new date has been set yet. - PaperThin has stopped supporting v6.0 - Some customers have expressed unwillingness to migrate until v6.2 which requires v9.0.1. We need a plan and timeline on upgrading existing VMs. |  |  |

### Project Milestones and Key Deliverables

| Milestone Report | Start Dates |  | Completion Dates |  |
| --- | --- | --- | --- | --- |
|  | Planned | Actual | Planned | Actual |
| Environment ready for customers | 11/24/10 | 11/24/10 | 12/01/10 | 12/01/10 |
| Site migrations begin with Computing at Cornell as beta site | 12/09/10 | 12/09/10 | 12/14/10 | 12/17/10 |
| Computing at Cornell (www.cit.cornell.edu) went live on v6 | 12/09/10 | 12/17/10 | 02/13/10 | 03/03/11 |
| Engage with PaperThin to migrate customer sites https://confluence.cornell.edu/x/uwJyC | 10/15/10 | 10/15/10 |  |  |
| SVN issues resolved |  |  |  | 05/11/11 |
| Arts & Sciences Site Migrated |  |  | 06/09/11 | 06/10/11 |
| DFA Site Migrated |  |  | 05/19/11 | 06/18/11 |
| Gov Relations Site Migrated |  |  | 07/07/11 | 07/07/11 |
| Engineering Site Migrated |  |  | 07/14/11 | 07/15/11 |
| CALS Site Migrated |  |  | 07/21/11 |  |
| Gannett Site Migrated |  |  | 07/21/11 07/28/11 08/03/11 | 08/04/11 |
| AAP Site Migrated |  |  | 08/18/11 |  |
| DOS Site Migrated |  |  |  |  |
| Land Grant Site Migrated |  |  |  |  |
| Press Office Site Migrated |  |  |  |  |
| NEES Site Migrated |  |  |  |  |
| OADI (OMEA) Site Migrated |  |  |  |  |
| CIT Hosting Site Migrated to Computing at Cornell Site |  |  | 07/28/11 08/31/11 |  |
| Engineering Departments #1 Migrated to Engineering site (MAE, CEE, SE) |  |  | 08/16/11 | 08/16/11 |
| Engineering Departments #2 Migrated to Engineering site (BME, CBE, MSE) |  |  | 09/08/11 |  |
| Engineering Department #3 Migrated to Engineering site (ORIE) |  |  |  |  |
| Finish migrations | 08/31/11 |  | 08/31/11 |  |
| Turn off CommonSpot v5 | 10/15/11 |  | 10/15/11 |  |

### Issues Analysis – If necessary, attach CPMM_IssuesLog (Highlight critical issues here if appropriate.)

| Issue Description | Impact | Resolution |
| --- | --- | --- |
| June 2010 - Additional issues with SVN integration - Unable to see hidden files - Transferring large sites was slow | Customers only can see SVN files Some sites transfers took up to 24 – 48 hours | Resolved: Removed SVN – resolved on 05/11/11 |
| July 21 – CF Apache Proxy outage due to typo in IP resource for the CALS migration effort | All CF9 instances using Apache proxy were down for 1 hour and half | Resolved: Fixed misconfiguration in IP resource and restarted proxy |
| July 21-22 CALS migration was postponed for a day, because the customer had cached the DNS entry and couldn’t complete testing. This was resolved on 7/21 and then it was decided to cancel the migration for other technical reasons. Those reasons are still unknown. | Customer couldn’t migrate when planned and missed the window of opportunity. We will have to remigrate the site at a later date. | Open: Rescheduled until after classes start. Date still TBD |
| July 28 – v6.2 released. Install on new sites, upgrade existing sites, but need to upgrade ColdFusion to v9.0.1 first. | Adds support for latest browsers and fixes several issues V6.0 is now unsupported | Open: V9.0.1 available for new VMs. Need a plan and timeline for existing VMs |
| August 3 – Gannett delayed twice due to resource constraints. | Customer having to change go live dates | Resolved: Site went live on 8/3 |
| August 18 - AAP go live delayed | Waiting for V6.2 due to bug in v6.0 that have been fixed | Open: Need CF v9.0.1 in order to install v6.2 |

### Change Request Analysis – If necessary, attach CPMM_ChangeLog (Highlight new changes since last status report here.)  Include a brief analysis of trends in change requests, such as whether they are increasing or decreasing, whether they can continue at the same rate and stay within the 30% limit, etc.

| Change Requested | Impact | Resolution |
| --- | --- | --- |

### Risk Analysis – Refer to attached updated CPMM_RiskMgmtPlan

Include a brief analysis of how successful the risk management practices have been and the percentage of risks that have been escalated into issues, etc.

### Financial Commentary

### Project Manager Comments

Project Estimated % Complete is: 65% Total Customers: 15 - Total completed: 6 - Not continuing with service: 3 - Total customer left to migrate: 6 Migration customer list and tentative schedule are located at: https://confluence.cornell.edu/x/uwJyC

As of August 26, 2011 - PaperThin has stopped supporting v6.0 which means they won’t work on bugs unless customers upgrade to v6.2 - Continue to work with customers to migrate and go live on CommonSpot v6