User Studies Work Plan (rev. February 15, 2012)

| Date | Action | Responsibility |
| --- | --- | --- |
|  | At MaLT meeting assign tasks to team |  |
| Week of Feb. 12 | Establish team, budget, and level of effort (schedule daily meetings; finalize budget for tests) | Camille, Sara and Howard (Howard gets formal approval from Mary and process for getting cash is approved by Christina) |
| Feb. 16 onward | Put out and collect sign up and tear off sheets and online flyers for soliciting students (contact Liz for Visix posting); email info to Mann staff (1 hr) | Staff member |
| Feb. | Make copies of furniture/ Teamspot survey and signs | Camille |
| After troubleshooting | Revision of signs (5 hrs?) | Sara/Gilad? |
| current | Troubleshooting of Teamspot | Tom/Bill |
| Feb. 16 | Revise script and tasks for Teamspot usability study | Camille |
| After troubleshooting | Schedule time and participants for Teamspot usability study for staff again and then students | Camille |
| Feb. 17 | Meet with Gaby and Matt on getting hour long blocks for interviews into usability signup system | Camille |
| Feb. 20 | Plan interview and focus group training for research team (with Gaby Castro Gessner) | Camille and Gaby |
| Feb. 20-21 | Installation of furniture | Agati & staff member |
| Feb. 22 | Set up furniture and software surveys at Agati installations and in group study room (sign, consent form and paper surveys, submission box) (15 min) | Staff member |
| After Feb. 20 | Create individual and focus group interview scripts | Camille and staff members |
| Week of Feb. 20 | Teamspot usability test for students ( 2 one hr blocks) | Camille and staff members (notetakers) |
| Feb. 24 | Schedule testing times and block off room(s) for interviews (1 hr) | Staff member |
|  | Schedule interviewers for testing times (1 hr) | Staff member |
| Feb. 29 | Run interview and focus group training Pilot and refine instruments | Camille and Gaby; team (already scheduled) |
| Feb. 27 | Recruit participants for interview sign up times (1 hr) | Staff members |
|  | Collect survey box from dismantled demo installations (15 min) | Staff member |
| March 5-9 | Run interviews: Interviewers pick up consent forms, cash, flip chart, markers, notepads and script for tests (at least 5 one hr individual interviews-need interviewer and notetaker for each interview; at least 1 one hr focus group interview w/interviewer and notetaker) | Staff members |
| March 12-30 | Code and analyze Feb studies by April for preliminary report | Staff members |
| April | Collect data with refined surveys and other ethnographic methods; | Team |
| April | Preliminary report to Council and recs on furniture and Teamspot | Team |
| May-July | Mann roundtable on user studies so far in May; Transcription, coding and analysis of rest of data | Team |
| June | Report back from Council on preliminary recs and begin any possible implementation plans | Council; Team |
| July-August | Final report and recommendations | Team |
| August | Outline of paper and finish implementation of preliminary recommendations |  |

Ongoing:

Literature review (Phase 1: anything about Teamspot or collaborative software? Whiteboards? Furniture requirements)