## Slide 1: User Studies Workplan
Phase 1: now-mid March
Furniture and Teamspot surveys and usability studies; observations in Bissett (ongoing throughout semester)
Phase 2: early March-April
Interviews (indiv. & focus group) on Bissett use and collaborative work; prelim. report to Council
Phase 3: April-July
Bissett survey, Mann roundtable, other ethnographic studies (if time), and final report to Council & implementation

## Slide 2: Interviews-Study Process
Volunteers join study pool (recruitment via flyers, signs & email to CA)
MaLT member schedules study in usability registration system, locations in Mann reservation system, interviewers & notetakers on Outlook
Recruiter sends email to volunteer study pool with study explanation, schedule, consent form, & link to registration system for self-sign up
Volunteers sign up; recruiter sends reminder email day before study
Interviewer and notetaker follow study procedures (TBD & posted on wiki) on day of study
Audiorecording & consent forms given to CA; Notetaker types up & posts summary of notes
MaLT group meets to review audiorecording and find themes

## Slide 3: Dates to remember
Feb. 29, 2:30-4 PM, Mann 202A:
  interview training for those who have completed CITI training already
March 6-9, ~4:30-7 PM, rooms TBD:
  interview week for interviewers and notetakers
Mar. 12-30, TBD:
  analysis jam sessions