## Sheet1
# | CATEGORY | ACTION | ASSIGNED TO | WHEN | COMMENTS | STATUS
1 | AV Design | Andy and Greg to investigate XS20 to see it is a better alternative to C20 | Andy Page | 2013-07-12 | Specifications have been reviewed. When all licenses are purchased for SX20 cost is ~$2k higher for a C40 | Closed
2 | AV Design | Barbara to research early candidates for cloud-based annotation collaboration | Barbara Friedman | 2013-07-12 | July 29 - On hold. Next steps confirmation req'd LearnSpace trialed. Slightly confusing at first. $200/yr. Has to be hosted from a PC - Macs can join but can't host. Note has been sent to developer re: future Mac support | Hold
3 | AV Design | Andy Page to research possibility of utilizing a Cisco codec as an endpoint in WebEx sessions | Andy Page | 2013-07-12 | July 19 - Scott Yoest expressed interest during mtg. w/ Ted | Open
4 | AV Design | Greg to produce photoshop renderings of Big Red showing large displays mounted to long-wall pillars | Greg Bronson | TBD | This request has not yet been asked of Greg. Site visit to get proper photos of space required. Not a currently a priority. | Hold
5 | AV Design | Greg to research third party driver installed at Memorial that allows Windows to be run on Apple TV | Greg Bronson | 2013-07-12 |  | Closed
6 | Project Management | Michael to schedule weekly touchpoint w/ NAT | Michael Kennedy | 2013-07-16 |  | Closed
7 | Project Management | Michael to acquire implementation schedule from NAT | Michael Kennedy | 2013-07-19 |  | Closed
8 | Project Management | Michael to secure Chelsea rooms for AV installation | Michael Kennedy | 2013-07-19 | July 24 - Bookings secure. July 16 - Bookings for wire pulling are made. | Closed
9 | AV Design | Andy S. to provide design briefing to NAT | Andy Slusar | 2013-07-12 | Version 2 draft complete. | Closed
10 | Project Management | Andy S. to produce project plan | Andy Slusar | 2013-07-12 |  | Closed
11 |  | Michael to forward site photos to Greg and Andy | Michael Kennedy | 2013-07-08 | Sheet hanging in Big Red obstructed view - follow up photos required | Closed
13 | AV Design | Michael to confirm number of confidence monitors used in Big Red | Michael Kennedy | 2013-07-12 | Size and location to be determined onsite | Closed
14 | Project Management | Michael to consolidate system limitations and concerns in a single document for dissemination to academic leadership | Michael Kennedy | 2013-07-19 | July 24 - On hold. Need to confirm purpose of document, re-evaluate | Hold
15 | AV Design | Michael to provide cloud based whiteboarding solution information to NAT | Michael Kennedy | 2013-07-19 | July 24 - On hold. Likely not ready for Aug 23. | Hold
16 | AV Design | Michael to expedite decision regarding lectern-mounted annotation tablet | Michael Kennedy | 2013-07-12 | Email sent proposing 22" Sympodium. DECISION: 24" Podium used for lecture theatres | Closed
17 | AV Design | Nick to provide Andy P. with wireless Crestron unit for evaluation | Andy Page | 2013-07-12 | Low priority - not to be installed in summer build. Unit delivery scheduled | Closed
18 | Project Management | Clare and Andy P. to identify Ithaca endpoints and verify compatibility | Andy Page | 2013-07-21 | July 24 - Scott has confirmed room at ILR will be connected to - confirmation and site visit required July 23 - Confirmation required to schedule commissioning | Open
19 | AV Design | Clare to confirm required whiteboarding functionality with Ragit | Clare Van Den Blink | 2013-07-16 | July 16 - Scott has confirmed that interactive whiteboards are not required in classrooms or conference rooms. Annotation solution required. | Closed
20 | Operations | Andy Page and Laurie to determine wireless bandwidth for distributed learning classrooms | Andy Page | 2013-07-19 |  | Closed
21 | Project Management | Andy S. to update PIP to align with design brief | Andy Slusar | 2013-07-12 |  | Open
22 | Operations | Dan H. to determine 'boots on the ground' support allocation for first few weeks of distributed classes and longer term support model for 111 8th | Andy Slusar | 2013-07-26 | July 19 - Mtg between Dan, Scott and Clare required to confirm commissioning schedule | Open
23 | AV Design | Clare and Andy P. to align proposed solutions for Gates Hall with classroom and collaboration spaces (functional / requirements standards) | Clare Van Den Blink | 2013-07-19 | July 16 - Design constraints at Cornell Tech are not necessarily the same as Gates. | Open
24 | Operations | Barbara to identify Gates Hall video collaboration and learning spaces and map to learning space room types | Barbara Friedman | 2013-07-19 |  | Open
25 | Project Management | Michael to schedule onsite power / data infrastructure discussion for Touchdown | Michael Kennedy | 2013-07-19 | July 22 - Rep onsite July 23 Steven Seiden - Cel: 917.748.8274 seiden@derector.com July 16 - Email was sent to Steven @ 12:30 | Closed
26 | Project Management | Andy Slusar to request NAT provide an invoice for design services | Andy Slusar | 2013-07-12 |  | Closed
27 | Project Management | Andy to acquire AV/AT design guidelines from Jo-ann Chubb at UBC Faculty of Medicine | Andy Slusar | 2013-07-12 | July 22 - Meeting occurred, documentation received. | Closed
28 | Project Management | Michael to wkly meeting with Scott and Clare | Michael Kennedy | 2013-07-16 |  | Closed
29 | Operations | Michael to collect 'risk' data for hardware costing over 5k | Michael Kennedy | 2013-08-23 | We would want to collect serials, make, models for an insurance inventory for all risk coverage: http://www.risk.cornell.edu/insurance/all_risk.cfm | Open
30 | AV Design | Michael to outline confidence monitor positioning onsite next week. | Michael Kennedy | 2013-07-24 | July 23 - Feasible locations for confidence monitors is very limited. | Closed
31 | AV Design | Michael and NAT to identify physical dataport availability in rooms. | Michael Kennedy | 2013-07-24 | July 25 - Ports (Big Red: 3.1-005) Touchdown (3.1-00153) Ursa (3.1-149) Dubi (3.1-147) | Closed
32 | AV Design | Michael to find the Logitech camera previously installed in Big Red | Michael Kennedy | 2013-07-24 | July 22 - camera located. | Closed
33 | AV Design | Michael to determine if new requirement for whiteboards in Touchdown can be ordered by Tom and installed by NAT | Michael Kennedy | 2013-07-24 | July 23 - whiteboard sizes have been provided to Tom. He will be ordering - boards due onsite week of Aug. 12 July 16 - contact Julia Dumas with questions re: purchasing | Closed
34 | Project Management | Greg to draft commissioning process for new rooms at NYC tech and coordinate room scheduling for connection (Aug 6, 9) | Greg Bronson | 2013-07-26 | July 30 - Greg and Andy to identify and book Ithaca room for Aug 6th and 9th testing. July 22 - Commissioning checklist has been developed | Open
35 | Project Management | Michael to coordinate Crestron user interface review | Michael Kennedy | 2013-07-19 | July 30 - review occurred. Instructions provided to Nick. Barbara to review VC component. July 26 - mock-up will not be arriving. July 22 - mock-ups to arrive July 25, Review mtg scheduled for July 30. BF, AP, AS, MK, NB to attend. | Open
36 | Project Management | Nick to send list of all equipment requiring IP addresses | Nick Barnes (MK) | 2013-07-30 | July 30 - address bank has been provided to NAT; they are assigning and will provide to Andy P. and network team (Kyle) July 24 - Nick and Andy are coordinating | Open
37 | Project Management | Michael to ensure SIP information for phone tie-in is provided to NAT | Michael Kennedy | 2013-07-30 | Aug 1 - Nick is connecting with Ed Fisher to work on work-around. Request for dedicated POTS has been sent to Geri July 30 - SIP tie-in limitations. July 24 - Email sent to Andy, Greg and Scott | Open
38 | Project Management | Michael to ensure ports are configured for VC | Michael Kennedy | 2013-08-05 | July 31 - identified port numbers has been distributed via email July 25 - Andy P. is leading. Request has been sent to network from Andy's team. Kyle Pond from AV engineering July 24 - Email sent to Scott and Andy P. to confirm process | Open
39 | Project Management | Barbara to prepare user documentation for AV systems | Barbara Friedman |  | July 24 - Michael and Beth are available to support documentation production | Open
40 | project Management | Michael to coordinate HVAC balancing prior to commissioning | Michael Kennedy | 2013-08-05 | July 31 - requests made to Geri and Bob (architect) July 23 - request has been made to Geri. | Open
41 | Project Management | Phase II planning – What rooms are in scope? Dan H – may turn them into offices. | Andy Slusar | 2013-08-30 |  | Open
42 | Project Management | Michael to confirm required steps for Panopto set up. | Michael Kennedy | 2013-08-02 | Aug 1 - Email sent to Mike T. with use case outlined - requesting recommended approach - to be presented to Scott. July 29 - Email sent to Barbara and Mike. Barbara responded that she would work with Mike to set-up Panopto for NYTech. Follow-up required. Schedule/timing confirmation July 31. | Open
43 | Project Management | Investigate use of area rug behind lectern to denote camera range. | Michael Kennedy | 2013-08-12 |  | Open
44 | Quality Assurance | Test plan schedule, coordination and integration | Michael Kennedy | 2013-08-05 | July 30 - confirming user documentation deliverables July 31, schedule updates to follow | Open
45 | Quality Assurance | Produce list of use cases for functional testing | Barbara Friedman | 2013-08-02 | July 30 - Mtg (MK and BF) scheduled for July 31 to draft use case testing plan | Open
46 | Change Mgmt | Clare to Discuss AV and AT solutions with Ragit | Clare Van Den Blink | 2013-08-02 |  | Open
47 | AV Design | Order 2 Wacoms for Cornell Tech | Barbara Friedman | 2013-08-02 |  | Open
48 | Installation | Ensure Rooms are exclusively reserved for Installations | Michael Kennedy | 2013-08-05 | July 30 - Room bookings at NYC have been confirmed as per NAT's request. Rooms at Ithaca are outstanding - Greg and Andy to coord. | Open
49 | AV Design | Schedule meeting between Kyle and Nick Barnes | Andy Page | 2013-07-30 |  | Closed
50 | Project Management | Andy Page to schedule Ithaca rooms and required resources for intersite testing - August 6th and August 9th. | Andy Page | 2013-07-31 |  | Open
51 | Project Management | Andy P. and Greg confirm use of vaddio will enable camera and microphone inegraton for webex, skype, etc. | Greg Bronson | 2013-08-06 |  | Open
52 | Project Management | Andy S. to connect with Scott and coordinate inclusion of dedicated laptop to support Panopto recording in Classrooms | Andy Slusar | 2013-08-12 |  | Open
53 | AV Design | Barbara to look into go-wire and report user experience to team - to make decision re: purchasing it | Barbara Friedman | 2013-08-02 | Aug 1 - wire is avaialble for product review, Barbara will pick it up and review. | Open
54 | Operations | Confirmation of student sign-off requirements for student project recodings is required. | unassigned |  |  | Open
55 | Operations | Michael to articulate recommended approach for managing panopto recordings - for discussion with Scott | Michael Kennedy | 2013-08-06 | Aug 1 - Email sent to Mike T. with use case outlined - requesting articulation | Open
56 | Project Management | Michael to confirm August and September shedule for Big Red and identify sessions requiring high level of support | Michael Kennedy | 2013-08-06 |  | Open
57
58
59
60