## Sheet1
# | ACTION | ASSIGNED TO | WHEN | COMMENTS | STATUS
1 | Andy and Greg to investigate XS20 to see it is a better alternative to C20 | Andy Page | 2013-07-12 | Specifications have been reviewed. When all licenses are purchased for SX20 cost is ~$2k higher for a C40 | Closed
2 | Barbara to research early candidates for cloud-based annotation collaboration | Barbara Friedman | 2013-07-12 | July 29 - On hold. Next steps confirmation req'd LearnSpace trialed. Slightly confusing at first. $200/yr. Has to be hosted from a PC - Macs can join but can't host. Note has been sent to developer re: future Mac support | Hold
3 | Andy Page to research possibility of utilizing a Cisco codec as an endpoint in WebEx sessions | Andy Page | 2013-07-12 | July 19 - Scott Yoest expressed interest during mtg. w/ Ted | hold
4 | Greg to produce photoshop renderings of Big Red showing large displays mounted to long-wall pillars | Greg Bronson | TBD | This request has not yet been asked of Greg. Site visit to get proper photos of space required. Not a currently a priority. | Hold
5 | Greg to research third party driver installed at Memorial that allows Windows to be run on Apple TV | Greg Bronson | 2013-07-12 |  | Closed
6 | Michael to schedule weekly touchpoint w/ NAT | Michael Kennedy | 2013-07-16 |  | Closed
7 | Michael to acquire implementation schedule from NAT | Michael Kennedy | 2013-07-19 |  | Closed
8 | Michael to secure Chelsea rooms for AV installation | Michael Kennedy | 2013-07-19 | July 24 - Bookings secure. July 16 - Bookings for wire pulling are made. | Closed
9 | Andy S. to provide design briefing to NAT | Andy Slusar | 2013-07-12 | Version 2 draft complete. | Closed
10 | Andy S. to produce project plan | Andy Slusar | 2013-07-12 |  | Closed
11 | Michael to forward site photos to Greg and Andy | Michael Kennedy | 2013-07-08 | Sheet hanging in Big Red obstructed view - follow up photos required | Closed
13 | Michael to confirm number of confidence monitors used in Big Red | Michael Kennedy | 2013-07-12 | Size and location to be determined onsite | Closed
14 | Michael to consolidate system limitations and concerns in a single document for dissemination to academic leadership | Michael Kennedy | 2013-07-19 | July 24 - On hold. Need to confirm purpose of document, re-evaluate | Hold
15 | Michael to provide cloud based whiteboarding solution information to NAT | Michael Kennedy | 2013-07-19 | July 24 - On hold. Likely not ready for Aug 23. | Hold
16 | Michael to expedite decision regarding lectern-mounted annotation tablet | Michael Kennedy | 2013-07-12 | Email sent proposing 22" Sympodium. DECISION: 24" Podium used for lecture theatres | Closed
17 | Nick to provide Andy P. with wireless Crestron unit for evaluation | Andy Page | 2013-07-12 | Low priority - not to be installed in summer build. Unit delivery scheduled | Closed
18 | Andy P. to identify Ithaca endpoints and verify compatibility | Andy Page | 2013-08-06 | Aug 6 - ILR 109 identified as room to connect with. Andy Page reviewing room functionality/connection quaility - testing Aug 9th. July 24 - Scott has confirmed room at ILR will be connected to - confirmation and site visit required July 23 - Confirmation required to schedule commissioning | Closed
19 | Clare to confirm required whiteboarding functionality with Ragit | Clare Van Den Blink | 2013-07-16 | July 16 - Scott has confirmed that interactive whiteboards are not required in classrooms or conference rooms. Annotation solution required. | Closed
20 | Andy Page and Laurie to determine wireless bandwidth for distributed learning classrooms | Andy Page | 2013-07-19 |  | Closed
21 | Andy S. to update PIP to align with design brief | Andy Slusar | 2013-07-12 |  | Hold
22 | Dan H. to determine 'boots on the ground' support allocation for first few weeks of distributed classes and longer term support model for 111 8th - Asset Management | Andy Slusar | 2013-08-03 | Aug 26 - Temporary solution determined. To be communicated to users July 19 - Mtg between Dan, Scott and Clare required to confirm commissioning schedule | Open
23 | Clare and Andy P. to align proposed solutions for Gates Hall with classroom and collaboration spaces (functional / requirements standards) | Clare Van Den Blink | 2013-07-19 | July 16 - Design constraints at Cornell Tech are not necessarily the same as Gates. | Hold
24 | Barbara to identify Gates Hall video collaboration and learning spaces and map to learning space room types | Barbara Friedman | 2013-07-19 |  | Hold
25 | Michael to schedule onsite power / data infrastructure discussion for Touchdown | Michael Kennedy | 2013-07-19 | July 22 - Rep onsite July 23 Steven Seiden - Cel: 917.748.8274 seiden@derector.com July 16 - Email was sent to Steven @ 12:30 | Closed
26 | Andy Slusar to request NAT provide an invoice for design services | Andy Slusar | 2013-07-12 |  | Closed
27 | Andy to acquire AV/AT design guidelines from Jo-ann Chubb at UBC Faculty of Medicine | Andy Slusar | 2013-07-12 | July 22 - Meeting occurred, documentation received. | Closed
28 | Michael to wkly meeting with Scott and Clare | Michael Kennedy | 2013-07-16 |  | Closed
29 | Michael to collect 'risk' data for hardware costing over 5k | Michael Kennedy | 2013-08-23 | We would want to collect serials, make, models for an insurance inventory for all risk coverage: http://www.risk.cornell.edu/insurance/all_risk.cfm | Open
30 | Michael to outline confidence monitor positioning onsite next week. | Michael Kennedy | 2013-07-24 | July 23 - Feasible locations for confidence monitors is very limited. | Closed
31 | Michael and NAT to identify physical dataport availability in rooms. | Michael Kennedy | 2013-07-24 | July 25 - Ports (Big Red: 3.1-005) Touchdown (3.1-00153) Ursa (3.1-149) Dubi (3.1-147) | Closed
32 | Michael to find the Logitech camera previously installed in Big Red | Michael Kennedy | 2013-07-24 | July 22 - camera located. | Closed
33 | Michael to determine if new requirement for whiteboards in Touchdown can be ordered by Tom and installed by NAT | Michael Kennedy | 2013-07-24 | July 23 - whiteboard sizes have been provided to Tom. He will be ordering - boards due onsite week of Aug. 12 July 16 - contact Julia Dumas with questions re: purchasing | Closed
34 | Greg to draft commissioning process for new rooms at NYC tech and coordinate room scheduling for connection (Aug 6, 9) | Greg Bronson | 2013-07-26 | Aug 6 - testing protocol confirmed, rooms for testing are booked July 30 - Greg and Andy to identify and book Ithaca room for Aug 6th and 9th testing. July 22 - Commissioning checklist has been developed | Closed
35 | Michael to coordinate Crestron user interface review | Michael Kennedy | 2013-07-19 | July 30 - review occurred. Instructions provided to Nick. Barbara to review VC component. July 26 - mock-up will not be arriving. July 22 - mock-ups to arrive July 25, Review mtg scheduled for July 30. BF, AP, AS, MK, NB to attend. | Closed
36 | Nick to send list of all equipment requiring IP addresses | Nick Barnes (MK) | 2013-07-30 | Aug 14 - IP table being managed by Andy P. July 30 - address bank has been provided to NAT; they are assigning and will provide to Andy P. and network team (Kyle) July 24 - Nick and Andy are coordinating | closed
37 | Michael to ensure SIP information for phone tie-in is provided to NAT | Michael Kennedy | 2013-07-30 | Aug 6 - SIP tie-in not possible. Alternate solution required. This item is now being tracked through other action items. Aug 1 - Nick is connecting with Ed Fisher to work on work-around. Request for dedicated POTS has been sent to Geri July 30 - SIP tie-in limitations. July 24 - Email sent to Andy, Greg and Scott | Closed
38 | Michael to ensure ports are configured for VC Aug 12 - Additional Ports required for touch panels in conference rooms | Michael Kennedy | 2013-08-05 | Aug 14 - Andy P and Nick discussing switching solution. Expedition with network group re: switching needs likely required Aug 12 - Additional ports required in conference rooms (for touch panel) Aug 6 - Port provided to Scott; Scott to have configured July 31 - identified port numbers has been distributed via email July 25 - Andy P. is leading. Request has been sent to network from Andy's team. Kyle Pond from AV engineering July 24 - Email sent to Scott and Andy P. to confirm process | Closed
39 | Barbara to prepare user documentation for AV systems | Barbara Friedman |  | Aug 26 - Onsite. Amendments required Aug 14 - Classroom documentation ready Aug 15, conference room Aug 23. Aug 12 - Underway. Should be ready for Aug 15 July 24 - Michael and Beth are available to support documentation production | Open
40 | Michael to coordinate HVAC balancing | Michael Kennedy | 2013-08-05 | Aug 27 - HVAC balanced in Big Red. HVAC shut down in Dubi, Ursa, Touchdown - Geri addressing Aug 14 - HVAC balancing for Big Red approved. Awaiting scheduled dates. Aug 12 - HVAC is additional scope. Quote received, Andy S. to determine next steps. Aug 5 - Call with Tareq from Derector Associates to meet team at 2:00pm, aug 7th onsite to discuss HVAC July 31 - requests made to Geri and Bob (architect) July 23 - request has been made to Geri. | Open
41 | Phase II planning – What rooms are in scope? Dan H – may turn them into offices. | Andy Slusar | 2013-08-30 |  | Open
42 | Michael to confirm required steps for Panopto set up. And confirm/communicate Panopto recordings management | Michael Kennedy | 2013-08-02 | Aug 6 - Barbara and Mike T. are in convo with Scott re: loaner laptop Panopto set-up. Aug 2 - NYC Tech folder created. Panopto trialed - easy to use. Aug 1 - Email sent to Mike T. with use case outlined - requesting recommended approach - to be presented to Scott. July 29 - Email sent to Barbara and Mike. Barbara responded that she would work with Mike to set-up Panopto for NYTech. Follow-up required. Schedule/timing confirmation July 31. | Closed
43 | Investigate use of area rug behind lectern to denote camera range. | Michael Kennedy | 2013-08-12 |  | hold
44 | Test plan schedule, coordination and integration | Michael Kennedy | 41491 | July 30 - confirming user documentation deliverables July 31, schedule updates to follow | Closed
45 | Produce list of use cases for functional testing | Barbara Friedman | 2013-08-02 | July 30 - Mtg (MK and BF) scheduled for July 31 to draft use case testing plan | Closed
46 | Clare to Discuss AV and AT solutions with Ragit | Clare Van Den Blink | 2013-08-02 |  | hold
47 | Order 2 Wacoms for Cornell Tech | Barbara Friedman | 2013-08-02 |  | hold
48 | Ensure Rooms are exclusively reserved for Installations | Michael Kennedy | 2013-08-05 | July 30 - Room bookings at NYC have been confirmed as per NAT's request. Rooms at Ithaca are outstanding - Greg and Andy to coord. | Closed
49 | Schedule meeting between Kyle and Nick Barnes | Andy Page | 2013-07-30 |  | Closed
50 | Andy Page to schedule Ithaca rooms and required resources for intersite testing - August 6th and August 9th. | Andy Page | 2013-07-31 | Aug 12 - Intersite for Touchdown, Dubi and Ursa req'd Aug 6 - Big Red Complete | closed
51 | Andy P. and Greg confirm use of vaddio will enable camera and microphone inegraton for webex, skype, etc. | Greg Bronson | 2013-08-06 |  | Closed
52 | Andy S. to connect with Scott and coordinate inclusion of dedicated laptop to support Panopto recording in Classrooms | Andy Slusar | 2013-08-12 | Aug 12 - confirmation of ownership required (what files to be uploaded) Aug 6 - loaner laptops onsite have been identified for use. | Closed
53 | Barbara to look into go-wire and report user experience to team - to make decision re: purchasing it | Barbara Friedman | 2013-08-02 | Aug 6 - wire discontinued. Aug 1 - wire is avaialble for product review, Barbara will pick it up and review. | Closed
54 | Confirmation of student sign-off requirements for student project recodings is required. | unassigned |  |  | hold
55 | Michael to articulate recommended approach for managing panopto recordings - for discussion with Scott | Michael Kennedy | 2013-08-06 | Aug 27 - Email outlining use case sent to Andy S., Barbara, and Mike for discussion. Onsite point-person likely required to map process. Aug 12 - Bryan and Barbara are discussing Panopto set up. Aug 6 - Bryan (support resource) has used the program before. Aug 1 - Email sent to Mike T. with use case outlined - requesting articulation | Open
56 | Michael to confirm August and September shedule for Big Red and identify sessions requiring high level of support | Michael Kennedy | 2013-08-06 | Aug 12 - August 26th and 27th = Orientation. High level of support required. Aug 30 = likely first guest speaker; Sept 3rd = first distributed class | Closed
57
58
59
60
57 | Andy Page to provide recommendation re: phone integration (re: unavailability of SIP). | Andy Page | 2013-08-19 | Aug 14 - Andy Page meeting with Ed Fisher Aug 15 to discuss solution Aug 14 - Geri has provided two analog phone lines to support phone integration. BigRed: 212-255-8642 Touchdown: 212-255-8763 | Open
58 | Andy Slusar to communicate SIP issues and absence of phone integration for Day 1 to stakeholders | Andy Slusar | 2013-08-12 | Aug 14 - solution found. No longer requird. | Closed
62 | Andy Page to develop tech support plan (checklist tasks and activities) | Andy Page | 2013-08-19 | Aug 28 - Andy working with Dan H. group to document requirements. Now outside of project scope. | Closed
60 | Greg to review and approve as-built drawings | Greg Bronson | 2013-08-23 | Aug 26 - outstanding shop drawings included in deficiency list | Open
61 | Andy Slusar to review and approve
61 | Michael to consolidate information required for guest users (breakdown of room functionality/limitaton for BYOD incl. expectations re: drivers). | Michael Kennedy | 2013-08-23 | Aug 27 - Awaiting Panopto recording process | Open
62 | Michael to coordinate with Scott to determine process for having drivers installed on faculty laptops | Michael Kennedy | 2013-08-23 | Aug 28 - Chris F. preparing msi file for simplified download of drivers via usb hub in classrooms | Open
63 | Andy Page to link potential 'technical issues' with responsible support person and provide information in operations hand-over | Andy Page | 2013-08-23 | Aug 26 - Occuring within CIT team. | Closed
64 | Andy Slusar to schedule meeting with Michelle Reynods to discuss Help Desk education (req'd documentation; req'd | Andy Slusar | 2013-08-23 |  | Closed
66 | Michael to draft AV system functionality matrix for Geri | Michael Kennedy | 2013-08-23 | Aug 28 - Drafted. To be provided to Jen for inclusion in project documents. | Open
67 | Michael to contact Scott/Geri re: moving data in Touchdown | Michael Kennedy | 2013-08-23 |  | Open
68 | Andy Page to determine 'support handover date' when password protected system access is put in place by CIT for the rooms at Cornell Tech. | Andy Page | 2013-09-30 |  | Open
69 | Andy Page to work with NAT to populate the address books in Dubi, Ursa, Big Red and Touchdown | Andy Page | 2013-09-06 |  | Open
70
71
72
73
74