## Sheet1
ID | Owner | Individual | Type | Area | Issue | Room | Date Noted | Impact | Status | Comments
1 | NAT | NAT | Deficiency | Touchpanel | Camera control functionality in Touchdown not responding consistently | Classrooms | 2013-08-20 | High | Open | Sep 3 - MK had issues with camera control: Andy P. to try to reproduce issues and articulate (or close).
2 | NAT | NAT | Addition | Infrastructure | AirMedia for classrooms | Classrooms | 2013-08-20 | Medium | Open | Sep 3 - Airmedia to be installed Friday, September 6
3 | NAT | NAT | Deficiency | Infrastructure | Lectern Temperature operating out of range | Classrooms | 2013-08-20 | Critical | Closed | Sep 3 - Completed. Aug 27 - Letern fans are being installed Aug 29
4 | AT | MK | Deficiency | Software/ Infrastrucure | Panopto Recording Quality poor - see Barbara's and Mike T's memos | All | 2013-08-20 |  | Closed | Aug 26 - quality recording achieved
5 | CIT | AS | Outstanding | Support | Support Model definition/communication | All | 2013-08-20 | High | Open
6 | CIS | SY | Outstanding | Software | Driver installation on Laptops | All | 2013-08-20 | Medium | Open | Aug 27 - Scott to manage process
7 | CIT | AP | Outstanding | Support | System Testing and Maint Schedule | All | 2013-08-20 | Low | Open | Aug 27 - Andy Page to develop and communicate
8 | NAT | NAT | Deficiency | Infrastructure | Macs plugged in before sharing content - screen flickers | Classrooms | 2013-08-20 | Low | Open | Sep 3 - Andy Page to try to reproduce and further articulate issue Aug 28 - Addressed through unplugging and replugging Mac - but shouldn't happen in the first place.
9 | NAT | NAT | Deficiency | Software/ Infrastrucure | Camera remains active when WebEx session is ended | Classrooms | 2013-08-20 | Medium | Open | Sep 3 - Andy Page to reproduce onsite Aug - WebEx and Standard VC
10 | NAT | NAT | Deficiency | Infrastructure | Student Camera is shaking in Big Red | Big Red | 2013-08-21 | Medium | Open | Sep 3 - Rubber washers have been installed. Andy Page to assess impact of shaking on users. Aug 27 - Severity of the problem needs to be assessed. It it only noticable in high zoom?
11 | NAT | NAT | Deficiency | Infrastructure | Poor audio quality during WebEx | Classrooms | 2013-08-22 | Critical | Open | Sep 3 - Ticket is open with WebEx, NAT and Andy are pursuing a solution using analog phone lines
12 | CIT | AS | Outstanding | Support | MOU re: support documented and communicated to users | All | 2013-08-21 | High | Open
13 | NAT |  | Outstanding | Infrastructure | Assisted listening device tested | Classrooms | 2013-08-22 |  | Addressed | Sep 3 - Andy P. to confirm in touchdown; big red is functional
14 | NAT | NAT | Outstanding | Documentation | Latest copy of DSP Programming required | All | 2013-08-27 | Medium | Open | Sep 3 - NAT will provide by Friday September 6 Aug 26 - last known copies received Aug 26
15 | CIT | GB | Outstanding | Infrastructure | iPad as a source is HDCP protected and cannot feed VTC. To mitigate this (and allow other iPad presentation beyond encrypted movies) Nick will activate/deactivate in VTC based on content share input selection and then by call end | Classrooms | 2013-08-27 | High | Open | Aug 28 - Action Required and detailed outline of what is possible, what is not required
16 | AT | AS/BF | Outstanding | Documentation | Need to document that for "soft CODECs" (Skype, WebEx, etc.) that the respective software setting for "auto-level adjust" is turned Off | All | 2013-08-27 | Medium | Open | Aug 28 - Can this be circumvented entirely?
17 | CIT/AT | GB/BF | Outstanding | Documentation | Battery Management Plan | All | 2013-08-27 | Low | Open
18 | CIT/NAT | AP | Outstanding | Infrastructure | Audioconferencing interface (SIP) | Classrooms | 2013-08-27 | Low | Open | Sep 3 - Solution to be implemented by NAT Friday, September 6 Aug 27 - Workout is in place via analog lines; long term SIP is req'd
19 | AT | BF/MK | Outstanding | Documentation | Content Management Plan re: Panopto recordings | All | 2013-08-27 | High | Open | Aug 28 - Barbara has outlined approach. Individiual at Cornell Tech needs to be identified to manage the recordings (admin? prof?)
20 | NAT | NAT | Outstanding | Documentation | Latest copy of Crestron control programming required | Classrooms | 2013-08-27 | Medium | Open | Sep 3 - NAT will provide by Friday September 6 Aug 26 - Last known copies received Aug 21
21 | NAT | NAT | Outstanding | Infrastructure | Turn over of OEM "gack" for furture tech support (additional remote controls and/or AV hookup cables, etc. not otherwise needed for day to day operations) | All | 2013-08-27 |  | Open | Sep 3 - Equipment has been placed in lectern drawers - R.Boyer to confirm
22 | NAT | NAT | Outstanding | Documentation | As Built documentation (manual PDF's, signal flow/risers finals, other tech support info) | All | 2013-08-27 | Medium | Open | Sep 3 - NAT will provide by Friday September 6 Aug 26 - Greg required drawings for review
23 | NAT | NAT | Deficiency | Infrastructure | Crestron touch panels screens are washed out | Classrooms | 2013-08-27 | Low | Open | Sep 3 - Simple swap required. Crestron stock issue, date TBD.
24 | CIT | MK | Deficiency | Environmentals | Room air handling is loud in Touchdown. | Touchdown | 2013-08-27 | Medium | Open | Aug 26 - Geri has contacted contractors, they are scheduled to address Friday, Aug 30
25 | NAT | NAT | Outstanding | Infrastructure | Audio balancing - now that Big Red HVAC levels are acceptable | Big Red | 2013-08-27 | Low | Closed
26 | AT | BF/AS | Outstanding | Documentation | Due to use of Cisco codec and SmartTech Sympodium pass through for laptop input/switch no HTCP encrypted content (copyrighted material) is supported | All | 2013-08-27 |  | Open | Aug 28 - Are there work arounds? Or, we need to let everyone know
27 | NAT | NAT | Deficiency | Infrastructure | Old Micophone holes in Big Red need to be plated | Big Red | 2013-08-27 | Low | Open | Sep 3 - NAT to complete Friday, September 3
28 | CIT | AS | Outstanding | Network | Ethernet for laptops is not available in classrooms - patching required | Classrooms | 2013-08-27 | Low | Open | Aug 26 - Suggestions need to be passed on to Geri/Scott
29 | CIT | NAT | Outstanding | Environmentals | Label required for blackout blind switch | Big Red | 2013-08-27 | Low | Open | Sep 3 - Andy P to complete onsite. NAT to bring label maker Friday, Sept 6.
30 | NAT | NAT | Outstanding | Environmentals | Cable labels required for Conferene Rooms | Conference | 2013-08-27 | Medium | Closed
31 | NAT | NAT | Deficiency | Infrastructure | Connecting more than three sites in standard VC is not supported - audio only for third site | Classrooms | 2013-08-27 | High | Open | Sep 3 - Licenses arrived. Andy P to confirm full functionality. Aug 23 - Multi-site issue
32 | CIS | SY/MK | Outstanding | Software | msi of exactly what's needed for smart driver to be created and placed on usb hub | Classrooms | 2013-08-27 | Low | Open | Aug 26 - Chris has created; MK to test
33 | NAT | NAT/AP | Outstanding | Documentation | Process outlined for wireless access to the projectors | Classrooms | 2013-08-27 | Low | Open | Sep 3 - Friday Sep 6 - air media to address connection (process outline still req'd).
34 | NAT | NAT | Deficiency | Touchpanel | System auto-mutes when some BYOD are plugged in (Windows 8 using HDMI). No way to unmute on the touch panel - have to touch hit the lit button on Vaddio. | Classrooms | 2013-08-28 | Critical | Open | Sep 3 - NAT and Andy P. to review and propose solution - potentially user education. Aug 27 - This is a repeatable problem and renders some laptops useless for presenting audio
35 | NAT | NAT | Outstanding | Infrastructure | See if Panopto can benefit from DSP noise gate | Classrooms | 2013-08-28 | Low | Open | Sep 3 - NAT to address on Friday September 6 site visit Aug 26 - Panopto recordings sounds good but there doesn't seem to be any type of noise gate - all noise in the room is captured.
36 | CIT | AP | Outstanding | Network | Firewall needs to be extablished for VC units - units are being called by anonymous numbers | Classrooms | 2013-08-28 | High | Open
37 | CIT | MK | Outstanding | Documentation | Risk data required for hardware costing over $5000 | All | 2013-08-03 | Low | Open | Aug 29 - S/N requested from NAT
38 | CIT | MK | Outstanding | Documentation | Consolidated information required for guest users (expectations re: drivers) | All | 2013-08-23 | Medium | Open
39 | CIT | MK | Outstanding | Documentation | AV System Functionality document/matrix | All | 2013-08-23 | Medium | Open | Aug 28 - Document drafted and reviewed by A.Page. Provided to Jen for distribution
40 | CIT | AP | Deficiency | Infrastructure | Address bookes in Dubi, Ursa, Big Red, Touchdown need population | All | 2013-08-23 | Medium | Open | Sep 3 - Andy P. to complete Friday, Sept 6
41 | NAT | NB | Outstanding | Infrastructure | As it relates to the iPad HDCT - confirm that Nick modified the Crestron code | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - Nick to explain configuratio to Andy P.
42 | NAT | PN | Deficiency | Infrastructure | Vadio only has left channel audio | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - NAT to address on Friday Sept 6 site visit
43 | NAT | PN | Addition | Infrastructure | Add-on camera control for soft codec | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - NAT to provide pricing to A.Slusar for review
44 | CIT | AP | Outstanding | Infrastructure | Standard VC is getting spam called | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - Andy P and N.Barnes to discuss solutions
45