## Sheet1
ID | Owner | Individual | Type | Area | Issue | Room | Date Noted | Impact | Status | Comments
1 | NAT | NAT | Deficiency | Touchpanel | Camera control functionality in Touchdown not responding consistently | Classrooms | 2013-08-20 | High | Closed | Sep 6 - Confirmed that camera control is responding, but left and right reversed on instructor camera. This was resolved. Sep 3 - MK had issues with camera control: Andy P. to try to reproduce issues and articulate (or close).
2 | NAT | NAT | Addition | Infrastructure | AirMedia for classrooms | Classrooms | 2013-08-20 | Medium | Closed | Sep 6 - Installed, touch panel updated, and testing well Sep 3 - Airmedia to be installed Friday, September 6
3 | NAT | NAT | Deficiency | Infrastructure | Lectern Temperature operating out of range | Classrooms | 2013-08-20 | Critical | Closed | Sep 12 - Lectern has been running cool since fan installation and HVAC balancing. Aug 27 - Letern fans are being installed Aug 29
4 | AT | MK | Deficiency | Software/ Infrastrucure | Panopto Recording Quality poor - see Barbara's and Mike T's memos | All | 2013-08-20 |  | Closed | Aug 26 - quality recording achieved
5 | CIT | AS | Outstanding | Support | Support Model definition/communication | All | 2013-08-20 | High | Open
6 | CIS | SY | Outstanding | Software | Driver installation on Laptops | All | 2013-08-20 | Medium | Open | Aug 27 - Scott to manage process of getting software onto professor machines (CIT to provide support as requested).
7 | CIT | AP | Outstanding | Support | System Testing and Maint Schedule | All | 2013-08-20 | Low | Open | Aug 27 - Andy Page to develop and communicate
8 | NAT | NAT | Deficiency | Infrastructure | Macs plugged in before sharing content - screen flickers | Classrooms | 2013-08-20 | Low | Open | Sep 6 - Reproduced by Andy Page. Count not reproduce with NAT. NAT is pursuing with Crestron. Sep 3 - Andy Page to try to reproduce and further articulate issue Aug 28 - Addressed through unplugging and replugging Mac - but shouldn't happen in the first place.
9 | NAT | NAT | Deficiency | Software/ Infrastrucure | Camera remains active when WebEx session is ended | Classrooms | 2013-08-20 | Medium | Closed | Sep 6 - Removed PIP/POP buttons as they do not provide functionality in dual screen configurations Sep 3 - Andy Page to reproduce onsite Aug - WebEx and Standard VC
10 | NAT | NAT | Deficiency | Infrastructure | Student Camera is shaking in Big Red | Big Red | 2013-08-21 | Medium | Closed | Sep 12 - Concluded impact of shaking not critical. Item Closed unless re-opened by user concerns. Sep 3 - Rubber washers have been installed. Andy Page to assess impact of shaking on users. Aug 27 - Severity of the problem needs to be assessed. It it only noticable in high zoom?
11 | NAT | NAT | Deficiency | Infrastructure | Poor audio quality during WebEx | Classrooms | 2013-08-22 | Critical | Open | Sep 12 - Ticket open with Cisco WebEx engineering. Dependency with Item 25. Sep 3 - Ticket is open with WebEx, NAT and Andy are pursuing a solution using analog phone lines
12 | CIT | AS | Outstanding | Support | MOU re: support documented and communicated to users | All | 2013-08-21 | High | Open
13 | NAT |  | Outstanding | Infrastructure | Assisted listening device tested | Classrooms | 2013-08-22 |  | Closed | Sep 6 - Confirmed operational Sep 3 - Andy P. to confirm in touchdown; big red is functional
14 | NAT | NAT | Outstanding | Documentation | Latest copy of DSP Programming required | All | 2013-08-27 | Medium | Open | Sep 3 - NAT will provide by Friday September 6 Aug 26 - last known copies received Aug 26
15 | CIT | GB | Outstanding | Infrastructure | iPad as a source is HDCP protected and cannot feed VTC. To mitigate this (and allow other iPad presentation beyond encrypted movies) Nick will activate/deactivate in VTC based on content share input selection and then by call end | Classrooms | 2013-08-27 | High | Open | Aug 28 - Action Required and detailed outline of what is possible, what is not required
16 | AT | AS/BF | Outstanding | Documentation | Need to document that for "soft CODECs" (Skype, WebEx, etc.) that the respective software setting for "auto-level adjust" is turned Off | All | 2013-08-27 | Medium | Open | Aug 28 - Can this be circumvented entirely?
17 | CIT/AT | GB/BF | Outstanding | Documentation | Battery Management Plan | All | 2013-08-27 | Low | Open
18 | CIT/NAT | AP | Outstanding | Infrastructure | Audioconferencing interface (SIP) | Classrooms | 2013-08-27 | Medium | Closed | Sep 6 - SIP gateway installed and audio conferencing added back into touch panel. Audio fine tuning req'd (Item 25) Sep 3 - Solution to be implemented by NAT Friday, September 6 Aug 27 - Workout is in place via analog lines; long term SIP is req'd
19 | AT | BF/MK | Outstanding | Documentation | Content Management Plan re: Panopto recordings | All | 2013-08-27 | High | Open | Aug 28 - Barbara has outlined approach. Individiual at Cornell Tech needs to be identified to manage the recordings (admin? prof?)
20 | NAT | NAT | Outstanding | Documentation | Latest copy of Crestron control programming required | Classrooms | 2013-08-27 | Medium | Open | Sep 3 - NAT will provide by Friday September 6 Aug 26 - Last known copies received Aug 21
21 | NAT | NAT | Outstanding | Infrastructure | Turn over of OEM "gack" for furture tech support (additional remote controls and/or AV hookup cables, etc. not otherwise needed for day to day operations) | All | 2013-08-27 |  | Open | Sep 3 - Equipment has been placed in lectern drawers - R.Boyer to confirm
22 | NAT | NAT | Outstanding | Documentation | As Built documentation (manual PDF's, signal flow/risers finals, other tech support info) | All | 2013-08-27 | Medium | Open | Sep 3 - NAT will provide by Friday September 6 Aug 26 - Greg required drawings for review
23 | NAT | NAT | Deficiency | Infrastructure | Crestron touch panels screens are washed out | Classrooms | 2013-08-27 | Low | Closed | Sep 12 - Ross and Andy Page cannot confirm washed out touch panels. Sep 3 - Simple swap required. Crestron stock issue, date TBD.
24 | CIT | MK | Deficiency | Environmentals | Room air handling is loud in Touchdown. | Touchdown | 2013-08-27 | Medium | Open | Aug 26 - Geri has contacted contractors, they are scheduled to address Friday, Aug 30
25 | NAT | NAT | Outstanding | Infrastructure | Audio balancing - now that Big Red HVAC levels are acceptable | Big Red | 2013-08-27 | Low | Open | Sep 12 - Now that SIP audio conferencing is installed, and HVAC balanced, consolidating all audio fine tuning (WebEx, Panopto, Video Conferencing, and Audio Conferencing) to this Item 25. Student microphones for Audio Conferencing need fine tuning.
26 | AT | BF/AS | Outstanding | Documentation | Due to use of Cisco codec and SmartTech Sympodium pass through for laptop input/switch no HTCP encrypted content (copyrighted material) is supported | All | 2013-08-27 |  | Open | Aug 28 - Are there work arounds? Or, we need to let everyone know
27 | NAT | NAT | Deficiency | Infrastructure | Old Micophone holes in Big Red need to be plated | Big Red | 2013-08-27 | Low | Open | Sep 12 - Pending confirmation Sep 3 - NAT to complete Friday, September 3
28 | CIT | AS | Outstanding | Network | Ethernet for laptops is not available in classrooms - patching required | Classrooms | 2013-08-27 | Low | Open | Aug 26 - Suggestions need to be passed on to Geri/Scott
29 | CIT | NAT | Outstanding | Environmentals | Label required for blackout blind switch | Big Red | 2013-08-27 | Low | Closed | Sep 6 - Complete Sep 3 - Andy P to complete onsite. NAT to bring label maker Friday, Sept 6.
30 | NAT | NAT | Outstanding | Environmentals | Cable labels required for Conferene Rooms | Conference | 2013-08-27 | Medium | Closed | Sep 12 - Complete
31 | NAT | NAT | Deficiency | Infrastructure | Connecting more than three sites in standard VC is not supported - audio only for third site | Classrooms | 2013-08-27 | High | Open | Sep 12 - Awaiting Licenses Sep 3 - Licenses arrived. Andy P to confirm full functionality. Aug 23 - Multi-site issue
32 | CIS | SY/MK | Outstanding | Software | msi of exactly what's needed for smart driver to be created and placed on usb hub | Classrooms | 2013-08-27 | Low | Open | Sep 3 - Handoff to Ross. Update Req'd Aug 26 - Chris has created; MK to test
33 | NAT | NAT/AP | Outstanding | Documentation | Process outlined for wireless access to the projectors | Classrooms | 2013-08-27 | Low | Open | Sep 3 - Friday Sep 6 - air media to address connection (process outline still req'd).
34 | NAT | NAT | Deficiency | Touchpanel | System auto-mutes when some BYOD are plugged in (Windows 8 using HDMI). No way to unmute on the touch panel - have to touch hit the lit button on Vaddio. | Classrooms | 2013-08-28 | Critical | Open | Sep 3 - NAT and Andy P. to review and propose solution - potentially user education. Aug 27 - This is a repeatable problem and renders some laptops useless for presenting audio
35 | NAT | NAT | Outstanding | Infrastructure | See if Panopto can benefit from DSP noise gate | Classrooms | 2013-08-28 | Low | Closed | Sep 6 - Consolidated with Item 25 Sep 3 - NAT to address on Friday September 6 site visit Aug 26 - Panopto recordings sounds good but there doesn't seem to be any type of noise gate - all noise in the room is captured.
36 | CIT | AP | Outstanding | Network | Firewall needs to be extablished for VC units - units are being called by anonymous numbers | Classrooms | 2013-08-28 | High | Open
37 | CIT | MK | Outstanding | Documentation | Risk data required for hardware costing over $5000 | All | 2013-08-03 | Low | Open | Aug 29 - S/N requested from NAT
38 | CIT | MK | Outstanding | Documentation | Consolidated information required for guest users (expectations re: drivers) | All | 2013-08-23 | Medium | Open
39 | CIT | MK | Outstanding | Documentation | AV System Functionality document/matrix | All | 2013-08-23 | Medium | Open | Aug 28 - Document drafted and reviewed by A.Page. Provided to Jen for distribution
40 | CIT | AP | Deficiency | Infrastructure | Address bookes in Dubi, Ursa, Big Red, Touchdown need population | All | 2013-08-23 | Medium | Closed | Sep 6 - Complete. More addresses may be added as usage patterns emerge. Sep 3 - Andy P. to complete Friday, Sept 6
41 | NAT | NB | Outstanding | Infrastructure | As it relates to the iPad HDCT - confirm that Nick modified the Crestron code | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - Nick to explain configuratio to Andy P.
42 | NAT | PN | Deficiency | Infrastructure | Vadio only has left channel audio | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - NAT to address on Friday Sept 6 site visit
43 | NAT | PN | Addition | Infrastructure | Add-on camera control for soft codec | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - NAT to provide pricing to A.Slusar for review
44 | CIT | AP | Outstanding | Infrastructure | Standard VC is getting spam called | Classrooms | 2013-09-03 | Medium | Open | Sep 3 - Andy P and N.Barnes to discuss solutions
45 | NAT | NB | Outstanding | Infrastructure | Mute content channel when not sharing content | Classrooms | 2013-09-06 | Medium | Closed