|  | SUMMARY | FORECAST |
| --- | --- | --- |

NOW; NEXT. Efforts for NY Tech have been split into two projects. Project A, the subject of this report, is tasked with providing Academic Technology and Video Collaboration solutions for the start of fall classes for 4 rooms at the Chelsea Campus (Big Red, Touchdown, Ursa and Dubi). The Team is currently working on the conceptual design for the four rooms, ordering the equipment, detailed technical design and creation of the project plan. The Yellow status reflects the extremely tight timeframe for the project.

| Legend: | Impact to Scope, Time or Cost: |  | None |  | Caution |  | Impacted |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | MILESTONE | TARGET | REVISED | ACTUAL |
| --- | --- | --- | --- | --- |
|  | Design Brief | 02-Jul-13 | 12-Jul-13 |  |
|  | Equipment Order | Waiting for PO |  |  |
|  | PIP | 26-Jul-13 |  |  |
|  | Project Schedule | 19-Jul-13 |  |  |
|  | Room Infrastructure | 09-Aug-13 |  |  |
|  | Ursa | 23-Aug-13 |  |  |
|  | Dubi | 23-Aug-13 |  |  |
|  | Touchdown | 23-Aug-13 |  |  |
|  | Big Red | 09-Aug-13 |  |  |
|  | Support Model | 23-Aug-13 |  |  |
|  | Training | TBD |  |  |
|  | 23-Aug-13 | 28-Aug-13 |  |  |
|  | Transition to support | 28-Aug-13 |  |  |
|  | Planning for Phase II | 28-Aug-13 |  |  |

|  | PROGRESS | Milestone |
| --- | --- | --- |
|  | Project team leadership traveled to Cornell Tech for a site visit and to present the design brief to the exec sponsors. |  |
|  | Revised Design Brief based on feedback from Executive Sponsors. |  |
|  | Team began working with AV Vendor NAT on technical design |  |
|  | AV Vendor began ordering equipment. | #2 |
|  | NEXT STEPS | Milestone |
|  | Complete PIP and Distribute for approval | #3 |
|  | Complete project Schedule | #4 |
|  | # Complete technical design |  |
|  | # Schedule rooms for installation | #10 |
|  | # Define Support model for AT/VC |  |

|  | OPEN ISSUES and PLANNED ACTIONS | IMPACT ON | Milestone |
| --- | --- | --- | --- |
|  | Need to confirm use cases for whiteboarding/annotation for Ursa and Dubi with Ragit |  |  |
|  | - Need input on displays and room layout for Touchdown from Exec Sponsors |  |  |
|  | - Tight timelines for project mean there is no contingency; lead times for some equipment may be an issue. |  |  |