|  | SUMMARY | FORECAST |
| --- | --- | --- |

NOW; NEXT. Efforts for NY Tech have been split into two projects. Project A, the subject of this report, is tasked with providing Academic Technology and Video Collaboration solutions for the start of fall classes for 4 rooms at the Chelsea Campus (Big Red, Touchdown, Ursa and Dubi). The Team is currently working on the conceptual design for the four rooms, ordering the equipment, detailed technical design and creation of the project plan. The Yellow status reflects the extremely tight timeframe for the project.

| Legend: | Impact to Scope, Time or Cost: |  | None |  | Caution |  | Impacted |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | MILESTONE | TARGET | REVISED | ACTUAL |
| --- | --- | --- | --- | --- |
|  | Design Brief | 12-Jul-13 | 19-Jul-13 |  |
|  | Equipment Order | 16-Jul-13 | 18-Jul-13 |  |
|  | PIP | 26-Jul-13 |  |  |
|  | Project Schedule Confirmation | 19-Jul-13 |  |  |
|  | Room Infrastructure | 09-Aug-13 |  |  |
|  | Ursa | 23-Aug-13 |  |  |
|  | Dubi | 23-Aug-13 |  |  |
|  | Touchdown | 23-Aug-13 |  |  |
|  | Big Red | 09-Aug-13 |  |  |
|  | Support Model | 23-Aug-13 |  |  |
|  | Training | TBD |  |  |
|  | Transition to support | 28-Aug-13 |  |  |
|  | Planning for Phase II | 28-Aug-13 |  |  |

|  | PROGRESS | Milestone |
| --- | --- | --- |
|  | Confirmed core design for all rooms |  |
|  | Confirmed core AV equipment required for all rooms, communicated to vendor |  |
|  | Ordered required cabling for all rooms |  |
|  | Scheduled pre-wiring of Big Red and Touchdown for next week |  |
|  | Received vendor equipment pricing |  |
|  | NEXT STEPS | Milestone |
|  | Review and approve submitted equipment pricing | #2 |
|  | Finalize outstanding design items (projector screen location in TD; confidence monitor location in Big Red; etc.) |  |
|  | Finalize design brief and distribute | #1 |
|  | Update PIP and distribute | #3 |
|  | Confirm and distribute project schedule | #4 |
|  | # Coordinate required infrastructure addition (power for projectors in Touchdown) | #9 |
|  | # Schedule rooms for installation |  |
|  | # Develop and schedule room commissioning program | #10 |
|  | # Develop user documentation |  |
|  | # Define Support model for AT/VC |  |

|  | OPEN ISSUES and PLANNED ACTIONS | IMPACT ON | Milestone |
| --- | --- | --- | --- |
|  | - Tight timelines; lead times for some equipment may be an issue. | - Schedule |  |