|  | SUMMARY | FORECAST |
| --- | --- | --- |

NOW; NEXT. Efforts for NY Tech have been split into two projects. Project A, the subject of this report, is tasked with providing Academic Technology and Video Collaboration solutions for the start of fall classes for 4 rooms at the Chelsea Campus (Big Red, Touchdown, Ursa and Dubi). The Team is currently working on the conceptual design for the four rooms, ordering the equipment, detailed technical design and creation of the project plan. The Yellow status reflects the extremely tight timeframe for the project.

| Legend: | Impact to Scope, Time or Cost: |  | None |  | Caution |  | Impacted |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | MILESTONE | TARGET | REVISED | ACTUAL |
| --- | --- | --- | --- | --- |
|  | Design Brief | 12-Jul-13 | 19-Jul-13 |  |
|  | Equipment Order | 16-Jul-13 | 18-Jul-13 | 18-Jul-13 |
|  | PIP | 26-Jul-13 |  |  |
|  | Project Schedule Confirmation | 19-Jul-13 |  |  |
|  | Room Infrastructure | 09-Aug-13 |  |  |
|  | Ursa | 23-Aug-13 |  |  |
|  | Dubi | 23-Aug-13 |  |  |
|  | Touchdown | 23-Aug-13 |  |  |
|  | Big Red | 09-Aug-13 |  |  |
|  | Support Model | 23-Aug-13 |  |  |
|  | Training | TBD |  |  |
|  | Transition to support | 28-Aug-13 |  |  |
|  | Planning for Phase II | 28-Aug-13 |  |  |

|  | PROGRESS | Milestone |
| --- | --- | --- |
|  | Approved equipment lists and confirmed orders for all equipment | #2 |
|  | Pre-wired Big Red (90% complete) | #9 |
|  | Provided electrical requirements to electrician | #5 |
|  | Finalized outstanding design items |  |
|  | Drafted room commissioning check-list |  |
|  | NEXT STEPS | Milestone |
|  | Finalize design brief and distribute | #1 |
|  | Update PIP and distribute | #3 |
|  | Confirm and distribute project schedule | #4 |
|  | # Coordinate electrical requirements | #9 |
|  | # Schedule rooms for installation |  |
|  | # Schedule rooms for commissioning (Including Ithaca sites) | #10 |
|  | # Develop user documentation |  |
|  | # Define Support model for AT/VC |  |

|  | OPEN ISSUES and PLANNED ACTIONS | IMPACT ON | Milestone |
| --- | --- | --- | --- |
|  | - Tight timelines; lead times for some equipment may be an issue. | - Schedule |  |