|  | SUMMARY | FORECAST |
| --- | --- | --- |

NOW; NEXT. This Project is tasked with providing Academic Technology and Video Collaboration solutions for the start of fall classes for 4 rooms at the Chelsea Campus (Big Red, Touchdown, Ursa and Dubi). The Team is currently installing, testing and commissioning the equipment. We are currently on target to meet the delivery dates. The Yellow status reflects the extremely tight timeframe for the project.

| Legend: | Impact to Scope, Time or Cost: |  | None |  | Caution |  | Impacted |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | MILESTONE | TARGET | REVISED | ACTUAL |
| --- | --- | --- | --- | --- |
|  | Design Brief | 12-Jul-13 | 19-Jul-13 |  |
|  | Equipment Order | 16-Jul-13 | 18-Jul-13 | 18-Jul-13 |
|  | PIP | 26-Jul-13 |  |  |
|  | Project Schedule Confirmation | 19-Jul-13 |  | 31-Jul-13 |
|  | Room Infrastructure | 09-Aug-13 |  |  |
|  | Ursa | 23-Aug-13 | 16-Aug-13 |  |
|  | Dubi | 23-Aug-13 | 15-Aug-13 |  |
|  | Touchdown | 23-Aug-13 | 14-Aug-13 |  |
|  | Big Red | 09-Aug-13 | 12-Aug-13 |  |
|  | Support Model | 23-Aug-13 |  |  |
|  | Training Materials | 23-Aug-13 |  |  |
|  | Transition to support | 28-Aug-13 |  |  |
|  | Planning for Phase II | 28-Aug-13 |  |  |

|  | PROGRESS | Milestone |
| --- | --- | --- |
|  | Infrastructure requirements (Electrical and HVAC) are being met |  |
|  | Installation and commissioning of Big Red and Touchdown has occurred. Camera swap is required. | #8.9 |
|  | Bryan Daily has met with the project team onsite | #10 |
|  | User documentation is well underway | #5 |
|  | Panopto account opened for NYC Tech |  |
|  | Admin user training scheduled for Monday, August 19 | #11 |
|  | Faculty have begun interacting with the system |  |
|  | Loaner laptops have been uploaded with required drivers |  |
|  | NEXT STEPS | Milestone |
|  | Complete room installations and commissioning. | #6,7,8,9 |
|  | # Finalize user documentation | #7,8,9 |
|  | # Onboard ‘boots-on-the-ground’ support. | #12 |
|  | # Train users | #11 |
|  | # Communicate support model and escalation path for AT/VC | #11 |
|  | # Define process and roles for Panopto recording management | #12 |
|  | # Outline and communicate process for loading required drivers on Cornell Tech staff laptops |  |

|  | OPEN ISSUES and PLANNED ACTIONS | IMPACT ON | Milestone |
| --- | --- | --- | --- |
|  | - Tight timelines; lead times for some equipment may be an issue. | - Schedule |  |
|  | - Support Model is on the critical path for delivery. The team will need to be in a position to support Big Red for local use starting on 12-Aug. Support for Touchdown will need to start on 15-Aug. | - Support | #10 |
|  | - Building HVAC shut down over the weekends increases the risk of equipment overheating. Programmed ‘shut down’ solution in place but coordinating an alternate HVAC schedule is highly recommended. | - Schedule |  |

|  | EFFORT and COST |  |
| --- | --- | --- |

|  | BUDGET |  | ACTUALS to Date | FORECAST Total Project | VARIANCE Total Project <1> | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | Original | Revised |  |  |  |  |
| Central IT FTE: |  |  | 1.1 | 1.1 | (1.1) |  |
| Cash ($1,000s): | 350 |  | 18 | 18 | 332 | Actuals to date are mostly Ambit consulting expenses, NAT expenses should begin hitting the account this month. Total NAT expenses should be about $242K. |
| <1> Variance: Budget minus Forecast. |  |  |  |  |  |  |