## Sheet1
ID | Issue | Description | Comments | Status
1 | HVAC Balancing in Big Red | HVAC putting out ~60db - far too loud for system. Balancing requried. | Aug 14 - HVAC balancing quote has been approved. Awaiting balancing date | Open
2 | SIP absence | Absence of SIP limits phone integration in classrooms. | Aug 14 - Analog lines provided to project team to support integration. Andy Page working with Ed Fisher to address issue | Open
3 | Cameras for Touchdown | Cisco shipped the wrong cameras. | Aug 14 - Decision made to go with Panasonic cameras - NAT to confirm logistics/pricing by end of day tomorrow. Aug 14 - Cisco cameras are out of stock. Next available shipment is mid September Aug 13 - Incorrect cameras shipped by Cisco. Patrick to determine when replacements will be shipped | Open
4 | Additional port required in both Dubi & Ursa to support telepresence panel |  | Aug 13 - Requested ports have not been patched. Andy P and Michael to review onsite | Open
5 | Technical systems management handover |  | Aug 14 - Emails sent to Dan H, Clare and Scott | Open
6 | Escalation path defined |  | Aug 14 - Emails sent to Dan H, Clare and Scott | Open