## Sheet1
ID | Issue | Description | Comments | Status
1 | HVAC Balancing in Big Red | HVAC putting out ~60db - far too loud for system. Balancing requried. | Aug 23 - addressed Aug 14 - HVAC balancing quote has been approved. Awaiting balancing date | Closed
2 | SIP absence | Absence of SIP limits phone integration in classrooms. | Aug 14 - Analog lines provided to project team to support integration. Andy Page working with Ed Fisher to address issue | Open
3 | Cameras for Touchdown | Cisco shipped the wrong cameras. | Aug 14 - Decision made to go with Panasonic cameras - NAT to confirm logistics/pricing by end of day tomorrow. Aug 14 - Cisco cameras are out of stock. Next available shipment is mid September Aug 13 - Incorrect cameras shipped by Cisco. Patrick to determine when replacements will be shipped | Closed
4 | Additional port required in both Dubi & Ursa to support telepresence panel |  | Aug 23 - ethernet daisy-chained via switch. Closed. Aug 13 - Requested ports have not been patched. Andy P and Michael to review onsite | Closed
5 | Technical systems management handover |  | Aug 26 - Awaiting communication Aug 14 - Emails sent to Dan H, Clare and Scott | Closed
6 | Escalation path defined |  | Aug 26 - Awaiting communication Aug 14 - Emails sent to Dan H, Clare and Scott | Closed
7 | HVAC in Touchdown, Dubi, Ursa | HVAC is shut down. | Aug 26 - Geri is workign with contractors to resolve. Fan blowing on lectern in Touchdown | Open