LibGuides Audit & Accessibility Compliance Initiative

Wiki: https://confluence.cornell.edu/x/H8TLFQ

Rationale

CUL is currently engaging in extensive accessibility compliance work to meet the December 2019 deadline for WCAG 2.0 Level AA standard relating to library content, as per Cornell University Policy 5.12, Web Accessibility Standards. Content created and shared on the Springshare platform is included in this compliance work. The LibGuides Subteam of PSEC Instruction submitted recommendations for this process to LDLT and AUL Mizzy in December 2018, which were accepted for implementation in January 2019.

Objective

All publicly accessible CUL LibGuides (“published” and “private”) will meet WCAG 2.0 Level AA standards for web accessibility by December 31, 2019.

Actions

- Units and guide owners determine which Guides are current and relevant, and which are not.

- Units and guide owners unpublish Guides that should not be prioritized for accessibility revisions.

- Units and guide owners update remaining Guides in order to comply with accessibility standards.

- LibGuides Subteam provides training and technical support to units and guide owners throughout the process, and reports on progress to LDLT and AUL Mizzy.

Timeline

- February-June: Audit

  - Reminders and technical support provided by LibGuides Subteam

  - Trainings and consultations hosted by LibGuides Subteam

  - Audits implemented by units and guide owners

- June: Audits completed

  - All non-priority Guides unpublished by owners

  - Subteam distributes list of remaining CUL Guides to LDLT and AUL Mizzy

- July-November: Accessibility Compliance

  - Reminders and technical support provided by LibGuides Subteam

  - Trainings and consultations hosted by LibGuides Subteam

  - Accessibility work implemented by units and guide owners

- December

  - Non-compliant Guides unpublished by owners

  - Review of remaining Guides shared with LDLT/AUL

LibGuides Administrators by Unit

| Name | Unit |
| --- | --- |
| Aliqae Geraci | Catherwood |
| Camille Andrews | Mann |
| Carole Atkinson | Kroch Asia |
| Erin Eldermire | Vet |
| Jeremy Cusker | Engineering |
| Julia Gardner | RMC |
| Ken Bolton | Hotel |
| Lynn Thitchener | Olin |
| Marsha Taichmann | Fine Arts/Africana/Music |
| Mel Jensen | Mann |
| Nina Scholtz | Law |
| Rachel Holder | Management |