## KEY
Report Type | Description
ORIG CR | original canned report requirement
NEW CR | new canned report requirement
REV CR | canned report in revision
NEW AHR | new ad hoc report requirement
REV AHR | revised ad hoc report requirement

## Summary Pivot
Functional Area | (All)
Report Type | (All)
Count of Cornell Priority | Column Labels
Row Labels | 1 | 2 | R1 | R2 | R3 | R4 | Grand Total
blocked | 1 |  |  | 6 | 3 | 2 | 12
complete | 78 | 5 | 32 | 15 | 6 |  | 136
in progress | 4 |  |  | 5 |  |  | 9
not started | 4 |  | 5 | 6 | 3 | 1 | 19
Grand Total | 87 | 5 | 37 | 32 | 12 | 3 | 176

## All CUL Reports
Report Type | Cornell Priority | Report Requirement | CR Numbers | Cornell Report Name | TDX Number | Summary | Cornell Query Status | Functional Area | Description | Notes | Target Date
ORIG CR | R2 | REP-216 |  |  |  | Academic Staff by department / campus address | blocked | Access Services | Patron name, address, department, patron status (active/expired) | need LDP 1.8
ORIG CR | R2 | REP-221 |  |  |  | Active patrons by stat code | blocked | Access Services | At Cornell, we use stat codes in the Voyager LMS for reporting on collection usage by patron demographic, such as college, department, and field of study. Stat codes can capture additional information on faculty, staff, and students. Patron demographic information is used to inform collection development and funding decisions in libraries. If this information cannot be include in the Access Services application, we would like to use Custom Fields to capture this additional information for use in reports. Examples of stat codes include: field of study, college, library card holder stat code types (show what program user got his/her library card), academic rank, department, career, program, plan. | need LDP 1.8
ORIG CR | R2 | REP-222 |  |  |  | Find new faculty (created date>=x); show dept, campus address | blocked | Access Services |  | need LDP 1.8
ORIG CR | R4 | REP-224 |  |  |  | Guest users by library card type and expiration date | blocked | Access Services |  | need LDP 1.8
ORIG CR | R4 | REP-225 |  |  |  | Guest Users with GuestID access and expiration date | blocked | Access Services | At Cornell, we currently keep track of this information manually. | need LDP 1.8
ORIG CR | R2 | REP-238 |  |  |  | Patron Notice Statistics | blocked | Access Services | Cornell needs a log of patron notices to troubleshoot problems with notices. Log should include notice type, recipient, library, service point, and date of notice. | Blocked, waiting for metadb
ORIG CR | R1 | REP-103 | CR145, CR100 | loans_counts and equipment_with_holdings_checkouts_statCodes |  | Collections use - physical (internal): Charges and Renewals by collection type (regular, reserve, laptops, other equipment) patron group and Library. | complete | Access Services | Annual library statistics; annual trend report. Collections use - physical (internal): count of charges and renewals by collection type (regular, reserve, laptops, other equipment), patron group, and Library. | done and posted
ORIG CR | R1 | REP-105 | CR107 | requests |  | Requests usage (Libary-to-Library delivery, Faculty Dept Office delivery, Remote Program delivery) | complete | Access Services | Annual library statistics; annual trend report, on-demand reporting. Delivery Services usage (Library-to-Library delivery, Faculty Dept Office delivery, Remote Program delivery). This report shows the number of requests filled in the fiscal year by owning library and pickup location. Criteria includes owning library, date requested, patron group type, pickup location. | done and posted
ORIG CR | R1 | REP-106 | CR150 | physical_and_ereserve_stats |  | Reserve statistics by semester | complete | Access Services | Semester report to all library units. At Cornell, reserve statistics include item, course, instructor, usage, semester start and end dates, and record IDs (item ID, item barcode, title call number, etc.). For e-reserves, we count the number of clicks. For physical reserves, we count the number of checkouts. These reports are used for faculty members to show them how much those items were used. This report is a "data dump" from FOLIO that will be matched to a data set from ARES to create the final report. The same data dump from FOLIO can be used for both REP-106 and REP-213. For the FOLIO data dump, we need to pull the data before libraries de-reserve their materials (close to the last day of exams). The data elements needed are: location ("unit, res" for semester, "unit, permres" for permanent reserve), service point associated with the reserve location (e.g., Uris), checkout start date, checkout end date, record IDs (item ID, item barcode, loan type associated with the reserve transaction (usually 2 hours), title, call number, material type, etc.),Â semester start and end dates, loan interval, publisher.Â Barcode is the only common data between FOLIO and Ares. Dupe barcode issue could be fixed by changing ARES in the workflow in the future. | done and posted
ORIG CR | R1 | REP-143 | CR107 | requests |  | Number of requests | complete | Access Services |  | done and posted
ORIG CR | R1 | REP-152 | CR106 | missing_items |  | Missing Items Report | complete | Access Services | This report includes items whose status is "missing," a date filter, a status filter, all item bibliographic details, owning library details, and circulation details. It is used to inform replacement decisions if needed. Business process workflows for missing and lost items vary by institution. For Cornell: should be used for searching; should include last date of discharge, in bib details, includes pagination and size (325 MARC); should include browse information (will be developed later). | This report includes items whose status is "missing," a date filter, a status filter, all item bibliographic details, owning library details, and circulation details. It is used to inform replacement decisions if needed. Business process workflows for missing and lost items vary by institution. For Cornell: should be used for searching; should include last date of discharge, in bib details, includes pagination and size (325 MARC); should include browse information (will be developed later).
ORIG CR | R1 | REP-195 | CR147_A | annual_circ_non_cons_pg_stats |  | Circulation by Patron Group (undergraduate, faculty, staff, reciprocal borrower, etc.) and borrowing location by date range. | complete | Access Services | Mostly internal reporting and analysis. For Cornell: Number of patrons in each patron group (e.g., faculty, staff, student), department, and college. Total current and historical checkouts are included. Criteria to filter by checkout date range is also included. | done and posted
ORIG CR | R3 | REP-197 | CR152 and CR153 | patron_groups_with_demographics AND active_patrons_with_demographics |  | List of borrowers with items for specified location by date range | complete | Access Services | For Chicago, mostly internal reporting and analysis. For Cornell, this report needs all patron information including patron department, item barcode, title, all item information, item location and "owning" library. For date range use due date. It should also include loan date information.Â | done and posted
ORIG CR | R1 | REP-213 | CR150 | physical_and_ereserve_stats |  | List of e-items and print items on reserve, with processing status and reserve usage to date | complete | Access Services | View items on reserve, their status and usage. At minimum I use this report to capture usage at the end of the semester and distribute it to reserve desks and archive the report on a wiki. Unit libraries use the reports to evaluate how many items are used. This report will combine data from ARES and FOLIO to show a physical count of items that have been reserved by a given date range. This report provides the source data for the Course Reserve dashboard. ARES captures bar code number for physical items only. Cornell will not be using the Reserves application. Â For the FOLIO data dump, we need to pull the data before libraries de-reserve their materials (close to the last day of exams). The data elements needed are: location ("unit, res" for semester, "unit, permres" for permanent reserve), service point associated with the reserve location (e.g., Uris), checkout start date, checkout end date, record IDs (item ID, item barcode, loan type associated with the reserve transaction (usually 2 hours), title, call number, material type, etc.),Â semester start and end dates, loan interval, publisher.Â Barcode is the only common data between FOLIO and Ares. Dupe barcode issue could be fixed by changing ARES in the workflow in the future. | done and posted
ORIG CR | R1 | REP-220 | CR153 | active_patrons_with_demographics |  | Active patrons by patron group | complete | Access Services
ORIG CR | R2 | REP-243 | CR159 | Circ_stats_2_requests |  | Volume of actions at service point | complete | Access Services | Purpose: Detect where additional staffing or changes to workflow are needed. Used for annual library statistics, staffing adjustments at service points. It is a report on number of circulation transactions by service-point and transaction type, with time aggregated to date, day of week, and hour of day. Can also be filtered to a particular date range (either a full year or a smaller date range, as needed). Alternately could be aggregated to transaction count per week. Alternately could be filtered to a single service-point. This report can be used to report weekly statistics over a full year or to review hourly statistics for a shorter time period to review staffing needs.
ORIG CR | R3 | REP-271 | CR152 and CR153 | patron_groups_with_demographics AND active_patrons_with_demographics |  | List of Patrons by Demographic Criteria | complete | Access Services | List of patrons by specific demographic criteria, such as field of study and college. Requested by Sabrina Sondhi and Bonna Boettcher. This is also used by libraries to enable selected patrons to use a pickup location that is restricted by specific demographic criteria. For example, this kind of report is needed on Law, Geneva, and Vet patrons.Â For example, using custom fields that show department and college, find Geneva/Law/Vet based patrons; include patron record create date. For entering patrons into the remote delivery database, to be authorized for pickup location = Geneva/Law/Vet. Need the create date for the patron as well as the expire date for the patron. Â Data elements needed: Patron name, patron group, patron address, patron status, status date, patron record create date | tested with new patron feed, done, and posted
ORIG CR | R2 | REP-272 | CR127 | borrow_direct_interlibrary_loan_overdue_items |  | Borrow Direct Patron Report | complete | Access Services | List of patrons who currently have Borrow Direct loans with patron name, email address, lending university, book title, and due date. Used to determine what items are overdue. Also used to determine what Borrow Direct items made due when the library is closed (and thus need renewal). Report criteria includes a filter by date range. Reports will use the FOLIO material type "Borrow Direct." Requested by Caitlin Finlay. | may be able to get just from ARES; checking with Caitlin Finlay
ORIG CR | R1 | REP-274 | CR107 |  |  | List of Delivery Requests by Process Status | complete | Access Services | Retrieve list of requests that includes filters for date of request and process status (e.g., not filled). Needs patron name and email address. Need book information such as title, owning library (effective location), pickup library, barcode number, location, call number (all request information). This is a troubleshooting report. This report should flag "no fill," open, and expired requests within a given data range in the current request queue. Report is requested by Bill Cowdery.Â
ORIG CR | R1 | REP-275 | CR107 |  |  | Contactless Pickup Report | complete | Access Services | Contactless pickup requests to date by owning library, pickup location, patron group, field of study/college, date of request, and fill status. To identify contactless pickup items, include callslip requests that occur after June 30, 2020. This includes "curbside" requests, as they cannot be separated from contactless requests. This is a delivery request to selected pickup locations on campus. For Cornell: in-house paging vs library-to-library delivery; monthly report to show owning library and pickup library for annual statistics; for in-house paging, owning and delivery library are the same
ORIG CR | R1 | REP-278 | CR105 | item_related_exceptions |  | Item, Patron, and Transaction-Related Exceptions | complete | Access Services | There are three reports which we may be able to consolidate into one: Item Related, Patron Related and Transaction Related. The most frequently used is the Item Related. It basically tells us when a book with a status (any status) has been either charged or discharged. We use this report to make sure bills are waived when lost books are returned and for general clean-up of records, such as deleting item record notes. Data fields needed are: For the item-related report, we should add patron data to each exception, so the report will contain location, exception description, item title, item ID, barcode, exception date, operator ID, patron name (patron who was associated with the loan), patron email, patron group type (faculty, staff, student, etc.). See attached reports. Report details provided by Michelle Hubbell (mah94@cornell.edu). The circulation log should have the exceptions information.
ORIG CR | R3 | REP-291 | CR145 |  |  | Decommissioned Equipment Archival Statistics | complete | Access Services | This is a circulation report for decommissioned equipment archival statistics and record cleanup. It needs to be run annually in the spring. At Cornell, this report is primarily used by Mann and Olin libraries. For circulation, those in charge of equipment will use the holding statistical code WD (withdrawn) to mark the holding record for equipment has been taken out of circulation. If the item is in repair and only temporarily out of circulation, the item will be marked with the item status = unavailable. If the item has been permanently withdrawn because it has been replaced or cannot be fixed, the item will be marked with item status = withdrawn. A report will need to be run once a year to show which items have been withdrawn and those items will be removed from the system. The report should also show circulation statistics for equipment to support future decisions about equipment purchases.Â * holding statistical code (WD) * item status (unavailable or withdrawn) * circ stats Â | posted
ORIG CR | R1 | REP-292 | CR148 | Expired patrons with overdue unreturned books |  | Expired Patrons with Lost Books; Finds all expired patrons with unreturned overdue books (most are lost). Shows book details and some patron infor (net ID, patron group). | complete | Access Services | Find expired patrons with Lost items; include book information, circ detail, patron contact information. | posted
ORIG CR | R2 | REP-88 | CR124 | lost_paid_returned |  | Lost Item Paid for via Bursar | complete | Access Services |  | done and posted
NEW AHR | 1 |  | AHR_104 | oku_materials_by_LC_class_and_year_acquired | 584406 | OKU materials by LC Class and year acquired - Voyager data | complete | Access Services | Finds the last five fiscal years of newly acquired items in OKU. Groups by LC class, bib format, number of volumes and total checkouts.Consolidated numbers, not individual for each item.Needs historical Voyager data, because we don't have year acquired in Folio. | Voyager query
NEW CR | 2 |  | CR167 | expired_patrons_with_unreturned_overdue_books |  | Finds all expired patrons with unreturned overdue books (most are lost). Shows book details and some patron infor (net ID, patron group). | complete | Access Services |  | posted
NEW CR | 1 |  | CR147_B | annual_circ_cons_pg_stats |  | Annual circulation statistics by consolidated patron group | complete | Access Services |  | posted
REV CR | 2 |  | CR107 | requests |  |  | complete | Access Services |  | posted
NEW CR | 1 |  | CR141 | Lost bursared returned |  | This report finds all items that were billed as lost, then bursared, and later returned. | complete | Access Services |  | posted
NEW CR | 1 |  | CR149 | Checkouts_by_loan_policy_and_material_type _overview |  |  | complete | Access Services | Overview of checkouts by owning library, loan policy and material type. Allows you to see how libraries are circulating their equipment. | posted
NEW CR | 1 |  | CR151 | Checkouts by Userid |  | Finds checkouts by a specific userid. This report is used to get a list of checkouts for an individual patron. It also contains patron information. | complete | Access Services |  | posted
NEW CR | 1 |  | CR155 | titles_acquired_by_fiscal_year |  | Titles acquired by Fiscal Year. Also uses Voyager Historical data. | complete | Access Services | may need to be 2 queries, one FOLIO, one Voyager, need to get subject headings | posted
NEW CR | 1 |  | CR156 | historical_charges_from_voyager |  | Finding Voyager historical charges | complete | Access Services | Clarify in posting that this is run by request only | posted
NEW CR | 1 |  | CR158 | Circ_stats_1_checkouts |  | Checkouts of the last month by library, patron group, and material type | complete | Access Services |  | posted
NEW CR | 1 |  | CR159 | circ_stats_2_requests |  | Compilation of requests grouped by date, owning library, location, type of requests, status of requests, pickup point, type of service point, patron group name, and material type. | complete | Access Services |  | posted
ORIG CR | R2 | REP-104 | CR174 |  |  | Interlibrary Loan and Borrow Direct Annual Statistics | complete | Access Services | Annual library statistics; annual trend report. This report is a count of items loaned through ILL (Interlibrary Loan) or BD (Borrow Direct). For BD at Cornell: Cornell uses the Relais system for BD. Relais automatically creates an item record in FOLIO with Borrow Direct location (owning library) and "BD-material" in material type in Inventory. For Annual Statistics for BD, we need to get the totalÂ number of items checked out using the Borrow Direct location/owning library in FOLIO within a given time range.Â For BD statistics, we also use the Metridoc service at [https://metridoc.library.upenn.edu/.¦https://metridoc.library.upenn.edu/]Â We can get number of BD checkouts from the FOLIO integration (where location/owning lib=BD), which is different from number of requests fulfilled as obtained from Metridoc (one request may be multiple volumes). For ILL at Cornell: Cornell uses the ILLIAD system for ILL. There will not be an ILL integration with FOLIO at Go Live. We will continue to gather our ILL statistics from the ILLIAD system. For Annual Statistics for ILL, we need a total count of the number of items checked out using ILL location/owning library within a given time range.Â We can get number of ILL requests fulfilled as obtained from ILLIAD (one request may be multiple volumes). For annual statistics counts, we will get these numbers from Caitlin directly from the Relais and ILLIAD systems. Count physical items sent out or borrowed from ILL and BD. | Joanne to give Linda queries for this to test and confirm; Sharon to help post once confirmed; complete and posted on 5/25/22; Linda is revising as needed for annual stats counts.
ORIG CR | 1 | REP-195 | 147_B | annual_circ_cons_pg_stats |  | Annual circulation statistics by consolidated patron group | complete | Access Services |  | To be reviewed along with all annual data queries
NEW AHR | 1 |  |  |  | 534036 | Fund expenditures by Vendor for Fund 522 | blocked | Accounting | Finds total expenditures by Vendor for Fund 522 for FY22 | requires Voyager tables
ORIG CR | R1 | REP-10 |  |  |  | Invoice Control Report/Electronic Feed | complete | Accounting | This is a series of 8 quality control reports for reconciliation used by Cornell Accounting to check invoice feed results daily.Â These gather financial data in total for all of the invoices approved the day before.Â Invoice Control report: gather financial data in total for all of the invoices approved the day before. Electronic Feed: sending by vendor, by invoice, by account number to university financial system to be paid (batch job).
ORIG CR | R1 | REP-284 |  |  |  | Summarize Approved Invoices by University Account Number and Date Range | complete | Accounting | Duplicate Invoice Status Check. This report is run daily to check for duplicate invoice numbers. In Voyager, it relies on normalized_invoice_number. Because we do not have normalized invoice numbers in FOLIO, we may need to code this report to do the normalizing in SQL (removing things like hyphens and slashes, etc). The report includes invoice number, invoice date, vendor (organization) code, invoice status hardcoded to approved, invoice amount > 0, invoice status date, order type (firm, subscription, etc.), instance ID, po line ID, order location (bill to/ship to location), invoice amount > $1000, Title. Cornell: report used by both Acquisitions and Accounting The Invoices app provides a warning message that invoice number has been used already, which will help prevent duplicate invoices. This report is needed by Accounting, but it may not be needed by Acquisitions.
ORIG CR | R2 | REP-285 |  |  |  | Expenditure Summary by Group and Fund Type | complete | Accounting | For Cornell, this report summarizes expenditures by group and fund type. The data are available In-app but an LDP report is needed for historical purposes. Data elements needed are invoice ID, invoice number, invoice amount, payment date, fund, fund type, group, and ledger. Need to bring in the transactions derived table. Important to keep transaction amount with currency in case international currencies used.Â
ORIG CR | R2 | REP-286 |  |  |  | Year-to-date Balances by Group and University Account Number | complete | Accounting | At Cornell, this report provides Year-to-date Account Balances by Group and University Account Number.Â Provides library account staff with validation and reconciliation financial data to use with university financial systems. The Finance App doesn't provide balances by external account. Data elements needed include: fund, group, ledger, fiscal year, external account. The balance will be calculated from the budget amount.Â Invoice_voucher_lines has external account number.
ORIG CR | R2 | REP-97 | CR157 | funds_and_teams_with_expense_class |  | Report based on Reporting Codes 01-08 | complete | Accounting | At Cornell, this report is for Accounting and Selectors. All Selector reports include all the funds; reporting codes 01-08 are primarily used for ARL annual statistics [List Codes and their functions, see Annual Statistics folder for ARL Report, see Linda) LM: breakout: shipping?, binding, e-expenditures (one-time, vs. ongoing). Â For Cornell, 01, 02 = electronic resources; to be covered as Expense Class 04 = lost book cost fines, fees 06 - Bindery; to be covered as Expense Class 05, 07, 08 = no longer used Â | done and posted
ORIG CR | R1 | REP-98 | CR122 | fund_detail |  | Change in Fund Allocation | complete | Accounting | Accounting report at Cornell. This report shows what changes done to allocations (increase or decrease) with date range; usually run monthly; show fund with transactions; show date allocated changed by when the transaction occured; show date occurred, amount, transaction description; this shows allocations between funds (from and to). Cannot be done by account number in the Finance application.Â | done and posted
NEW CR | 1 |  | CR136 | appr_inv_per_univ_acct_detail_date_range |  | Sum approved invoices by Univ Acct and date Range | complete | Accounting | summarize approved invoices by university account number and date range | done and posted
ORIG CR | R1 | REP-95 |  |  |  | Fund Cash Balance | not started | Accounting | This is currently done manually. We would like a way to automatically upload (roll over) fund allocations and balances at start of fiscal year | Cornell: The Rollover feature of the Finance app is being developed to cover the Voyager Cash Balance functionality, but still needs testing. If it passes testing, this report will not be needed.
NEW CR | 1 |  |  | bursar_master |  | includes all data elements from bursar reports | not started | Accounting
NEW CR | 1 |  |  | bursar_master_by_student_ID |  | Bursar amounts by item type – includes material type from FOLIO | not started | Accounting
NEW CR | 1 |  |  | bursar_amounts_by_item_type |  | Bursar amounts by item type – includes material type from FOLIO | not started | Accounting
NEW CR | 1 |  |  | bursar_amounts_by_fine_type |  | Bursar amounts by fine type – type of fine | not started | Accounting
NEW CR | 1 |  | CR179 | bursared_items_by_fine_fee_date_and_material_type | 583506 | monthly bursar transactions with material types | complete | Accounting |  | posted
ORIG CR | R2 | REP-37 |  |  |  | Ongoing Subscriptions (clean-up) | blocked | Acquisitions | Determine what subscriptions have not been sending issues; the most recent issue received is displayed (can be several years old) -claiming | Receiving app not developed enough to provide the data elements needed for this report; need to see things like publication frequency; see UINV-340
ORIG CR | R1 | REP-269 | CR123 | open_orders |  | Daily Purchase Order Status Check including Open Orders | complete | Acquisitions | LTS is considering a different workflow for this data (see Lisa Maybury, Masayo, Jesse) because live data is needed. This report may not be needed. Â At Cornell, this report will be used by Acquisitions. Daily Purchase Order status report showing PO number, purchase order status (approved, sent), Vendor ID, Vendor Code (Organization), Notes, PO lines receipt status, PO created date, PO approval date , PO Line receipt date,Â PO Type,po line item id, po line item status, copy id, fund, split fund info, order amount, requestor, title, bib id, bib format, selector, subject. Print results should be available in Iris but no search by selector? UX-PROD-1150 for exporting results in CSV. Â
ORIG CR | R1 | REP-280 | CR129 | pol_notes |  | Purchase Order Selectors Notes (ITSO report) | complete | Acquisitions | LTS is considering a different workflow for this data (see Lisa Maybury, Masayo, Jesse) because live data is needed. This report may not be needed. Â This report shows PO created, PO number, Notes field from MARC showing notes from Selectors. Still need to see how to get Notes from PO lines. This report may be able to be created from the Orders application using the Lehigh app, which creates POs from MARC records.
ORIG CR | R1 | REP-281 | CR131 | duplicate_instances_on_ISBN |  | Duplicate Orders report (LDP-based) | complete | Acquisitions | At Cornell, this is used by Acquisitions. Natalya working with Christie on this report, and with Nick on Acquisitions requirements. May need live data. To identify recent orders that duplicate already held volumes or that lack standard numbers for and require manual searching. Criteria needed: ISBN, purchase order, date created (derived), vendor code, PO number, order status, created by (UUID), created location, POL instance id, title, publication date, publisher, requestor, workflow status, instances identifier. Â This report may not be required if FOLIO can eliminate the possibility of these duplicates. Â This is essentially the same report asÂ https://issues.folio.org/browse/UXPROD-888Â except that it is LDP-based rather than in-app. h4. TestRail: Results
ORIG CR | R2 | REP-282 |  |  |  | Duplicate Invoice Status Check | complete | Acquisitions | Duplicate Invoice Status Check. This report is run daily to check for duplicate invoice numbers. In Voyager, it relies on normalized_invoice_number. Because we do not have normalized invoice numbers in FOLIO, we may need to code this report to do the normalizing in SQL (removing things like hyphens and slashes, etc). The report includes invoice number, invoice date, vendor (organization) code, invoice status hardcoded to approved, invoice amount > 0, invoice status date, order type (firm, subscription, etc.), instance ID, po line ID, order location (bill to/ship to location), invoice amount > $1000, Title. Cornell: report used by both Acquisitions and Accounting The Invoices app provides a warning message that invoice number has been used already, which will help prevent duplicate invoices.
ORIG CR | R1 | REP-283 | CR109 | standing_order_purchase_orders |  | Standing Order Purchase Order (SOPO) | complete | Acquisitions | Cornell Acquisitions only. This is a daily report run to review firm purchase orders against standing purchase orders. The report includes po_id, po_number, po create date, vendor code, order status, po line number, po line item id, ISBN, Author, Title, Publisher, Series Number (from MARC), Operator ID who created this order.Â Â Nick to set up to run in LTS shared space. Â
ORIG CR | R1 | REP-153 | CR134 | appr_invoices_bib_data |  | Serial Subscriptions Purchase Order Expenditures | complete | Acquisitions | Cornell Acquisitions made decision not to put info on serial subscriptions on purchase orders, but selectors need this information. See Natalya. The Voyager report uses invoices to show total expenditures by title because there are zero amounts on ongoing purchase orders. | cannot get from POs, but can get from invoices
ORIG CR | R2 | REP-38 |  |  |  | Subscription Payments Over Multiple Fiscal Years | in progress | Acquisitions | view cost chages to subscriptions over time; estimate serial paymets still due | Add Voyager data?
ORIG CR | R2 | REP-158 |  |  |  | Request and Verify Status of E-Resource Purchase Requests | not started | Acquisitions | At Cornell, You Lee runs this report to check which materials were invoice and purchased.Â | maybe covered by Orders app; ask You Lee Chun
ORIG CR | R3 | REP-290 |  |  |  | Monograph Claiming - Paper Only | not started | Acquisitions | This report needs to identify monographs that are overdue, have not been received â€“ data elements: title, date ordered, supplier/vendor, date expected (from PO line), ISBN, bill to/ship to to show LTS or Law Technical Services (see who placed the order). Include hard filter for one-time order type. The report should showÂ line items that have not been received and have also not been claimed, canceled, or backordered.
ORIG CR | R2 | REP-84 |  |  |  | Combined report of library print & electronic serials holdings along with ILS requests | not started | Acquisitions | Allow subject specialists and acq. librarians to determine which print volumes could be sent to remote storage. Required ILS holdings to be integrated with link resolver holdings. Current acquisition status shows open, closed, or no order for this item. | not covered by Mann Hort query
ORIG CR | R3 | REP-228 | CR168 | physical_serial_titles_currently_received |  |  | blocked | Annual Statistics | Annual Statistics. For this Cornell report, we need a list of the number of serial titles currently received. This list specifically excludes titles currently being published, for which Cornell no longer has a subscription. It would be helpful to show a distinction between e-journals and e-serials. For Cornell Annual Statistics, we need to be able to count subscriptions that are not associated with purchase orders, such as gift subscriptions. Need to see Joanna Cerro, Jean Pajerek, and Linda Miller about what is needed for this report. | receiving app not fully developed; not getting correct counts from this query
ORIG CR | R1 | REP-19 |  | volume_count_stats and volume_counts_retro_stats |  | Inventory_items_added_by_format | complete | Annual Statistics | University Purchasing requires this data for inventory. This report shows items added to the inventory by each format.
ORIG CR | R1 | REP-20 | CR144 | volume_count_stats |  | Inventory_items_withdrawn_by_format | complete | Annual Statistics | University Purchasing requires for inventory | for physical items, we can count those with withdrawn status and show date as after 7/1/21
ORIG CR | R1 | REP-21 | CR144 | volume_count_adc |  | Inventory_total_items_held | complete | Annual Statistics | University Purchasing requires this report for inventory. This report is also needed for Annual Statistics. | combining 144_A, B, and C into just CR144
ORIG CR | R2 | REP-41 | CR162, CR163, CR164 |  |  | Annual E-Resource Counts for ARL, ACRL and NCES and local reporting | complete | Annual Statistics | Annual E-Resource Counts for ARL, ACRL and NCES and local reporting | title counts
NEW AHR | R2 | REP-94 | AHR106 | east_asia_lang_subject |  | Annual Statistics for the Council of East Asian Libraries | complete | Annual Statistics | Annual Statistics for the Council of East Asian Libraries. Similar to ACRL Annual Statistics Report. See Liren Zheng for details. | This report provides a list of titles for east asia languages and subjects along with different formats.
NEW CR | 1 |  | CR162 | title_count_non-micr-physical_adc_stats |  |  | complete | Annual Statistics |  | posted
NEW CR | 1 |  | CR163 | title_count_micro_adc_stats |  |  | complete | Annual Statistics |  | posted
NEW CR | 1 |  | CR164 | title_count_servremo_adc_stats |  |  | complete | Annual Statistics |  | posted
NEW CR | 1 |  | CR160 | sound recording pieces count |  |  | complete | Annual Statistics |  | posted
NEW CR | 1 |  | CR161 | video recording pieces count |  |  | complete | Annual Statistics |  | posted
ORIG CR | R2 | REP-232 |  |  |  | All materials expenditures divided into physical vs. electronic (lower priority for breakouts by format within these divisions). (Lower priority for budgeted amounts for materials?) | not started | Annual Statistics | For Cornell, this data is used for Annual Statistics reports.This report is fulfilled by ERM Inventory Costs. You just need to leave the Physical/Electronic/PE Mix filter and format_name open. | review funds queries
ORIG CR | R4 | REP-233 |  |  |  | Materials expenditures tracked through the office of sponsored programs | not started | Annual Statistics | For Cornell, this data is used for Annual Statistics reports. This will depend on Fund setup at Cornell.
ORIG CR | R2 | REP-234 |  |  |  | Comparison Report for Print versus E-Resource Titles | not started | Annual Statistics | This report shows the estimated overlap between Print and Electronic Serial subscriptions. Matching is done on ISBNs or ISSNs. For Annual Statistics, we need to know estimated overlap between Print and E-Serial subscriptions. See Adam Chandler for details. For Cornell, this is needed by selectors and for Law Library. | see Natalya
ORIG CR | R3 | REP-289 |  |  |  | Bindery Report | not started | Annual Statistics | For Cornell, Accounting and Annual Statistics need a Bindery report on items that are "bound withs. Uses -06 funds. Need summary of charges against fund-06. Cornell will use "expense class" for items charged against Fund-06. | part of expenditures by vendor or fund; see Annual Statistics notes
NEW CR | 1 |  | CR166 | pcc_records_cataloged_by_user |  | lists PCC records cataloged by a given user | complete | Cataloging |  | posted
NEW CR | 2 |  | CR178 | cataloger_counts |  | list of titles catalogued by a staff member | complete | Cataloging |  | posted
ORIG CR | R2 | REP-154 |  |  |  | Use of print vs. e-equivalents | blocked | Collection Development | This report is designed to show selectors / collections managers best purchase and shelving options for physical versus electronic versions of the same book. For Cornell, input from selectors on the design and purpose of this report would be helpful. | requires eHoldings access
ORIG CR | R3 | REP-9 |  |  |  | Usage Data from electronic content providers | blocked | Collection Development | Provide data for public facing discovery tools | requires eHoldings access
NEW CR | 2 |  | CR173 | patron_purchase_requests | 685385 | List of requests to purchase items, including patron and item details with requestor field data; includes fund and bib data | complete | Collection Development |  | done and posted
REV CR | R1 | REP-98 | CR138 | orders_split_funds | 702673 | split funds summary based on invoices | complete | Collection Development |  | add fund id count >2
NEW CR | 1 | ` | CR165 | funds_and_teams |  | Provides a detailed report of amounts spent, encumbered, and remaining without expense class. | complete | Collection Development |  | posted
ORIG CR | R1 | REP-157 | CR101, CR130 | fund_expenditures_by_po_line_invoice_payments and fund_expenditures_by_po_line |  | Fund Expenditure Summary | complete | Collection Development | This report shows fund expenditures as the sum of the transaction amount by purchase order line grouped by fund and expense class. Fund expenditures can be viewed by fund name, fund type, fund code, purchase order line format, transaction type, expense class, and fiscal year.Â Query: fund_expenditure_summary inÂ [https://github.com/folio-org/folio-analytics] For Cornell - need to add tags with tag filters. | done and posted
ORIG CR | R2 | REP-287 |  |  |  | Fund Detail by Selector | complete | Collection Development | This report should show current fund balances by group, selector, subject, and fund type. Data elements to include are: fund group, selector (maybe), subject, ledger, fund type, fund name, original allocation, net allocation, expenditure amount, commitment amount, fund balance, fund category. Get selector data element from PO lines. Selectors can get this information from the Finance application initially, but a full report will be neededÂ for historical fund reporting. Filtering by date cannot be done in app, so this allows viewing fund details within specific dates.
ORIG CR | R1 | REP-39 | CR134 | appr_inv_bib_data |  | Fund Expenditures with Title Information | complete | Collection Development | The main query ties funds to invoices to show expenditures by fund with bibliographic information on what was purchased. Fund expenditures can be viewed by fiscal year, groups, and fund types. The title will come from the title entry at the purchase order line. For Cornell - need to add tags with tag filters. An example of this report would be Mideast/Islamica fund purchases requested by Ali Houissa, which would show purchases on a set of fund codes for FY13 - FY21, showing BIBs, locations, vendor, title, amount (from Joanne).Â Â Â | covered by appr_inv_bib_data
ORIG CR | R2 | REP-40 | CR134 | appr_inv_bib_data |  | Endowment Fund Restrictions | complete | Collection Development | This report is a listing of endowment funds with restrictions coming from the description field in the fund. Data elements to include are: today's date, fund code, fund name, fund type, fund balance, fund description, and group. Need to filter by group. | covered by appr_inv_bib_data
ORIG CR | R1 | REP-82 | CR125 | appr_invoices_vendor_funds |  | Invoice report (with order data) | complete | Collection Development | At Cornell, this report is good for selectors and accounting. This purpose of this report is to provide a summary of what was spent by purchase order line on an invoice line across all the invoices within a particular time period. Invoice line adjustments are included in the invoice line total. The "invoice_line_total_sum" column shows the sum of invoice line totals associated with each purchase order line number. This query only shows invoice line data that is linked to a purchase order. The output is aggregated by purchase order line id, purchase order line number, and invoice status.
ORIG CR | R1 | REP-83 | CR134 | appr_inv_bib_data |  | Invoice report (with bib data) | complete | Collection Development | At Cornell, this report is used by Accounting and Selectors. ItÂ is the "Approved Invoice Report by Invoice Date and Title." It includes invoice number, invoice status, invoice status (approval) date, invoice payment date, invoice line item id, ledger, subject, selector, fund, group, ledger (will show statutory or endowed) invoice line item note, order format date invoice was approved, budget group, donor, language, BIB_ID, Call Number, invoice line item description, and invoice amount. List approved invoices in a selected date range by selector, subject, fund and format. Partially fulfilled In-app. CU Med requires invoice date and invoice payment date. Main sort: PO line or Invoice Lines/Transactions Â For Cornell - need to add tags with tag filters.
NEW AHR | 1 |  | AHR100 | new and noteworthy books |  |  | complete | Collection Development |  | posted
NEW AHR | 1 |  | AHR102 | Collection Growth over time |  |  | complete | Collection Development |  | posted
NEW CR | 1 |  | CR157 |  | 614507 | Funds and teams with amounts spent, encumbered, and remaining | complete | Collection Development | updated to include expense class | posted
NEW CR | 1 |  | CR157 | funds_and_teams_with_expense_class |  |  | complete | Collection Development |  | posted
ORIG CR | R3 | REP-156 | CR171 | BD_ILL_selectors_report_part1 |  | BD_ILL_selectors_reports - details of BD/ILL items borrowed by CUL | complete | Collection Development |  | posted
ORIG CR | R3 | REP-156 | CR172 | BD_ILL_selectors_report_part2 |  | BD_ILL_selectors_reports - details of BD/ILL items borrowed from CUL | complete | Collection Development |  | posted
ORIG CR | R3 | REP-156 | CR 174 | BD_ILL_selectors_report_ counts |  | BD_ILL_selectors_reports - counts of BD/ILL items borrowed by CUL, and from CUL. | complete | Collection Development | Need Borrow Direct requests broken down by academic dept requesting, department, LC call number, and other data points; Borrow Direct spreadsheets difficult to use; show what titles people are borrowing via Borrow Direct to inform selectors. We need to know what we (Cornell) borrow from other institutions as well as what other institutions borrow from us. See Caitlin Finlay for more information. For BD at Cornell: Cornell uses the Relais system for BD. Relais automatically creates an item record in FOLIO with Borrow Direct location (owning library) and "BD-material" in material type in Inventory. For Annual Statistics for BD, we need to get the total number of items checked out using the Borrow Direct location/owning library in FOLIO within a given time range. For BD statistics, we also use the Metridoc service at https://metridoc.library.upenn.edu/. We can get number of BD checkouts from the FOLIO integration (where location/owning lib=BD), which is different from number of requests fulfilled as obtained from Metridoc (one request may be multiple volumes). Need to figure out how to bring in outside tables into Folio (barcodes from ARES), as that is the only way to create this report. May only be able to pull titles. Trying to see if we can get ISBN from Caitlin's database then match to FOLIO via table import to LDP. | posted
ORIG CR | R2 | REP-90 |  |  |  | Manage Serial Expenses | in progress | Collection Development | Show paid subscriptions by fiscal year, invoice payment date. Also include vendor, title, subscription to and subscription from, and other subscription related data elements. Typically, there is one PO line per subscription. | compare to subscription cost
ORIG CR | R2 | REP-91 |  |  |  | Serial Budget Use Report | in progress | Collection Development | This report is designed to show selectors how much of their budget has been spent on serials; show classifications for journals; need to tie fund to subscriptions through instance. Â RM Reports Team: subscription count query should mostly cover; need to add fund and budget from finance_tranactions_invoice derived table and consider that there can be multiple funds per po line. | compare to subscription cost
ORIG CR | R2 | REP-93 |  |  |  | Vendor Approval Report | in progress | Collection Development | see Kizer's standing /firm order and continuation order approval report | Continuations report underway; similar to CR134; need to specify ongoing continuations in the Order Type
NEW CR | 1 |  |  | expense_transfer | 526675 | Finds YTD paid invoice amounts. Includes holdings type, aggregated subject headings, locations for purchased items, folio and vendor invoice numbers, and split fund percentages. | in progress | Collection Development |  | query needs optimization; need to add expense class
NEW CR | 1 |  |  | continuations |  | continuation (ongoing serials or packages) expenditures | in progress | Collection Development | combine with REP-93 | in progress
ORIG CR | R2 | REP-288 |  |  |  | Estimate Serial Expenditures by Vendor | not started | Collection Development | This report shows estimated serial expenditures by unique vendor by a range of fiscal years. Data elements include vendor, title, publisher, format, location and expenditures by vendor per fiscal year (VOYRPT-526) | See if Annual Statistics material expenditures addresses this
ORIG CR | R2 | REP-36 |  | donor_report |  | Report to donor | in progress | Collection Development | generate reports of titles purchased by endowed funds--sent to the donor Â For Cornell, this may not be needed for bookplating. AAD still needs a donor letter report.Â | need to add fund description field | 2023-02-02
ORIG CR | R2 | REP-89 |  |  |  | Vendor Title Match Report | not started | Collection Development | useful for monographs and serials (database coverage comparison)
REV CR | 1 |  | CR173 | patron_purchase_requests |  | List of requests to purchase items, including patron and item details with requestor field data; includes fund and bib data | complete | Collection Development |  | posted
ORIG CR | R1 | REP-215 | CR128 | Steady State |  | Steady State Report for Moving Items to the Library Annex | complete | Collection Management | To identify specific items that can be moved to long-term storage or duplicate items held in different library locations. Data elements include title, call number, owning location, circulation history, holdings by location, and format. Identify duplicated items in existing Annex holdings (for Cornell, no duplicates can go to Annex) and other library locations. Supports process of "steady state" and other collection management reports. | covered by CR128; can be modified for different material sets
ORIG CR | R1 | REP-270 |  |  |  | Identify Materials by Language and Subject Criteria | complete | Collection Management | Identify materials in selected locations, languages, call number ranges and subject areas for evaluation. For example Mideast materials in RMC and RMC Annex (requested by Ali Houissa). There is some functionality for this in the FOLIO Inventory application. Â Â
NEW CR | 1 |  |  |  | 493824 | Bound With Materials | complete | Collection Management | list of bound-with materials for collections management | done and posted
NEW CR | 1 |  | CR146 | missing_items_date_ranges | 579363 | Missing Items with Date Ranges | complete | Collection Management | This report shows items where the item status is 'Missing'. It is different from CR106 in that it includes parameters for filtering results by the last 2 weeks, the last 6 months, the last year, the last 2 years, and a freeform start date and end date. | done and posted
NEW AHR | 1 |  | AHR101 | Nestle Library Non-Book Inventory |  |  | complete | Collection Management |  | posted
NEW CR | 1 |  | CR128 | ceased or cancelled serials |  |  | complete | Collection Management |  | posted
NEW CR | 1 |  | CR103 | annex non-circulating list |  | uses circ policy of non-circulating | complete | Collection Management |  | posted
NEW CR | 1 |  | CR176 | annex_duplicates_from_barcode_list |  | finding duplicate holdings at the annex from a list of barcodes | complete | Collection Management |  | done and posted
ORIG CR | R1 | REP-101 |  |  |  | Annex Media Report | not started | Collection Management | metadata; generate a digitization inventory for circulation items at the annex; get specifics from Cammie
ORIG CR | R1 | REP-102 |  |  |  | Digitization Inventory | not started | Collection Management | Compile catalog details for a collection that has been slated for digitization. Cornell example: collect details for a set of Music Department Recordings with the local field code 899a = â€œmusicdeptcassâ€ (see attached report). 899 field is mapped to FOLIO Inventory as an identifier. Ad hoc with general template; Michelle interested in this report as well.
ORIG CR | R1 | REP-189 |  |  |  | Shelf List by Location (item level) | not started | Collection Management | To extract records for all items that have a permanent location or temporary location that matches the location(s) selected from the location list. This can include barcode information or not. | Use call number sort fix (COLLATEC); see if we can genericize Joanne's Olin HM report
ORIG CR | R1 | REP-18 |  |  |  | HathiTrust Print Holdings | complete | HathiTrust | These are three separate (but similar) reports. Cornell annually delivers three print holdings statements (single volume monongraphs, multivolume monographs and serials). The statements include lost/withdrawn or missing items, as well as current holdings. These statements are the data source on which our annual fee is based, and also form the basis of the mechanism by which we can access preservation copies of withdrawn, lost or missing items that are in copyright. Output must be reviewed before transfer to a known Box location owned by UMich; would be good to discuss with Jenn and Adam for LTS workflows. Report has 3 parts, and there is a DRAFT version available.
ORIG CR | R3 | REP-16 |  |  |  | Processing steps for processing Google Candidate list into a picklist | not started | HathiTrust | Google uses static catalog extracts that are out of date. To refresh locations to current ones, and to deduplicate among locations, and to exclude certain locations, locations must be reconciled and new picklists derived. This report will use large tablular inputs. | need to check with Michelle and Mira
ORIG CR | R1 | REP-17 |  |  |  | HathiTrust Pre-deposit Display Preview Report | not started | HathiTrust | This report will be one large dataset. The purpose is to predict the display behavior (full or limited view) of individual items and groups of items in HathiTrust prior to deposit. This report is also used to spot catalog issues and locate rights owners. It helps Cornell understand the amount of effort it will take to display an item in full view in the local library catalog prior to depositing it in the HathiTrust digital library. Overall, the report supports decision making by curators and collection stewards in determining the appropriate destination for collections migrations. Variations of this report might be useful, but Digital Lifecycle Services staff can most likely adapt a single report themselves to a variety of nuanced needs. | need to check with Michelle and Mira; perhaps Brian working on this
ORIG CR | R1 | REP-223 | N/A | permissions_user_names |  | User by Permission Set in FOLIO | complete | Security | This report lists the names of FOLIO users and the FOLIO permissions or permission sets assigned to them | complete
NEW CR | 1 |  | CR169 | database_count_adc |  | Gets counts of databases for ACRL and NCES reporting | complete | Annual Statistics |  | posted
REV CR | 1 |  | CR175 | team_related_split_funds | 702673 | a report showing split funds by PO line that enables selectors to filter by the funds for their team while also seeing what other team funds split a purchase order payment with them | complete | Collection Development | based on request from Leah McEwan | fund_code added
NEW AHR | 2 |  | AHR 105 | cataloger_counts | 714832 | Lists items catalogued (instance id and title) by cataloger netid, date, ttype, and unit (lts, law, etc.) | complete | Metadata Management | Laura Daniels | Jean and Joanne
NEW CR | 1 |  | CR177 | in_process_items_by_location | 694061 |  | complete | Access Services |  | based on "in process" need to parameterize for items status and location
ORIG CR | R3 | REP-228 |  | electronic_serial_titles_currently_received |  | Number of serial titles currently received | blocked | Annual Statistics | Annual Statistics. For this Cornell report, we need a list of the number of serial titles currently received. This list specifically excludes titles currently being published, for which Cornell no longer has a subscription. It would be helpful to show a distinction between e-journals and e-serials. For Cornell Annual Statistics, we need to be able to count subscriptions that are not associated with purchase orders, such as gift subscriptions. Need to see Joanna Cerro, Jean Pajerek, and Linda Miller about what is needed for this report. | receiving app not fully developed
NEW AHR | 1 |  | AHR105 |  | 675937 |  | complete | Collection Management | ILR metadata cleanup report | posted
ORIG CR | R2 | REP-229 | CR154 | titles_by_subject_and_language |  | Shows titles held by subject, format, language, and location. | complete | Collection Development | Counts of resources by language/country of publication
NEW AHR | 1 |  | AHR107 | Olin HM items with circ counts showing item level detail and aggregate summary | 723423 | Lists all items in "Olin" location and "HM" LC class with pub date, date of acquisition, instance format, subject headings and circ counts (Voyager and Folio) | complete | Collection Management | Request from Leah Dodd | posted
NEW AHR | 1 |  | AHR108 | Olin HM items grouped by subject heading showing total circ counts | 723423 | Lists all items in "Olin" location and "HM" LC class with pub date, date of acquisition, instance format, subject headings and circ counts (Voyager and Folio) | complete | Collection Management | Request from Leah Dodd | posted
NEW CR | 1 |  | CR180 | 773_and_899_aggr_counts_adc |  | Gets counts of aggregators and other collections coded in 773 and 899 fields. Used to help track changes in e-counts from year to year. | complete | Annual Statistics |  | np55, lm15
NEW AHR | 1 |  | AHR109 | Mann Bee Collection - item detail and summary count |  | List of all items held at Mann, Annex and Geneva within a specified call number range for the study of bees. Includes year of publication, language, format and subject. Provide summary count by location, format, language, primary subject and century of publication. (Folio) | complete | Collection Development/ Collection Management |  | posted
NEW AHR | 1 |  | AHR110 | Phillips Endowment purchases FY01 - FY21 (Voyager) |  | List of all items purchased on the Phillips Endowment fund (p1166) from Voyager | complete | Collection Development |  | posted
NEW CR | 1 |  | AHR111 (Change to CR) | Voyager purchases by fund number |  | Same as the Phillips fund report, but generalized for any fund in Voyager; can select fund, order type or fiscal year range | complete | Collection Development |  | posted
REV CR | 1 |  | CR101 | fund_expenditures_by_po_line_invoice_payments |  |  | complete | Collection Development |  | finance_fund_id removed
REV CR | 1 |  | CR122 | fund_detail |  |  | complete | Collection Development |  | posted; revised for fiscal year fix
REV CR | 1 |  | CR123 | open_orders |  |  | complete | Collection Development |  | posted; revised for fiscal year fix
REV CR | 1 |  | CR134 | appr_invoices_bib_data |  |  | complete | Collection Development |  | posted; revised for fiscal year fix
REV CR | 1 |  | CR157 | funds_and_teams_with_expense_class |  |  | complete | Collection Development |  | posted; revised for fiscal year fix
REV CR | 1 |  | CR165 | team_related_split_funds |  |  | complete | Collection Development |  | posted; revised for fiscal year fix
ORIG CR | R2 | REP-135 | CR181 | serial_circ_count_by_instanceHRID | 566987 | This report returns circ counts from both Voyager and Folio for an individual serial by instance HRID, as selected in the parameters. Title, location, and number of items are also included. | complete | Collection Development |  | posted
NEW CR | 1 |  |  | open_orders_encumbered |  |  | in progress | Collection Development |  | new query to focus on encumbrance details of orders | 2023-02-02
ORIG CR | 1 |  | 147-A | circulation_chargesrenewals_adc |  |  | complete | Access Services |  | To be reviewed along with all annual data queries
REV CR | 1 |  | CR183 | laptop_circ_count |  |  | complete | Access Services |  | posted
NEW CR | 1 |  | CR182 | voyager_checkouts_by_circ_desk |  | desk activity at circulation from Voyager data; circ desk activity for circulation | complete |  |  | posted
REV CR | R2 | REP-135 | CR181 | serial_circ_count_by_instanceHRID | 566987 | This report returns circ counts from both Voyager and Folio for an individual serial by instance HRID, as selected in the parameters. Title, location, and number of items are also included. | complete | Collection Development |  | revised to run faster
NEW CR | 1 |  | CR189 | book list |  | list of books (monographs) by library | complete | Access Services | creates a list of books at a specified library showing title, author, call number, year of publication and number of circs (Voyager plus Folio)
NEW CR | 1 |  | CR188 | Acronyms item level |  | items that contain selected acronyms in the title at the item level | complete | Collection Management
NEW CR | 1 |  | CR187 | Acronyms holdings level |  | items that contain selected acronyms in the title at the holdings level | complete | Collection Management
NEW CR | 1 |  | CR186 | Ceased or Cancelled Titles at the Item Level |  |  | complete
NEW CR | 1 |  | CR185 | Ceased or Cancelled Titles at the Holdings Level |  |  | complete
REV CR | 1 |  | CR184 | Physical Collections Use for Tableau |  |  | complete |  |  | will be superceded by 184A
REV CR | 1 |  | CR143_A | Hathi serials |  |  | complete |  |  | Posted
REV CR | 1 |  | CR143_B | Hathi monographs |  |  | complete |  |  | Posted
REV CR | 1 |  | CR143_C | Hathi multivolumes |  |  | complete |  |  | Posted
REV CR | 1 |  | CR128 | Ceased or Cancelled Serials - holdings level |  |  | complete |  |  | Posted revision 10-6-22
NEW CR | 1 |  |  | List of inactive patrons with open fines |  |  | complete |  |  | need to post
NEW CR | 1 |  | CR128B | Ceased or Cancelled Serials - Item Level |  |  | complete |  |  | posted
NEW CR | 1 |  | CR184A | physical_collections_use |  | This query is an annual circulation count query by material type and patron group. | complete |  |  | posted
REV CR | 1 |  | CR184B | physical_collections_use_split |  | This report splits up CR184A into two parts: one query for loans, and one query for renewals, with a fiscal year filter for each. These two queries are specifically constructed for use in Tableau dashboards | complete |  |  | will be superceded by 184A
NEW CR | 1 |  | CR191A | physical_materials_counts |  | This query is an annual circulation count query of all physical materials holdings. The query can be run as a whole and then filtered for material type based on the details provided at the end of the query, or specified 'Where' statements can be included in the query to obtain data subsets by material type. A fiscal year filter is included, based on the date the item was created. | complete |  |  | posted
NEW CR | 1 |  | CR191B | physical_materials_counts_parts |  | This query is CR191A split into parts, where each part creates a table in the local_core directory. The purpose of this query is to enable users to use data from intermediate tables as needed. | complete |  |  | posted
REV CR | 1 |  | CR134 | appr_invoices_bib_data |  | Approved invoices | complete | Collection Development |  | Nancy fixing several issues
REV CR | 1 |  | CR174 | BD_ILL_counts |  | ILL and BD counts | complete | Annual data dashboard
NEW CR | 1 |  | CR192 | withdrawn_items |  |  | complete | Annual data dashboard
NEW CR | 1 |  | CR193 | filled_delivery_requests |  |  | complete | Annual data dashboard
NEW CR | 1 |  |  | microform count |  | looks in 007 fields of the bib record to find microform records then looks at the call number of the found records, then counts the instance records and the item records attached to those instance records | in progress | Annual Statistics |  | need to reconcile how we obtain the count; use call number as master source; microform count is based on some assumptions; need to add date range parameters; ON HOLD
NEW CR | 1 |  | CR195 | expense transfer |  | This query is a customization of CR-134 (paid invoices with bib data) for the purpose of identifying expenditures -- that can be transferred from unrestricted funds to restricted funds. | complete | Collection Development |  | posted
NEW CR | 1 |  | CR194 | checkouts_and_checkins_by_date_range_and_service_point |  | checkouts and checkins by month and service point | complete | Access Services |  | posted
REV CR | 1 |  | CR134 | approved invoices with bibliographic data for selectors |  |  | complete | Collection Development |  | updated to remove carriage returns and line breaks in title and description fields; [posted
NEW CR | 1 |  | CR134_F | approved invoices with bibliographic data for accounting |  |  | complete | Accounting |  | modified CR134 for finance office; fewer fields; posted
NEW CR | 1 |  | CR196 | lost_laptops_and_equipment |  | This query identifies laptops and equipment with an item status of "Aged to lost," "Declared lost" or "Lost and paid" and displays the loan and borrower information. | complete |  |  | posted
NEW CR | 1 |  | CR197 | physical_materials_counts_by_marc_format_type |  | This query provides a count of all distinct instances, holdings, and items, by marc format type as classified using the 06 and 07 fields in the Marc leader. It also includes format types based on the old Voyager bib format table, for comparison purposes. | complete | Annual data Collection |  | posted
NEW CR | 1 |  | AHR112 | patron_purchase_requests_Folio.sql |  | This report was created specifically for collection development needs and includes the following fields: requestor netid or other requestor information (where available), fiscal year of payment, title, instance hrid, subject, fund code, days until fulfilled, and total circ count in Folio. | complete | Collection Development |  | posted
NEW CR | 1 |  | AHR113 | patron_purchase_requests_voyager.sql |  | This report was created specifically for collection development needs and includes the following fields: requestor netid or other requestor information (where available), fiscal year of payment, title, instance hrid, subject, fund code, days until fulfilled, and total circ count in Voyager. | complete | Collection Development |  | posted
NEW AHR | 1 |  | AHR114 | microforms_counts_details |  | This query was developed for the 2023 Olin Basement move project, and includes details of microform bibliographic information to help selectors make decisions about moving or de-accessioning the materials. | complete | Collection Development |  | posted | 2023-01-19

## Dashboards
Tableau Dashboards
Dashboard Name | Source Query | Description | Target Audience | Person Responsible | Status | Note
Fund Summary | CR138, CR165 | Provides a current date report of funds and teams with amounts spent, encumbered, and remaining. Also provides the list of split funds purchases for a purchase order line that has multiple funds used along with the transaction amount for each fund and the percentage spent. Data updated daily. | Selectors | Vandana | Test | need to review, as it may no longer be needed
Approved Invoices | CR134 | Provides the list of approved invoices along with invoice payment date, vendor name, invoice number, and other details. Data updated daily. | Selectors | Nancy | Active | revisions completed
Fund Detail with Expense Class |  | Provides a detailed current date report of funds and teams with expense class information. This dashboard provides the list of all active funds along with their ledger, fund group and fund type. It also provides allocations, transfers, encumbrances, expenditures, fund balance and percentage spent for each fund. | Selectors | Nancy | Active | Fund Summary dashboard was merged into Fund Detail with Expense Class
Eusage by Title | NA | Annual data from EBSCO Consolidated files, received twice a year. Data not available in Folio. Data compiled by Sally Lockwood (sjl8) and made available in a BOX folder. | Selectors | Vandana | Active
Eusage by Platform | NA | Annual data from EBSCO Consolidated files, received twice a year. Data not available in Folio. Data compiled by Sally Lockwood (sjl8) and made available in a BOX folder. | Selectors | Vandana | Active
Fund Expenditures by PO Line Invoice Payments | CR101 | Shows fund expenditures by purchase order line. For each purchase order line number, details shown are fund ID, fund code, fund name, fund group, fund type and purchase order line transaction amount. Filters are included for all these details as well as for transaction type (credit or payment). When the transaction type is "Payment," the transaction amount is shown as a positive value. When the transaction type is "Credit," the transaction amount is shown as a negative amount. | Selectors | Vandana | Active | need to review, as it may no longer be needed
Physical collections use | CR184B, CR174, CR192, CR193 | Provides counts of physical collections use (loans, renewals) with filters for owning library, patron group, material type, and collection type (regular, equipment, etc.) Also shows withdrawn items, filled delivery requests, and counts of BD/ILL. | All Staff | Vandana | Revision | need to get data from automated reports to get correct time of day because Tableau converts dates to UTC, adding 4 hours
Requests | CR107 | Provides counts of patron requests (hold, page, recall) with filters for patron group, owning library, request status, and requests type. | All Staff | Vandana | Active
Circulation Desk Transactions | CR108 | Provides counts of circulation desk transactions by month, day, date, and time of day, with filters for material type, request type, and action type (checkin or checkout). | All Staff | Vandana | Revision | need to get data from automated reports to get correct time of day
Missing and In Transit Items | CR106 ; CR118 | Provides a list of all items that have an item status of 'missing', including item details, with filters including Library, permanent location, missing status date, call number and LC class. Also contains a separate view for list of items where item status is 'in transit', along with item details and a filter for number of days in transit. If items haven't been checked in at the home location (permanent location) after a specified time period, the items might have been lost or misplaced on their way back to their home location. | All Staff | Vandana | Active
BD/ILL Counts and Details | CR171, CR172, CR174 | Provides counts as well as details of BD/ILL loans from CUL to other universities, and from other universities to CUL. For loans to CUL, title names are available, but no further information about the title is available. Patron group and department names are included when available. | Selectors | Vandana | Active
Patron purchase requests | CR173 | Lists patron purchase requests since 7-1-22. Details include fund code, LC class, subject, title, holdings location, PO line number, receipt date, request date, and amount. Filters include PO line receipt status and PO line payment status. | Selectors | Vandana | Active
Team_Related Split Funds | CR175 | Shows split funds by PO line that enables selectors to filter by the funds for their team while also seeing what other team funds split a purchase order payment with them. There is a separate view for each team. | Selectors | Nancy | Active
Physical Materials Counts | CR191 | Annual data dashboard; shows counts for all physical materials by format type. | All Staff | Vandana | in progress
E-materials Counts |  | count of electronic materials by format type | All Staff | Vandana | not started
Purchase Orders | CR123 | Shows open purchase orders and their encumbrance and/or amount paid, broken down by purchase order lines. Three views of the purchase order data provide an order summary, orders by title, and a purchase order search. | Selectors | Sharon | in progress | may supercede CR101 dashboard, will include second query with focus on encumbrances
Physical collections use | CR184A, CR174, CR193 | loans, renewals, ILL, BD, and filled delivery requests | All Staff | Vandana | Active
FBO Daily Reports |  | This dashboard was created to assist the Finance and Budget Office team with Daily Reconciliation. It provides the total amount of vouchers for the most recent day of approvals. It also splits the total amount of vouchers approved sent to KFS and the ones approved manually. It also provides the YTD transactions amount. Search vouchers and paid invoices by date range is also available. Downloads to add to KFS Distribution of Income and Expense documents can be performed. | FBO | Nancy | Active
FBO Invoices Reviewed Status |  | This dashboard was created to assist the Finance and Budget Office team with gathering information about invoices in reviewed status. It also provides the list of invoices in reviewed status for which no fund and/or expense class have been selected in Folio. Search for invoice lines and adjustments data can also be performed. | FBO | Nancy | Active
FBO Vouchers Date Range |  | This dashboard was created to assist the Finance and Budget Office team with Reconciliation. This dashboard is similar to the FBO Daily Reports dashboard, but only provides vouchers information searchable by voucher approval date. This dashboard will be useful for late process of KFS Distribution of Income and Expense documents and to verify voucher amounts from previous dates. | FBO | Nancy | Active

## Target 1-19-23
Report Type | Cornell Priority | Report Requirement | CR Numbers | Cornell Report Name | TDX Number | Summary | Cornell Query Status | Functional Area | Description | Notes | Target Date
NEW AHR | 1 |  | AHR114 | microforms_counts_details |  | This query was developed for the 2023 Olin Basement move project, and includes details of microform bibliographic information to help selectors make decisions about moving or de-accessioning the materials. | complete | Collection Development |  | posted | 2023-01-19

## Target 2-2-23
Report Type | Cornell Priority | Report Requirement | CR Numbers | Cornell Report Name | TDX Number | Summary | Cornell Query Status | Functional Area | Description | Notes | Target Date
ORIG CR | R2 | REP-36 |  | donor_report |  | Report to donor | in progress | Collection Development | generate reports of titles purchased by endowed funds--sent to the donor Â For Cornell, this may not be needed for bookplating. AAD still needs a donor letter report.Â | need to add fund description field | 2023-02-02
NEW CR | 1 |  |  | open_orders_encumbered |  |  | in progress | Collection Development |  | new query to focus on encumbrance details of orders | 2023-02-02

## Data Integrity Testing
LDP Data Integrity Testing Queries
name | description | published
test_circulation_loans_dates | pulls the loan_date from the public.circulation_loans table | 2022-08-31
test_holdings_ext_dates | pulls the created_date from the folio_reporting.holdings_ext table | 2022-09-01 | `
test_holdings_ext_record_count | counts the number of holdings records created by date, from the holdings_ext derived table | 2022-09-04
test_instance_ext_dates | pulls the status_updated_date from the folio_reporting.instance_ext table | 2022-08-31
test_instance_ext_record_count | counts the number of instance records created, using the instance_ext derived table | 2022-08-31
test_inventory_holdings_record_count | finds the number of holdings records created by date, using the inventory_holdings public table | 2022-08-31
test_inventory_instances_by_create_date | counts inventory instances by create date | 2022-08-31
test_inventory_instances_record_count | counts the number of instance records created by date from the inventory_instances public table | 2022-08-31
test_inventory_items_record_count | counts the number of item records created by date, using the inventory_items public table | 2022-08-31
test_item_ext_dates | pulls the created_date for items from the folio_reporting.item_ext table | 2022-08-31
test_item_ext_record_count | counts the number of item records created by date, using the item_ext derived table | 2022-08-31
test_loans_by_netid | allows you to view loans by a user's net ID | 2022-09-03
test_loans_items_dates | pulls the loan_date from the folio_reporting.loans_items table | 2022-08-31
test_key_counts | provides counts for instances, holdings, items, srsmarctab instances, and srsrecord instances | 2022-10-13

## Derived Tables
Derived Tables for Nolana 1.5 Release | published
invoice_lines_adjustments | 2022-11-08
invoice_lines_adjustments_fund_distributions | 2022-11-08
invoice_lines_fund_distributions | 2022-11-08
invoice_transactions | 2022-11-08
po_instance | 2022-11-08
po_lines_details_subscription | 2022-11-08
po_lines_locations | 2022-11-08
po_lines_tags | 2022-11-08
po_lines_vendor_reference_numbers | 2022-11-08
po_ongoing | 2022-11-08
po_organizations | 2022-11-08
po_prod_ids | 2022-11-08
finance_transaction_purchase_order | 2022-11-08
item_ext | 2022-11-08
instance_administrative_notes | 2022-11-08
holdings_administrative_notes | 2022-11-08
instance_identifiers | 2022-11-08
holdings_tags | 2022-11-08

## Dependencies
Reporting Dependencies |  | Time Frames
1 | completed development of data elements needed by the report in the associated FOLIO application (by FOLIO Core Developers)
2 | FOLIO application development release dates - delayed releases delay the availability of data elements needed in reports
3 | availability of people on the CUL reporting team to help develop report templates in SQL, adapt them for Cornell's specific needs, and test them in Cornell's LDP reporting database environment (CUL Reporting Core Team members) | continuous
4 | availability of SRS MARC data in the LDP reporting database (part of LDP 1.2 software release) | made available July 2021
5 | scalable solution for CUL reporting users to have access to the Cornell LDP | made available July 2021
6 | availability of people on the FOLIO project to develop report templates in SQL, test them, and write query documentation (Reporting SIG members) | continuous
7 | availability of a Cornell LDP test environment with a broad data set to refine and test each report for Cornell's needs using Cornell data | made available October 2022
8 | local, Cornell-only FOLIO application configuration and data entry decisions impact how and what data are displayed in reports
9 | availability of select static Voyager historical tables in the LDP | made available July 2022
10 | availability of Metadb, the next version of LDP software | unknown